## November-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-02-11 | QMVAR-RPA | Debitnoteregister Monthly failure | 100% | Completed | While file was moved to backup failed.Root cause of the issue was file was not closed properly,handled it.Also wild card characters for removing the files in download directory is handled separatley for the service centers.
|  | HAYAAI-B2B | Jobs display for services login | 70% | WIP | For Services
2 | 2020-03-11 | HAYAAi-B2B | Jobs display for services login | 80% | WIP | Service
3 | 2020-04-11 |  | Leave
4 | 2020-05-11 |  | Leave
| 2020-06-11 |  | Leave
| 2020-09-11 |  | Leave
| 2020-10-11 |  | Leave
| 2020-11-11 |  | Leave
| 2020-12-11 |  | Leave
| 13/11/2020 |  | Leave
| 16/11/2020 | Rlogic - GL | Started with Rlogic general ledger task | 40% | WIP
| 17/11/2020 | Rlogic - GL | Rlogic general ledger task | 70% | WIP
| 18/11/2020 | Rlogic - GL | Rlogic general ledger task,completed | 100% | Completed
| 19/11/2020 | Rlogic-GL | Rlogic general ledger task,corrections from Rahman san,done those | 30% | WIP
| 20/11/2020 | Rlogic-PL | P&L,Parts IO donwload done | 30% | WIP
| 23/11/2020 | Rlogic-PL | Formula cauclations from Rahman San as P&L formula changed | 30% | WIP
| 24/11/2020 | Rlogic-PL | Call wise merging with VLOOKUP | 50% | WIP
| 25/11/2020 | Rlogic-PL | Call wise merging with VLOOKUP | 100% | Completed
| 26/11/2020 | Rlogic-PL | Call wise data calculations | 30% | WIP
| 27/11/2020 | Rlogic-PL | Call wise data calculations | 80% | WIP
| 30/11/2020 | Rlogic-PL | Since Callwise data sheet changed,had to modify the code | 80% | WIP

## December-2020
No | Date | Application | Task | % of completion | Status
1 | 2020-12-01 | RLOGIC RPA | RLOGIC P&L | 90% | WIP
2 | 2020-12-02 | RLOGIC RPA | RLOGIC P&L | 100% | Completed
3 | 2020-12-03 | RPA SONY | RPA SONY to enable IE 8 code to work on ie11 | 30% | WIP
4 | 2020-12-03 | RPA SONY | RPA SONY to enable IE 8 code to work on ie11 | 70% | WIP
5 | 2020-12-04 | HAYAAI API | Worked on issues on B2C API | 100% | Completed
7 | 2020-12-07 | HAYAAI API | Worked on issues on B2C API | 100% | Completed
8 | 2020-12-08 | HAYAAI API | Worked on B2B API issue | 100% | Completed
9 | 2020-12-09 | RPA GSPN | Correction received for Purchase Summary,service repair | 100% | Completed
11 | 2020-12-10 | RPA Sony | Tried for windows registry key for avoiding save popup but was not working | 20% | WIP
12 | 2020-12-11 |  | Leave
13 | 2020-12-14 | HAYAAI API | Jobs not created in B2B,hence working on the root cause of the issue | 40% | WIP
14 | 2020-12-15 | HAYAAI API | Corrected the APIs in B2B and B2C to display data in JobSheet and for jobs creation | 80% | WIP
15 | 2020-12-16 | HAYAAI API | Jobs display | 80% | WIP
16 | 2020-12-17 | HAYAAI API | Warranty_type,email,address information added | 80% | WIP
17 | 2020-12-18 | Rlogic GL | GL creation for Rlogic | 80% | WIP
18 | 2020-12-21 | Rlogic GL | GL completion and PL started | 100% | WIP
19 | 2020-12-22 | Rlogic PL | PL creation | 100% | WIP
20 | 2020-12-23 | Sony Asctax | Sony Asctax creation | 60% | WIP
21 | 2020-12-24 | Sony Asctax | Sony Asctax creation and integration | 60% | WIP
22 | 2020-12-28 | Sony Asctax and gsttax | Sony Asctax and gsttax integration | 60% | WIP
23 | 2020-12-29 | Sony Asctax and gsttax | Sony Asctax and gsttax integration | 80% | WIP
24 | 2020-12-30 | Sony Asctax and gsttax | Sony Asctax and gsttax integration,corrections | 90% | WIP
25 | 2020-12-31 | Sony Asctax and gsttax | Leave

## Januray-2021
No | Date | Application | Task | % of completion | Status
1 | 2021-04-01 | Samsung RPA | DebitNite Register error correction,Invoice update correction | 100% | Completed
2 | 2021-05-01 | RPA SONY | ApNewsis Report no data error,correction | 60% | Completed
3 | 2021-06-01 | Samsung RPA | Invoice update correction for loading file | 100% | Completed
4 | 2021-07-01 | RPA SONY | ApNewsis Report error,correction | 70% | WIP
5 | 2021-08-01 | HAYAAI API | updateimei error not updating imei no,corrected | 100% | Completed
7 | 2021-11-01 | HAYAAI API | Add partner error correction in B2B | 60% | Completed
8 | 2021-12-01 | HAYAAI API | Add partner error correction in B2B | 70% | Completed
9 | 13/01/2021 | HAYAAI API | Add partner error correction in B2B | 100% | Completed
11 | 18/01/2021 | HAYAAI API | Product information for Service Request in B2B | 60% | WIP
12 | 19/01/2021 | HAYAAI API | Manually created jobs doesn't show in the list - | 100% | Completed
13 | 20/01/2021 | HAYAAI API | view job in SR throwing error | 100% | Completed
14 | 21/01/2021 | HAYAAI API | Failure description in SR and JOB shows wrongly | 100% | Completed
15 | 22/01/2021 | Rlogic GL | Warranty Status not get displayed in Jobs page | 100% | Completed
16 | 25/01/2021 | Rlogic PL | PL Generated | 100% | Completed