## July-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/07/2021 | QMVAR | Weeekly Revenue calculation part going on
2 | 02/07/2021 | QMVAR | Weekly Revenue Report calculation part done
3 | 03/07/2021 | WeekEnd
4 | 04/07/2021 | WeekEnd
5 | 05/07/2021 | QMVAR | Weekly Revenue Report service center implemention show msg going on
6 | 06/07/2021 | QMVAR | Weekly Revenue Report service center implemention show msg going on
7 | 07/07/2021 | QMVAR | Monthly Target screen implementation going on
8 | 08/07/2021 | QMVAR | Monthly target screen search option implementation going on
9 | 09/07/2021 | QMVAR | Montly Target screen search four options implemented and tested
10 | 10/07/2021 | WeekEnd | Montly Target screen search options sent to mohan san
11 | 11/07/2021 | WeekEnd | Fixed issues in monthly search option as per mohan san suggestion
12 | 12/07/2021 | QMVAR | Weekly Revenue report div error issue code implementation going on
13 | 13/07/2021 | QMVAR | Weekly Revenue report div error issue code implementation going on
14 | 14/07/2021 | QMVAR | Div error fixed and sent to Mohan san
15 | 15/07/2021 | QMVAR | As per client requirement previous month report generation implementation going on in a single result
16 | 16/07/2021 | QMVAR | Previous month report generation going on
17 | 17/07/2021 | WeekEnd | Previous month report done and datas testing going on
18 | 18/07/2021 | WeekEnd | Previous month report done and datas testing going on
19 | 19/07/2021 | QMVAR | Previous month report done and graph dotted line implementation going on
20 | 20/07/2021 | QMVAR | Graph Implementation going on
21 | 21/07/2021 | Hoilday | Bakrid (Graph implementaion done and testing going on)
22 | 22/07/2021 | QMVAR | As per client server db datas comparision and checking going on for Apr,mon,june months
23 | 23/07/2021 | QMVAR | As per client server db datas comparision and checking going on for Apr,mon,june months
24 | 24/07/2021 | WeekEnd | As per client server db datas comparision and checked for Apr,mon,june months sent to Mohan san
25 | 25/07/2021 | WeekEnd
26 | 26/07/2021 | QMVAR | Mohan san finding decimal issues in report datas and graph issues fixed and sent to mohan san
27 | 27/07/2021 | QMVAR | Based on requirement week end datas calculation as per dynamic in graph generation going on
28 | 28/07/2021 | Leave | Personal Leave
29 | 29/07/2021 | QMVAR | Weekly graph dynamic code generation going on
30 | 30/07/2021 | QMVAR | Weekly Graph dynamic code generation completed sent to deployment
31