## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | RPA SAMSUNG | Correction Received for DRS-Monthly, SAW Discount Monthly and ReturnCredit Monthly tasks | 100% | Completed |  | Pending
2 | 2020-10-01 | RPA SONY | A 7 files are uploaded with customization in single approach for Scheduling Reports tasks | 70% | WIP |  | Completed
3 | 2020-10-05 | RPA SAMSUNG | 1. DRS-Weekly correction received and completed | 100% | Completed |  | Hold
|  |  | 2. Return Credit Correction received and completed | 100% | Completed
4 | 2020-10-05 | RPA SONY | Daily Task of Scheduling Report has been completed for download and upload (11 files except one is having upload issue which under progress by Mohan san) | 100% | Completed
5 | 2020-10-06 | RPA SAMSUNG | 1. DRS-WeeKly task of SSC8 , Correction has been done | 100% | Completed
|  |  | 2. DRS-DAILY task of SSC11, Correction has been done | 100% | Completed
6 | 2020-10-06 | RPA SONY | 1. SchedulingReport daiky has been completed | 100% | Completed
|  |  | 2. Scheduling Report Monthly task has been completed | 100% | Completed
7 | 2020-10-07 | RPA Sony | For Sony_Daily_SchedulingReport task,
|  |  | 1. method created to delete all specific pattern files before downloading the Sony daily scheduling report | 100% | Completed
2. method created to delete all specific pattern files before creating CSV files to upload from temp folder for the task Sony daily scheduling report
8 | 2020-10-08 | RPA Sony | Correction at Sony_Daily_SchedulingReport task has been done related to unicode error | 100% | Completed
9 | 2020-10-09 | RPA Sony | Customization work is in progress for Sony daily task of scheduling report | 60% | WIP
10 | 2020-10-12 | RPA Sony | 1. Customization of Sony Schedule Report of Daily task has been completed | 100% | Completed | Updated codes has been shared
|  |  | 2. Customization of Sony Schedule Report of Monthly task is work in progress | 60% | WIP
11 | 2020-10-13 | RPA Sony | 1. Customization of Sony Schedule Report of Daily task has been completed (with enhanced corrections) | 100% | Completed
|  |  | 2. Code included for SchedulingReport to give manual captcha | 100% | Completed
12 | 2020-10-13 | RLOGIC DEMO | 3. RPA Demo prepared and tested for the RLOGIC | 100% | Completed
13 | 2020-10-14 | RLOGIC DEMO | 1. Supported/Prepared for Demo Presentation | 100% | Completed
14 | 2020-10-14 | RPA Sony | 2. Correction work supported to Daily task of schedule_report for record count, and upload issue | 80% | WIP
15 | 2020-10-15 | RPA Sony | 1. Correction work supported to Sony task of scheduling report for file movement to backup folder and record count issue are fixed for the daily and monthly tasks | 100% | Completed
16 | 2020-10-15 | RLOGIC | 2. A set up has been established and GL,PL and RPA management files are copied(supported for installation and testing) and tested for the purchase summary from GSPN at RLOGIC system | 100% | Completed
17 | 2020-10-16 | RPA SAMSUNG | 1. Correction supported to the communication board task to clear pending notices | 90% | WIP
18 | 2020-10-16 | RPA SAMSUNG | 2 Correction of Password Management task is pending | 70% | WIP
19 | 2020-10-19 | RLOGIC | 1. Downloading DRS task done | 100% | Completed
|  |  | 2. Downloading InvoicePDF task done (downloading pdf, pdf to csv) | 100% | Completed
20 | 2020-10-19 | RPA SAMSUNG | 1. Correction of Password Management has done. | 100% | Completed
21 | 2020-10-20 | RPA Sony | 1. Went to the office to support the System Admin towards formatting, windows 7 installation and office 365 softwares are installed at Oldbot | 90% | WIP
|  |  | 2. and office365 has been installed at newbot | 100% | Completed
22 | 2020-10-20 | RLOGIC | 3. Warranty task has been done towards download | 100% | Completed
21 | 2020-10-21 | RPA SAMSUNG | 1. Manual date input has been implemented in warranty task | 100% | Completed
22 | 2020-10-21 | RPA SAMSUNG | 2. Corrections work supported for the Password management has been done | 100% | Completed
23 | 2020-10-21 | RPA SONY | 3. Correction work is in Progress for the scheduling reports(11 files task) | 60% | WIP
24 | 2020-10-22 | RPA SONY | 1. Correction has been completed for Sony Daily Scheduling Report (), | 100% | Completed | Code shared
2, failed files are to moved backup folder
3. records count correction and testing)
4. manual input date method implementation
25 | 2020-10-23 |  | Leave | Leave
26 | 2020-10-27 | RPA SONY | The below pointes are fixed at schedulingreport monthly task: 1. records counts are corrected, 2. failed files will be moved to backup, 3. success files also be moved to backup, 4. 100000 passwords are generated and stored as valid and invalid pwd at csv for password management, 5. manual date input logic can not be implemented at monthly task as it contains only previous month folder and others are daily folders(noticed to mohan san) | 100% | Completed
27 | 2020-10-27 | RLOGIC | 1. Created a report of Profit and Loss of Rlogic task | 100% | Completed
28 | 2020-10-27 | RPA SONY | 2. For schedulingreport task, uploading issue at MVS site, and it is in Progress | 90% | WIP
29 | 2020-10-28 | RPA SONY | 1. Uploading issue was at SchedulingReport daily task due to Invalid data presents in the csv file and it has been fixed | 100% | Completed
30 | 2020-10-28 | RPA SAMSUNG | 2. Uploading issue was at Warranty task due to special characters (tick mark symbol) presents and it has been fixed | 100% | Completed
31 | 2020-10-28 | RPA SAMSUNG | 3.Second approach has been implemented at Communicationboard task | 90% | WIP
32 | 2020-10-29 | RLOGIC | 1. Setup, Established and tested to give a RPA Management template demo towards RLOGIC, In addition GL, and PL and executed a predemo with Rahman san | 100% | Completed
33 | 2020-10-30 | RPA SAMSUNG | 1. Second Approach has been implemented at Communicationboard task, notice titles can be stored in database once all notices are cleared, tested in all SSCs and running smoothly | 100% | Completed
34 | 2020-10-30 | RLOGIC | 2. R & D has been done to convert a project files to exec and create a trial version | 50% | WIP

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | RPA SONY | Conversion issue during CSV files creation at Sony Daily SchedulingReport task has been fixed, tested and running smoothly for all 11 files | 100% | Completed
2 | 2020-11-02 | RPA SAMSUNG | Upload issue at RETURNCREDIT MONTHLY task has been fixed, tested and running smoothly | 100% | Completed
3 | 2020-11-02 | RPA SAMSUNG | Conversion issue during CSV files creation at SAWDISCOUNT Monthly task is going on | 80% | WIP
4 | 2020-11-03 | RPA SAMSUNG | Conversion issue has been fixed and tested in all SSCs for the task of SawDiscountMonthly and running smoothly from to download to csv and uploading success | 100% | Completed
5 | 2020-11-03 | RPA RLOGIC | 1. Prepared and supported for RLOGIC client demo GL/PL/RPA Management | 100% | Completed
6 | 2020-11-04 | RPA RLOGIC | 1. Extened warranty task has been established and tested for the given user and running smoothly to download and csv file creation etc | 100% | Completed
7 | 2020-11-04 | RPA SAMSUNG | 2. Correction at Warranty task has been fixed and tested in all SSCs, running smoothly from download to upload | 100% | Completed
8 | 2020-11-04 | RPA SONY | Tested and supported for Sony RPA at Oldbot after installation of sony certificate, still date fields are not working properly for RPSI Enquiry, Inboundlist, Outboundlist etc | 80% | WIP
9 | 2020-11-05 | RPA RLOGIC | 1. Log has been implemented at DRS download | 100% | Completed |  | Status
|  |  | 2. Converted Python script to Exe(Trial Version) for the DRS download and tested and running smoothly | 100% | Completed |  | WIP
|  |  | 3. Converted Python script to Exe (Trial Version) for RPA Management, tested and running smoothly | 100% | Completed |  | Pending
|  |  | 4. Sending email with attachments has been done for RPA Management template | 100% | Completed |  | Completed
10 | 2020-11-06 | RLOGIC | 1. Trial version Exe has been tested and functioning as expected for RPA Management Template | 100% | Completed |  | Hold
|  |  | 2. Log has been implemented to Warranty, InVoicePDF etc | 100% | Completed
|  |  | 3. Communicationboard task is implemented, tested and running smoothly | 100% | Completed
11 | 2020-11-09 | RLOGIC | 1. Log has been implemented at RPA Management template and converted as Exec file and placed at Scheduler to run daily 6:00 AM | 100% | Completed
|  |  | 2. Communication board task has been converted as Executive file and placed in Scheduler to run daily at 18:00 | 100% | Completed
12 | 2020-11-10 | SONY RPA | 1. Correction Received due to conversion issue at Sony Daily of scheduling report task and same had been fixed, tested, running smoothly to download,conversion and uploading | 100% | Completed
|  |  | 2. Supported to fix IE issue to ap-new-sis site at Oldbot with Mr Amit and Mr Oniel and issue fixed, manually site can be accessed, whereas, dynamically IE is not launching this | 60% | WIP
13 | 2020-11-10 | RLOGIC | 3. InvoiceUpdatePDF task are fine tunned to convert EXEC | 100% | Completed
14 | 2020-11-11 | RPA SONY | Supported to SONY task to luanch IE and it has been fixed at Oldbot, whereas we could not run the script to download and convertsion due to internet security and it is work in progress | 60% | WIP
15 | 2020-11-12 | RPA SONY | 1. Sony daily of OutboundList has been to download and CSV conversion at OldBot with IE11 | 100% | Completed
16 | 2020-11-12 | RLOGIC RPA | 2. While opening the Management model report of xlsx file, we have made the Management Sheet to active | 100% | Completed
|  |  | 3.In GL, InvoiceUpdate sheet has been created from the RLOGIC sheet received | 100% | Completed
17 | 2020-11-13 | RPA RLOGIC | 1. Downloaded DRS and Warranty Files from GSPN to generate Calls count report etc for October-2020 | 100% | Completed
|  |  | 2. Downloaded InvoiceUpdatePDF to generate InvoiceUpdate summary report with client provided data | 100% | Completed
|  |  | 3.Extended warranty report generated from the GSPN data | 100% | Completed
|  |  | 4. RPA Management Model report generated | 100% | Completed
|  |  | 5.Tested with Mr Rahaman to verify the data | 100% | Completed
18 | 2020-11-16 | RPA RLOGIC | 1. Downloading Warranty and DRS, generated to Calls count report | 100% | Completed
|  |  | 2. Converted warranty xls to CSV using pure python | 100% | Completed
|  |  | 3. Converted DRS xls to CSV using pure python is work in Progress | 60% | WIP
19 | 2020-11-17 | RPA RLOGIC | 1. Converting DRS to CSV using pure python has been completed | 100% | Completed
|  |  | 2. Creating WRTY_DRS.xlsx of merging (both warranty and DRS based on asc claim no) | 100% | Completed
20 | 2020-11-17 | RPA SONY | 1. Converting xls to CSV for SendRepairedReport1605588144058700.xls (from Mohan san) | 100% | Completed
21 | 2020-11-18 | RPA RLOGIC | 1. Created RPA Management model reports based the P and L reports | 100% | Completed
|  |  | 2. Code has been implemented to convert as Exec for General Ledger | 100% | Completed
22 | 2020-11-19 | RPA RLOGIC | 1. Prepared and Supported to RLOGIC tasks
2. discussion with Rahman san and Mamatha san for Rlogic live
|  |  | 3. Working on new logic gave by Rahman san for DRS, Warranty and Invoice Update etc | 60% | WIP
23 | 2020-11-20 | RPA RLOGIC | Creating DRS_WRNTY_InvoiceUpdate merge task is work in progress to get callwisedata report and callscount reports | 80% | WIP
24 | 2020-11-23 | RPA RLOGIC | Creating DRS_WRTY_INVOICE_SAW and merging based on some conditions (Work in Progress), whereas (Extracted data for the DRS, WRTY, InvoiceUpdate and SAW) | 80% | WIP
25 | 2020-11-24 | RPA RLOGIC | 1. Merging DRS_INV_SAW with WRT based on ClaimNo has been done for P & L | 100% | Completed
|  |  | 2. CallsCount Reports has been generated | 100% | Completed
26 | 2020-11-25 | RPA RLOGIC | Supporting to P and L process till 12:30 and since 12:30 no electric power due to heavy rain with wind | 100% | WIP
27 | 2020-11-26 | RPA RLOGIC | Due to Cyclone, no power supply and it has been restored at 19:30
28 | 2020-11-27 | RPA RLOGIC | Supporting to P and L process (Generating WRTY_DRS_INV_SAW_merging report and CallsCount Report) with updates (correction also corrected in results) | 100% | Completed
29 | 2020-11-29 | RPA RLOGIC | Supporting to P and L process (Generating WRTY_DRS_INV_SAW_merging report and CallsCount Report) with updates (correction also corrected in results) | 90% | WIP | supported on Sunday
30 | 2020-11-30 | RPA RLOGIC | Suppoted to RLOGIC for P&L | 100% | Completed
31 | 2020-11-30 | RPA GSPN | Corrections received for Warranty task and it has been completed from download to upload process | 100% | Completed

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | RLOGIC RPA | RPA Management model reports has been generated for P & L along with Charts, whereas Correcting data label and adding KPI details are pending | 90% | WIP
2 | 2020-12-02 | RLOGIC RPA | RPA Management model report has been generated with all updates (table and charts) and placed it on scheduler to trigger the task and sent email | 100% | Completed
3 | 2020-12-02 | RPA SONY | Tried to run sony task at old bot is in under study | 30% | WIP
4 | 2020-12-03 | RLOGIC RPA | RPA Management model report has been generated based on Final P&L updates (table and charts) and placed it on scheduler to trigger the task and sent email | 100% | Completed
5 | 2020-12-03 | RPA SONY | Research and Development of SQLITE3 database to support SONY | 60% | WIP
6 | 2020-12-04 | RPA SONY | Installation of MySQL, and establishment, testing also done using Python at Oldbot, whereas migration from mssql to mysql is pending | 60% | WIP
7 | 2020-12-07 | RPA SONY | Working on InboundList and OutBoundList task to download | 40% | WIP
and Upload, other tasks are pending like(Part, stock, RPSI)
8 | 2020-12-08 | RPA SONY | Working on Inbound, OutBound, RPSI, PartsOrderList and StockList to download | 60% | WIP
Status
9 | 2020-12-09 | RPA GSPN | Correction received for Warranty task and the issue has been fixed and tested in all SSCs and running smoothly | 100% | Completed |  | WIP
10 | 2020-12-09 | RPA SONY | Customization is going for Inbound, Outbound and RPSI task to download and upload | 60% | WIP |  | Pending
11 | 2020-12-10 |  | Leave |  |  |  | Completed
12 | 2020-12-11 |  | Leave |  |  |  | Hold
13 | 2020-12-14 | RPA SONY | Inbound and OutBound, RPSI and PartsOrder and stocklist are WIP | 70% | WIP
14 | 2020-12-15 | RPA SONY | Integration tasks of Inbound and OutBound, and RPS are completed from download to upload with customization and it is tested and running smoothly | 100% | Completed | Source code shared
15 | 2020-12-16 | RPA SONY | Correction received for the Inbound,Outbound and Rpsi tasks has been fixed | 100% | Completed
16 | 2020-12-16 | RPA GSPN | Correction received for the warranty task has been fixed (special characters issue) and tested in all SSCs and running smoothly | 100% | Completed
17 | 2020-12-16 | RPA SONY | The Password management work is work in progress for the SONY site | 20% | WIP
18 | 2020-12-17 | RLOGIC | Prepared for Rlogic trigger for GL and P&L | 60% | WIP
19 | 2020-12-17 | RPA SONY | Correction Received for the APNEWSIS Task(Inbound,Outbound and RPSI) has been done | 100% | Completed
20 | 2020-12-18 | RLOGIC | Supported to Rlogic to GL, P&L and Management template for the month of Nov-20 | 100% | Completed
21 | 2020-12-21 | RPA SONY | The Password management work is work in progress for the SONY site | 30% | WIP
22 | 2020-12-21 | RPA SONY | Correction received for the APNEWSIS Task to move file to backup, to record log live status and etc has been done | 100% | Completed
23 | 2020-12-22 | RPA SONY | The Password management work is work in progress for the SONY Site | 60% | WIP
24 | 2020-12-23 | RPA GSPN | Task of Password testing at GSPN site is work in progress | 80% | WIP
25 | 2020-12-24 | RPA SONY | The Password management work has been completed, tested and running smoothly | 100% | Completed
26 | 2020-12-24 | RPA GSPN | Task of Password testing at GSPN site has been completed, tested and running smoothly | 100% | Completed | Source code shared
27 | 2020-12-25 | Holiday | Christmas Holiday
28 | 2020-12-28 | RPA SONY | Task of Password testing has been done for the multiple centers and running summothly | 100% | Completed
29 | 2020-12-28 | RPA SONY | Correction received for GSPN Password Testing and it is work in progress | 60% | WIP
30 | 2020-12-29 | RPA GSPN | Correction received for Task of Password testing and it has been done for the multiple centers and running summothly, also recorded the workflow at database during task running | 100% | Completed
31 | 2020-12-29 | RPA GSPN | Correction Received for the warranty task has been fixed (special characters issue) and tested in all SSCs and running smoothly | 100% | Completed
32 | 2020-12-30 | RPA SONY | Sony Password Testing task has been completed and tested in multiple centers and running smoothly | 100% | Completed | Source code shared
33 | 2020-12-31 | RPA SONY | Correction received for sony password changing task and it has been completed | 100% | Completed

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-04 | RPA GSPN | Correction Received for OtherSales for SSC10 and SSC11 tasks, it is work in progress due to unit price not available at GSPN site. | 60% | WIP
2 | 2021-01-04 | RPA SONY | Correction Received Sony Daily task of Inoutrpsi task for the database updation issue and it is work in progress | 40% | WIP
3 | 2021-01-05 | RPA GSPN | The issue at OtherSales task has been fixed and tested in all SSCs and running smoothly from download to upload success | 100% | Completed
4 | 2021-01-05 | RPA SONY | Corrections received for Scheduler Report for Daily & Monthly tasks | 30% | WIP
5 | 2021-01-06 | RPA SONY | 1. Corrections for the Scheduler Report for Daily has been completed and running success(to download on previous month or on first of the current month folder) and also for nodata found case 2. Correction received for Scheduling report of monthly task to download on previous month first day or first day of the current month and the both are fixed | 100% | Completed
6 | 2021-01-06 | RPA GSPN | Record count has been corrected and recorded in database for the othersales task and it has been fixed | 100% | Completed
7 | 2021-01-07 | RPA GSPN | Correction Received for DRS Monthly to run from middle of month to middle month and it is tested and success | 100% | Completed
8 | 2021-01-07 | RPA SONY | Correction received for special characters issue at sony scheduling report monthly task and it has been fixed, tested and running smoothly | 100% | Completed
9 | 2021-01-07 | RPA SONY | Downloading PartsOrder task is work in progress | 60% | WIP
10 | 2021-01-10 | RPA SONY | 1. Downloading PartsOrder task is completed using onscreen data 2. Downloading StockList task is completed using onscreen data | 100% | Completed
11 | 2021-01-11 | RPA SONY | Correction received for the special characters issue and it has been fixed and tested for date 9th and 10th and it is uplaoding success | 100% | Completed
12 | 2021-01-12 | RPA SONY | Correction received for the schedule report task to do rerun the task when a task is getting failure and it has been fixed and tested and running smoothly | 100% | Completed
13 | 2021-01-12 | RPA SONY | Doing R & D for partsorder excel download task | 60% | WIP
14 | 2021-01-13 | RPA SONY | 1. Doing R & D for partsorder excel download task and open option has been disabled | 60% | WIP
15 | 2021-01-13 | Rlogic RPA | 2. Downloading DRS has been done for Dec-2020 3. Downloading InvoiceUpdate PDF files has been done for Dec-2020 4. Converted PDF to CSV file for the InvoiceUpdate 5. Downloading Extendend warranty for P&L has been done for Dec-2020 6. Downloading Purchase summary Excel for Dec-2020 7. Downloading Return Credit for Dec-2020 8. Downloading Warranty excel for Dec-2020 | 100% | Completed
16 | 2021-01-18 | RPA SONY | 1. Downloading PartsOrderReport is success using Chrome browser and CSV conversion and uploading are work in progress | 60% | WIP
17 | 2021-01-19 | RPA SONY | 1. Correction received for the schedulingreport daily task and issue was that records are running on with header and it has been fixed, tested from download to upload and it is success | 100% | Completed
18 | 2021-01-19 | RPA SONY | 2. Customization of the PartsOrderReport task is work in Progress | 70% | WIP
19 | 2021-01-20 | Leave | Leave
20 | 2021-01-21 | RPA RLOGIC | Supported to Rlogic tasks of General ledger for the InvoiceUpdate | 100% | Completed
21 | 2021-01-21 | RPA RLOGIC | Supported to P and L reports like CallsCounts report and merging of DRS_Invoice_Saw with Warranty excel has been done | 90% | WIP
22 | 2021-01-22 | RPA SONY | Correction Received for the record count mismatching at schedulingreport task and it has been fixed and tested, running smoothly | 100% | Completed
23 | 2021-01-22 | RPA RLOGIC | Supported to generate General Ledger report and Profit and Loss report, RPA Template management report | 60% | WIP
24 | 2021-01-25 | RPA RLOGIC | Supported to Generate General Ledger report and Profit and Loss report, RPA Template management report | 100% | Completed
25 | 2021-01-25 | Laptop workshop | Laptop workshop has been attended to speed up incoming and outgoing emails, whereas it could not do due to roundcube issue | 10% | Pending
26 | 2021-01-26 | RPA SONY | Customization of the PartOrderList has been completed and tested, running smoothly from download to upload and it is success | 100% | Completed
27 | 29-01-2021 | RPA SONY | Correction received for the PartsOrderList task and it has been done and it is tested success | 100% | Completed
28 | 29-01-2021 | RPA SONY | Customization of the StockLisReport task has been completed and tested, running smoothly from download to upload and it is success | 100% | Completed

## FEB-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01-02-2021 | RPA RLOGIC | Some customization work is in progress for P&L | 30% | WIP
2 | 01-02-2021 | RPA GSPN | Correction received for the SawDiscount task Monthly and it has been fixed and tested in all SSCs and running smoothly from download to upload | 100% | Completed
3 | 02-02-2021 | RPA GSPN | Correction received for the OtherSales Monthly task and it has been fixed and tested in all SSCs and running smoothly from download to upload | 100% | Completed
4 | 02-02-2021 | RPA SONY | Correction received for Schedulingreport monthly task and it is work in progress | 40% | WIP
5 | 02-02-2021 | RPA SONY | Correction received for Schedulingreport daily task and it is work in progress | 40% | WIP
6 | 02-02-2021 | RPA RLOGIC | Some customization work is in progress for P&L | 40% | WIP
7 | 03-02-2021 | RPA SONY | Correction of Sony scheduling report task has been received for the issue of log not recorded in database for no data found and it has been fixed and whereas a duplicate empty row is created in database during this task running | 90% | Completed
8 | 04-02-2021 | RPA SONY | Correction received for Parts_order_list task and it has been completed and tested and running smoothly from download to upload | 100% | Completed | 1. two extra columns are presented in csv 2. Junk characters in the region column
9 | 05-02-2021 | RPA SONY | 1. Correction Received for the ASCTax (SONY_APNEWSISREPORT_DAILY_V2) and it has been completed and tested from downloading to uploading success | 100% | Completed | 1. two extra columns are presented in csv 2. Junk characters in the region column
10 | 05-02-2021 | RPA SONY | 2. Correction Received for SONY_DELIVERED_SET_DAILY_V1 and it has been completed and tested from download to upload success | 100% | Completed | 1. two extra columns are presented in csv 2. Junk characters in the region column
11 | 08-02-2021 | RPA Token | 1. Tested the token system module to know the workflow is going right and obtained the Customer_Visit,Call_Registered,Repair_Completed,Goods_Delivered,Pending_Calls, Cancelled_Calls andnote from the GSPN and GSPN Token system,and it is tested from downloading to uploading success | 100% | Completed
12 | 08-02-2021 | RPA RLOGIC | Some customization work is in progress for P&L | 60% | WIP
13 | 09-02-2021 | RPA Token | Tested and A small demo has given to Mohan san and it is success | 100% | Completed | Source code has been shared
14 | 09-02-2021 | RPA SONY | Correction received for NO DATA FOUND when no date folder at schedulingreport task and it is work in progress | 50% | WIP
15 | 10-02-2021 | RPA SONY | Correction received for NO DATA FOUND when no date folder at schedulingreport daily task has been completed and tested from download to upload and it is success | 100% | Completed
16 | 10-02-2021 | RPA SONY | Correction received for the SONY_APNEWSISREPORT_DAILY_V2 task has been completed and tested from download to upload and it is success | 100% | Completed | Special characters issue
17 | 11-02-2021 | RPA SONY | Correction Received for the schedulingreport monthly task and it has been completed and tested from download to upload and it is success | 100% | Completed | One extra record count for the each monthly csv file and it is corrected
18 | 11-02-2021 | RPA LOGIC | Some customization work is in progress for P&L | 70% | WIP
19 | 12-02-2021 | RPA GSPN | Correction Received for the Warranty task due to task failed during uploading and it has been corrected, completed and tested in all SSCs and running smoothly from download to upload | 100% | Completed | the issue was that html tag presented within the cell along with texts
20 | 12-02-2021 | RPA LOGIC | Some customization work is in progress for P&L | 80% | WIP
21 | 15-02-2021 | RPA SONY | Correction received for SONY_APNEWSIS_DAILY task and it has been completed and it is tested from download to upload and it is success | 100% | Completed | Issue: the task failed during upload when no data in three integrated task
22 | 15-02-2021 | RPA RLOGIC | Some customization work has been completed for P&L | 100% | Completed | Testing is pending
23 | 16-02-2021 | RPA GSPN | 1. The customization has been completed for the Activity_PendingCalls_RepairCompleted_Note daily task and tested and it is success, the logs are written, task activities are recorded at database(rpalivelog & rpalivestatus), | 100% | Completed | Source code has been shared
|  |  | 2. Other two tasks are work in progress connected with Activity(Token system) report | 20% | WIP
24 | 17-02-2021 | RPA SONY | 1. Correction Received for the Sony Stocklistreport monthly task and it has been completed, tested from download to upload and it is success | 100% | Completed | Issue: the special characters generated during csv file conversion
25 | 17-02-2021 | RPA GSPN | The customization has been completed for the DRS_GOODS_DELEVERED Daily task and it is tested in all SSCs and running from download to upload and it is success, the logs are written, task activities are recorded at database(rpalivelog & rpalivestatus), and the source files are moved to backup folder | 100% | Completed | Source code has been shared
26 | 18-02-2021 | RPA GSPN | The customization has been completed for the CUSTOMER_VISIT Daily task and it is tested in Token sysetm and running from download to upload and it is success, the logs are written, task activities are recorded at database(rpalivelog & rpalivestatus), and the source files are moved to backup folder | 100% | Completed | Source code has been shared
27 | 18-02-2021 | RPA SONY | Correction Received for the stocklistreport monthly task and it has been completed, tested and running smoothly | 100% | Completed | Issue: to store the source filename and uploaded csv filename in database
28 | 19-02-2021 | RPA GSPN | 1. Correction Received for the PendingCalls and Repaircompleted daily task and it has been completed, tested in all SSCs and running smoothly 2. No data found made to zero and etc 3. Dynamically location will be selected based on SSC name at QVMAR | 100% | Completed | Issue: to store no data found condition, and select location dynamically at QVMAR and etc
29 | 19-02-2021 | RPA GSPN | 1. Correction Received for the CallRegistered and CallCancelled daily task and it has been completed, tested in all SSCs and running smoothly 2. No data found made to zero and etc 3. Dynamically location will be selected based on SSC name at QVMAR | 100% | Completed | Issue: to store no data found condition, and select location dynamically at QVMAR and etc
30 | 22-02-2021 | RPA SONY | 1. Correction received for APNEWSYS REPORT DAILY TASK and it has been completed , tested and it is success from Uploading to downloading | 100% | Completed | Issue: Log error for the rerun count has been increased due to frame not found error
31 | 22-02-2021 | RPA GSPN | 2. The correction received for the GOODSDELIVERED task and it has been completed, tested in all SSCs and it is running smoothly | 100% | Completed | Issue: Updation status not found at log file after GOODSDELIVERED has been updated
32 | 23-02-2021 | RPA SONY | 1. Correction received for the scheduling report daily (column issue) task has been completed, tested and running smoothly | 100% | Completed | Issue: two columns are moved unwantedly at CSV file of downloaded
34 | 23-02-2021 | RPA GSPN | Correction recived for the Token system for the password and dynamic location selection at QMVMAR are work in progress | 10% | WIP
35 | 24-02-2021 | RPA GSPN | Correction recived for the Token system for the password and dynamic location selection at QMVMAR are work in progress | 100% | Completed | Issue: to store token's system credential at data and fetch from it to run task
36 | 24-02-2021 | RPA GSPN | Discussion and Research and development to make a Token system as Integrated task | 20% | WIP
37 | 25-02-2021 | RPA GSPN | Integration of Token system tasks is work in progress (Callregister, CallCancelled, CallsPending,Repair Completed, Goods Delivered,Note and CustomerVisit) | 70% | WIP
38 | 25-02-2021 | RPA SONY | Integration of Token system tasks has been completed as Single task (Callregister, CallCancelled, CallsPending, Repair Completed, Goods Delivered,Note and CustomerVisit) and tested in three SSCs and running smoothly | 100% | Completed

## Mar-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01-03-2021 | RPA SONY | Correction Received for Sony PartsOrderList task and it has been completed, tested, due to sony site slow, final test is pending | 30% | WIP
2 | 01-03-2021 | RPA TOKEN | Correction received for the Activity token system and it has been completed, tested and it is running success | 100% | Completed | Issue: CustomerVisit count missing in RPALOG
3 | 02-03-2021 | RPA GSPN | Correction received for the OtherSales Monthly task of SSC7, SSC8 and SSC11, The issue at SSC7 and SSC8 are fixed, tested and it is success, whereas due to more records are at SSC11(around 89 records), still testing is going on | 80% | WIP
4 | 03-03-2021 | RPA TOKEN | Correction received for task of token system and it has been completed, tested and running smoothly | 100% | Completed | Issue: To include total count in log file and database
5 | 03-03-2021 | RPA GSPN | Correction Received for Othersales of SSC11, it is work in progress | 90% | WIP
6 | 04-03-2021 | RPA GSPN | Correction received for the OtherSales Monthly task of SSC11 and it has been fixed , tested and it is running smoothly | 100% | Completed
7 | 05-03-2021 | RPA GSPN | Correction received for the OtherSales Monthly task of SSC11 and it has been fixed , tested and it is running smoothly | 100% | Completed | Issue: 1. Active status is N 2. Non interactable error during data fetch and etc
8 | 08-03-2021 | RPA SONY | 1. Correction received for SONY_APNEWSISREPORT_DAILY to write log file and it is WIP | 20% | WIP | Issue: self second half leave
|  |  | 2. Correction recived for SONY_APNEWSIS_DAILY to write log file and it is wip | 20% | WIP | Issue: self second half leave
9 | 09-03-2021 | RPA SONY | 1. Correction received for SONY_APNEWSISREPORT_DAILY has been completed | 100% | Completed
|  |  | 2. Correction recived for SONY_APNEWSIS_DAILY has been completed | 100% | Completed
|  |  | 3. Correction received for the Activity task has been completed, tested in all SSCs and it is running smoothly | 100% | Completed
10 | 10-03-2021 | RPA GSPN | Downloading DRS and Othersales tasks, converted these into csv files and uploaded it at QMVAR2 URL and it is success | 100% | Completed
11 | 11-03-2021 | RPA GSPN | 1. Correction received for the DRS-Daily task to upload at QMVAR2.0 and also at old MVSTest url and it has been completed, tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
12 | 12-03-2021 | RPA GSPN | 1. The uploading task has been integrated at the below mentionend tasks and tested in five tasks named as 1. Warranty daily, 2. POC daily 3. GRS daily 4.GRD daily 5. ServicePartsReturn task | 100% | Completed
13 | 15-03-2021 | RPA GSPN | The uploading task has been integrated at the below mentionend tasks and tested in two tasks named as 1. Activity Task for the token system, 2. DRS-Weekly task | 100% | Completed
14 | 16-03-2021 | RPA GSPN | The uploading task has been integrated at the below mentionend tasks and tested in two tasks named as 1. OtherSales Monthly task, | 100% | Completed
|  |  | 2. Correction Received DRS-Daily task for wrong record insertion, and it has been corrected, and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
15 | 17-03-2021 | RPA SONY | The uploading task has been integrated at the below mentionend tasks: 1. SONY_PARTS_ORDER_LIST_DAILY Task 2. SONY_SCHEDULE_REPORT_DAILY Task 3. SONY_APNEWSIS_DAILY task | 100% | Completed
16 | 18-03-2021 | RPA GSPN | 1. Correction Received for DRS-Daily task has been completed, tested and it is running smoothly, The uploading task has been integrated at the below mentionend tasks: 2. DRS Weekly Task, 3. DRS Monthly task | 100% | Completed
17 | 19-03-2021 | RPA GSPN | 1. Correction received for DRS-Daily task to give a start date from the first day of month while fetching data and it has been completed, tested and it is running smoothly, | 100% | Completed
18 | 19-03-2021 | RPA SONY | 1. Correction received for scheduling report task to avoid duplicate records in database and it has been corrected, tested and it is running smoothly 2. Correction received for Apnewsis daily task to avoid duplicate records in database and it has been corrected , tested and it is running smoothly | 100% | Completed
19 | 22-03-2021 | RPA GSPN | The uploading task has been integrated at the below mentionend tasks: 1. RETURN_CREDIT_MONTHLY_TASK 2. SAW_DISCOUNT_MONTHLY_TASK | 100% | Completed
20 | 23-03-2021 | RPA GSPN | 1. The uploading task been integrated at StockOverView and it is tested in all SSCs and it is running smoothly 2. Advance date input to the previous day has been implemented at Goods Receiving Summary and 3. Advance date input to the previous day has been implemented at Goods Receiving Details tasks to get all late updated data and it is tested in all SSCs and it is running smoothly. | 100% | Completed
21 | 23-03-2021 | RPA SONY | 4. Correction Received for the SONY APNEWSIS Daily task due to time out and new connection error and it has been fixed and it is tested and it is running smoothly | 100% | Completed
22 | 24-03-2021 | RPA SONY | 1. Correction received for the SONY APNEWSISREPORT DAILY Task and it has been completed and it is tested and it is running smoothly | 100% | Completed
23 | 25-03-2021 | RPA GSPN | 1. Correction Received for the Activity (token system) task, it has been completed, tested in all SSCs and it is running smoothly | 100% | Completed
24 | 26-03-2021 | RPA GSPN | Doing Research and Development in Pandas Library of Python towards Excel data manipulation
25 | 29-0302921 | RPA GSPN | 1. Correction Received for SONY stock list report task due to incomplete download link failure during link extraction and it has been fixed, tested and it is running smoothly from download to upload 2. Correction Received for the DRS daily task due to multiple same file copied to backup folder, it has been fixed, tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
26 | 30-03-2021 | RPA GSPN | Doing Research and Development in Pandas Library of Python towards Excel data manipulation and to close web driver when the task fails and restart the task
27 | 31-03-2021 | RPA GSPN | 1. Correction received for the ACtivity (token system) task, it is work in progress as some updates is going on from 31-03-2021 to 01-04-2021 at samsung site 2. Correction received for DRS daily, whereas we are doubting that DRS and Actvity tasks are simultaneously at a time, wrongly drs of activity task is uploaded with DRS daily task,but it is under study | 60% | WIP | Issue1=>Call register and call cancell data will be zero as updates is going on Issue2=> DRS daily files replaced with DRS of activity task files

## APRIL-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01-04-2021 | RPA GSPN | Based on request, a short demo has been to Mamatha san and Monisha san about Token system | 100% | Completed
2 | 05-04-2021 | RPA GSPN | Correction Received for POC daily task as PO date is 00/00/0000, upload has been failed, Now it is fixed, tested in all SSCs and it is running smoothly from download to upload | 100% | Completed | Issue: 1. PO date was zeros 2. text encoding error
3 | 07-04-2021 | RPA GSPN | Doing Research and Development in Data Visualization using Python Libraries and etc
4 | 08-04-2021 | RPA GSPN | Searching Special Characters in EXCEL Files during CSV Conversion to avoid upload failure due to check your contents issue at QMVAR 2.0 | 50% | WIP
5 | 09-04-2021 | RPA GSPN | 1. Correction Received for the GRS task to change date from five days to three days to search data and it has been fixed, tested and it is running smoothly from download to upload success 2. Correction Received for the GRSummary Details task to change date from five days to three days to search data and it has been fixed, tested and it is running smoothly from download to upload success 3. One special character has been replaced with space during CSV conversion at SSC10 | 100% | Completed
6 | 12-04-2021 | RPA GSPN | 1. Searching Special Characters in EXCEL Files during CSV Conversion to avoid upload failure due to check your contents issue at QMVAR 2.0 and it is completed and it is tested in DRS task and if it is found it then it will be removed with space, 2. Correction Received for Service Part Return Daily task to know about any SSC is having data or data, it is tested in all SSC and it is not having any data | 100% | Completed
7 | 15-04-2021 | RPA GSPN | 1. A small demo has been given to to Prabhu san for the ServicePart Return to clarify regarding the data issue 2. A short demo has been given to Mohan san for the search special characters issue 3. Attended the Zoom meeting with MD(Ramesh san 4. Research and Development about Katalon recorder for RPA which alternative to Selenium | 100% | Completed
8 | 16-04-2021 | RPA GSPN | 1. Enhancing the searching special characters has been completed, tested and it is running smoothly from download to upload for the DRS daily task 2. Special characters are recorded at log file during the task execution has been done in case found | 100% | Completed
9 | 19-04-2021 | RPA GSPN | 1. Enhancing the searching special characters has been completed, implemented at GRSummary and GRS-Details daily tasks , tested and it is running smoothly from download to upload | 100% | Completed
10 | 20-04-2021 | RPA GSPN | 1. Enhancing the searching special characters has been completed, implemented at Warranty daily and Purchase Summary daily tasks , tested and it is running smoothly from download to upload | 100% | Completed
11 | 21-04-2021 | RPA GSPN | The searching special characters has been implemented at the below mentioned tasks: 1. POC Daily task 2. PR Summary task 3. PR Details task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
12 | 22-04-2021 | RPA GSPN | 1. Correction Received for GRS, GRS-Details and ServicePartReturn Tasks due to GSPN site error and it has been corrected by delaying some seconds before starts URL and it has been tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
13 | 26-04-2021 | RPA GSPN | The searching special characters has been implemented at the below mentioned tasks: 1. SAW DISCOUNT Monthly task 2. PARTS IO task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
14 | 27-04-2021 | RPA GSPN | The searching special characters has been implemented at the below mentioned tasks: 1. INVOICE_UPDATE_OOW_MONTHLY_V2 task 2. INVOICE_UPDATE_EXC_IW_MONTHLY_V2 task 3. INVOICE_UPDATE_IW_MONTHLY_V2 task 4. INVOICE_UPDATE_OOW_WEEKLY_V1 task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
15 | 28-04-2021 | RPA GSPN | The searching special characters has been implemented at the below mentioned tasks: 1. RETURN_CREDIT_MONTHLY_V1 task 2. STOCK_OVERVIEW_MONTHLY_V1 task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
16 | 29-04-2021 | RPA GSPN | The searching special characters has been implemented at the below mentioned tasks: 1. OTHER_SALES_MONTHLY_V4 task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
17 | 30-04-2021 | RPA GSPN | The searching special characters has been implemented at the below mentioned tasks: 1. DRS-Monthly task 2. DebitNote Register task QMVAR 2.0 Implementation at the belowmention task 3. Sony scheduling report monthly task 4. Sony StockList Report task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed

## MAY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 03-05-2021 | RPA GSPN | 1.Correction Received for DRS daily task due to input date error and it has been rectified, tested and it is running smoothly | 100% | Completed
2 | 03-05-2021 | RPA SONY | The searching special characters has been implemented at the below mentioned tasks: 1. SONY_APNEWSIS_DAILY_V2 2. SONY_APNEWSISREPORT_DAILY_V2 and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
3 | 04-05-2021 | RPA SONY | The searching special characters has been implemented at the below mentioned tasks:
|  |  | 1. Sony Parts Order List task | 100% | Completed
|  |  | 2. Correction received for the Sony scheduling report monthly task to eliminate the empty record at database and it has been completed, tested and it is running smoothly | 100% | Completed
|  |  | 3. Whereas the Schedulingreport daily task is work in progress | 10% | WIP
4 | 05-05-2021 | RPA SONY | The searching special characters has been implemented at the below mentioned tasks: 1. SONY_SCHEDULING_REPORT DAILY TASK(11 Tasks) and it is tested and it is running smoothly from download to upload | 100% | Completed
5 | 06-05-2021 | RPA SONY | The searching special characters has been implemented at the below mentioned tasks: 1. SONY_SCHEDULING_REPORT MONTHLY TASK(4 tasks) 2. SONY_STOCKLIST_REPORT MONTHLY TASK and it is tested and it is running smoothly from download to upload | 100% | Completed
6 | 07-05-2021 | RPA GSPN | The delay has been implemented at the below mentioned tasks: 1. DRS Daily Task 2. GRS Daily Task 3. GRS-Details Task 4. Warranty Daily Task 5. ServiceReturnParts Daily task 6. PR_Summary Daily task 7. Activity Report Daily task 8. POC Daily task All the tasks has been tested, whereas the Activity task is having additional work and it is WIP, | 100% | Completed
7 | 10-05-2021 | RPA GSPN | Correction received for the ACTVITY TASK due to not updating in database of QMVAR and it has been fixed,tested in all SSCs and it is running smoothly | 100% | Completed
8 | 11-05-2021 | RPA GSPN | 1. Searching special characters has been implemented at DRS-Weekly Task, tested in all SSCs and it is running smoothly 2. The delay has been increased at DRS-weekly and InvoiceupdateOOW-weekly task before url starts and it is tested in all SSCs and the both tasks are running smoothly | 100% | Completed
9 | 12-05-2021 | RPA GSPN | The delay has been implemented at the below mentioned tasks: 1. DRS Monthly 2. PR_DETAILS_10DAYS 3. PR_SUMMARY_10DAYS | 100% | Completed
10 | 12-05-2021 | RPA GSPN | Correction received for GRS Details due to typo error at the CSV contents and it has been rectified, tested in all SSCs and they are running smoothly | 100% | Completed
11 | 13-05-2021 | RPA GSPN | The delay has been implemented at the below mentioned tasks: 1. INVOICE_UPDATE_IW_MONTHLY_V2 2. INVOICE_UPDATE_OOW_MONTHLY_V2 3. INVOICE_UPDATE_EXC_IW_MONTHLY_V2 4. Modified the Activity task at CustomerVisiting Portion due to lockdown | 100% | Completed
12 | 17-05-2021 | RPA GSPN | The delay has been implemented at the below mentioned tasks: 1. OtherSales Monthly task, 2. SawDiscount Monthly task, 3. PartsIO Monthly task 4. ReturnCredit Monthly task and these tasks are tested, and they are running smoothly, | 100% | Completed
13 | 18-05-2021 | RPA GSPN | The delay has been implemented at the below mentioned tasks: 1. STOCK_OVERVIEW_MONTHLY_V1_21May18, 2. SERVICE_PART_RETURN_MONTHLY_V1_21May18, and these tasks are tested, and they are running smoothly, | 100% | Completed
14 | 19-05-2021 | RPA GSPN | 1. Correction Received and new requirements for GRS and GRS_Details task and the both are work in progress | 50% | WIP
15 | 20-05-2021 | RPA GSPN | 1. GRS and GRD tasks are completed with new changes, tested at SSC6, whereas testing on other SSCs are pending | 90% | WIP
16 | 21-05-2021 | RPA GSPN | 1.New changes has been implemented to avoid upload failure due to summary missing at GRD task and it is completed , tested in all SSCs and it is running smoothly | 100% | Completed
17 | 24-05-2021 | RPA GSPN | Prepared for RPA DEMO for usa clients( GL, PL and MGMT Template reports) | 100% | Completed
18 | 25-05-2021 | RPA GSPN | The unused variables, unused userdefined functions and unused modules are removed at the below mentioned tasks: 1. DRS-Daily task 2. GRS Daily task these tasks are tested in all SSCs and they are running smoothly | 100% | Completed
19 | 26-05-2021 | RPA GSPN | The unused variables, unused userdefined functions and unused modules are removed at the below mentioned tasks: 1. GRS-Details-Daily task 2. PR-Summary Daily task 3. The reordering the task series based on day and it has been implemented, tested at PR_Summary only and this task will not run on Sundays 4.these tasks are tested in all SSCs and they are running smoothly 5. whereas, the reordering the task is work in progress for the GRS-Details task | 100% | Completed
20 | 27-05-2021 | RPA GSPN | 1.The task reordering is completed (as logic changed) with database access and delay giving is work in progress and etc, 2. mostly, it will be completed by End of tomorrow as we need to run different aspects test cases at one task of PR_Summary Daily task | 70% | WIP
21 | 28-05-2021 | RPA GSPN | 1. Based on the Mohan san's suggestion, the taskorders series method has been implemented at PR_Summary, tested and it is running smoothly, 2. taskorders function has been defined at dbconn.py file, 3. Correction received for the Activity token system task due to activity report menu was not loaded at SSC6 and SSC7 during upload at QMVAR2.0, and it has been rectified by giving more delay, tested and it is running smoothly 4. we need to implement this approach at others tasks are pending | 100% | Completed
22 | 31-05-2021 | RPA GSPN | 1. Correction received for the Activity due to Report menu not loaded with timeout and it has been completed, tested and it is running smoothly 2. Taskorders has been implemented at the below mentioned tasks: a. DRS _Daily b. Communicationboard daily c. Activity daily | 100% | Completed

## JUNE-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01-06-2021 | RPA GSPN | The below mentioned tasks are implemented with task swap, holiday checks, sunday checks and removing chunk: 1. Communication board daily 2. DRS Daily 3. PR Summary daily 4. Activity daily | 100% | Completed
2 | 02-06-2021 | RPA GSPN | 1. A new updates has been done for the DRS-Daily and Activity Daily tasks and it will not run on Saturdays and Sundays(which is new updates) and some new logs are written at log file during task execution, tested and it is running smoothly 2. Supported for RPA demo perparation | 100% | Completed
3 | 03-06-2021 | RPA UIPATH | Research and Development in UIPATH TOOL | 10% | WIP
4 | 04-06-2021 | RPA UIPATH | 1. The upload has been done at MVSTEST using UIPATH TOOL 2. Research and Development in UIPATH TOOL | 30% | WIP
5 | 07-06-2021 | RPA UIPATH | 1. The upload has been done at MVSTEST using UIPATH TOOL 2. Download has been completed in UIPATH TOOL 3. Email attachments has been done UIPATH TOOL | 100% | Completed
6 | 08-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done 1. POC Daily task 2. DRS Daily task 3. Warranty Daily 4. a few modification has been done at user defined function in dbconn.py file | 100% | Completed
7 | 09-06-2021 | RPA GSPN | The below mentioned steps are completed with 1), Saturday and Sunday checking, 2), Task re-ordering checking, 3), cleaning unwanted codes, 4) Public Holiday checking and etc done To fetch data from from Friday, Saturday and Sunday are work in progress: | 100% | Completed
8 | 10-06-2021 | RPA GSPN | The new changes (to fetch data from Friday, Saturday, Sunday individually on Mondays) has been implemented at activity daily task, tested in all SSCs and it is running smoothly | 100% | Completed
9 | 11-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. PR_SUMMARY Daily 2. COMMUNICATIONBOARD DAILY | 100% | Completed
10 | 14-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. GRS_DAILY_V3_21June14 2. GRS_DETAILS_DAILY_V3_21June14 3. SERVICE_PART_RETURN_DAILY_V4_21June11 | 100% | Completed
11 | 15-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. INVOICE_UPDATE_OOW_WEEKLY_V1_21June15 2. DRS_WEEKLY_V2_21June15 3. DRS_DAILY_V4_21June15 | 100% | Completed
12 | 16-06-2021 | RPA GSPN | The four points (1), Saturday and Sunday checking, 2), Task re-ordering checking, 3), cleaning unwanted codes, 4) Public Holiday checking and etc) are at Implemented at Communication board and PR_SUMMARY tasks and it is tested in all SSCs and it is running smoothly, 1. ACTIVITY_DAILY_V3_21June16 2. POC_DAILY_V1_21June16 3. WARRANTY_DAILY_V3_21June16 | 100% | Completed
13 | 16-06-2021 | RPA GSPN | Correction received for ServicePartReturn task due to task is not ending properly, it has been fixed and tested in all SSCs and it is running smoothly. | 100% | Completed
14 | 17-06-2021 | RPA GSPN | The four points (1), Saturday and Sunday checking, 2), Task re-ordering checking, 3), cleaning unwanted codes, 4) Public Holiday checking and etc) are at Implemented at Communication board and PR_SUMMARY tasks and it is tested in all SSCs and it is running smoothly, 1. PR_DETAILS_10DAYS_V1_21June17 2. PR_SUMMARY_10DAYS_V1_21June17 | 100% | Completed
15 | 18-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. PASSWORD_CHANGE_10DAYS_V1_21June18 2. PASSWORD_CHECK_10DAYS_V1_21June18 | 100% | Completed
16 | 21-06-2021 | RPA GSPN | The four points (1), Saturday and Sunday checking, 2), Task re-ordering checking, 3), cleaning unwanted codes, 4) Public Holiday checking and etc) are at Implemented at Communication board and PR_SUMMARY tasks and it is tested in all SSCs and it is running smoothly, 1. DRS_MONTHLY_V2_21June21 2. The correction received due to upload failure at GRS-Details has been fixed, tested and it is running smoothly | 100% | Completed
17 | 22-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. PARTS_IO_MONTHLY_V1_21June22 2. STOCK_OVERVIEW_MONTHLY_V1_21June22 3. Also corrected the taskorders function to avoid error during task split at dbconn.py | 100% | Completed
18 | 23-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. SAW_DISCOUNT_MONTHLY_V1_21June23 Also, correction received for the GRS and GRS-Details tasks are completed, tested and they are running smoothly: 2. GRS_DETAILS_DAILY_V3_21June23 3. GRS_DAILY_V3_21June23 | 100% | Completed | file not moving to backup folder
19 | 24-06-2021 | RPA GSPN | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. RETURN_CREDIT_MONTHLY_V1_21June24 2. OTHER_SALES_MONTHLY_V4_21June24 | 100% | Completed
20 | 28-06-2021 | RPA SONY | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. SONY_APNEWSIS_DAILY_V2_21June28 2. SONY_PARTS_ORDER_LIST_DAILY_V2_21June28 | 100% | Completed
21 | 29-06-2021 | RPA SONY | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. SONY_SCHEDULE_REPORT_DAILY_V13_21June29 | 100% | Completed
22 | 30-06-2021 | RPA SONY | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. SONY_PASSWORD_CHANGE_10DAYS_V1_21June30 2. SONY_PASSWORD_CHECK_10DAYS_V1_21June30 | 100% | Completed
23 | 30-06-2021 | RPA GSPN | 1. Correction Received for the Communication board due to Failed at SSC7 during alert acknowledge before password update and it has been fixed by increasing the delay and it is running smoothly | 100% | Completed

## JULY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-07-01 | RPA SONY | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. SONY_SCHEDULE_REPORT_MONTHLY_V1_21July01 | 100% | Completed
2 | 2021-07-01 | RPA GSPN | 1. Correction Received for SawDiscount Monthly task due to double quotes error, it has been fixed and it is tested in all SSCs and it is running smoothly | 100% | Completed
3 | 2021-07-02 | RPA SONY | The below mentioned tasks are completed with 1), Saturday and Sunday checking, 2), Task re-ordering, 3), clean unwanted codes, 4) Public Holiday checking and etc done, 1. SONY_STOCKLIST_MONTHLY_V1_21July02 | 100% | Completed
4 | 2021-07-05 | RPA GSPN | 1. Correction Received for Activity daily task due to upload error, it has been fixed and it is tested in all SSCs and it is running smoothly 2. Taken Laptop to service to fix the battery issue | 100% | Completed
5 | 2021-07-06 | RPA GSPN | 1. Correction Received for Activity daily task due to upload error, it has been fixed by increasing delay before click activity report menu and it is tested in all SSCs and it is running smoothly
6 | 2021-07-06 | RPA SONY | 2. SONY_APNEWSIS_DAILY_V2_21July06 is work in progress to implement and to run task if it is Monday | 20% | WIP
7 | 2021-07-07 | RPA SONY | The below mentioned tasks are implemented to run on Mondays to fetch data from Friday to Sunday: 1. SONY_APNEWSIS_DAILY_V2_21July07 2. SONY_PARTS_ORDER_LIST_DAILY_V2_21July07 These tasks are tested, and they are running smoothly. In addition to these, xpath issue at activity task has been corrected, tested and running smoothly | 100% | Completed
8 | 2021-07-08 | RPA SONY | The below mentioned tasks are implemented to run on Mondays to fetch data from Friday to Sunday: 1. SONY_SCHEDULE_REPORT_DAILY_V13_21July08 This task has been tested, and they are running smoothly. | 100% | Completed
9
10 | 2021-07-09 | RPA GSPN | Based on the new requirement for the GRS and Details tasks from Mohan san, started the integration for the GRSummary and Details tasks as single task is work in progress | 70% | WIP
11 | 2021-07-13 | RPA GSPN | 1. Integration of the GRS and GRD tasks as Single task has been completed , tested in all SSCs and it is running smoothly. | 100% | Completed
12 | 2021-07-13 | RPA GSPN | 2. Correction Received at Warranty task due to comma placed at empty cell and it has been fixed, tested in all SSCs and it is running smoothly | 100% | Completed
13 | 2021-07-14 | RPA GSPN | 1. Customer Visit of Token system task is work in pprogress, whereas the workflow from download to upload has been completed and other logics are pending | 70% | WIP
14 | 2021-07-15 | RPA GSPN | 1. Correction Received for GRS-Details task , it has been fixed, tested in all SSCs and it is running smoothly. 2. Record count of Summary and Details are recorded at database 3. User-defined function 'firsttrackrecord' has been modified to avoid None error 4. Old MVS upload has been removed 5. New MVS upload has been implemented | 100% | Completed
15 | 2021-07-16 | RPA GSPN | 1. Customer Visit of Token system task has been completed, tested, and it is running smoothly from download to upload success | 100% | Completed
16 | 2021-07-16 | RPA GSPN | The below mentioned tasks are completed with "http://153.153.161.67/qmvartest/Login.aspx" and Removed the old MVSTEST upload URL: 1. ACTIVITY_DAILY_V3_21July16 2. DRS_DAILY_V4_21July16 3. POC_DAILY_V1_21July16 4. PR_SUMMARY_DAILY_V1_21July16 5. SERVICE_PART_RETURN_DAILY_V4_21July16 6. WARRANTY_DAILY_V3_21July16 These tasks are tested and they are running from download to upload success. | 100% | Completed
17 | 2021-07-19 | RPA GSPN | 1. Correction Received from the Activity task due to short pattern file to remove and it has been fixed by exapnding the pattern and it is tested and it is running smoothly | 100% | Completed
18 | 2021-07-19 | RPA GSPN | The below mentioned tasks implemented with qmvartest and it is tested and it is running smoothly 1. DRS-Weekly 2. DRS-Monthly 3. Stock_Over_View 4. GRS-Daily 5. GRS-Detaily daily | 100% | Completed
19 | 2021-07-20 | RPA GSPN | The below mentioned tasks implemented with qmvartest and it is tested and it is running smoothly 1. OTHER_SALES_MONTHLY_V4_21July20 2. OTHER_SALES_MONTHLY_V4_21July20 | 100% | Completed
20 | 2021-07-22 | RPA GSPN | 1. Correction Received from the warranty daily task: The issue at warranty task due to batchjobs alert is missing after click search, I think the site has been updated at GSPN, However, I have made it to run whether the alert is either coming or not using try/except. It is tested and it is running smoothly | 100% | Completed
21 | 2021-07-22 | RPA SONY | The below mentioned tasks are implemented with qmvartest and it is tested and it is running smoothly. 1. SONY_APNEWSISREPORT_DAILY_V2_21July22 2. SONY_SCHEDULE_REPORT_DAILY_V13_21July22 3. SONY_PARTS_ORDER_LIST_DAILY_V2_21July22 4. SONY_APNEWSIS_DAILY_V2_21July22 | 100% | Completed
22 | 2021-07-23 | RPA SONY | The below mentioned tasks are implemented with qmvartest and it is tested and it is running smoothly. 1. SONY_STOCKLIST_MONTHLY_V1_21July23 2. SONY_SCHEDULE_REPORT_MONTHLY_V1_21July23 | 100% | Completed
23 | 2021-07-26 | RPA GSPN | 1. browser issue (Alert is not working), yet to be fixed for GL tasks (InvoiceUpdate.py) 2. In P and L process, log implementation is going on 3. Correction Received for DRS_weekly due to no data found at SSC2 is work in progress | 50% | WIP
24 | 2021-07-27 | RPA GSPN | 1. Alert issue at DRS and Warranty tasks has been fixed by installing lower version of Chrome, | 100% | Completed
25 | 2021-07-27 | RPA GSPN | 2. Correction Received for GRSummary and Detail due to duplicate record at GRD's CSV file if rerun starts and it has been fixed by deleting the list variable's contents before rerun starts | 100% | Completed
26 | 2021-07-27 | RPA GSPN | 3. whereas, still we are searching for solution to activate alert at chrome is work in progress which is alternate solution | 30% | WIP
27 | 2021-07-28 | RPA GSPN | The new changes has been implemented at the below mentioned tasks due to new changes in browser at GSPN site: 1. DRS_DAILY_V4_21July28 2. WARRANTY_DAILY_V3_21July28 3. GRS_SUMMARY_DETAILS_DAILY_V1_21July28 | 100% | Completed
28 | 2021-07-29 | RPA GSPN | The new changes has been implemented at the below mentioned tasks due to new changes in browser at GSPN site: 1.. POC_DAILY_V1_21July29 2. PR_SUMMARY_DAILY_V1_21July29 3. SERVICE_PART_RETURN_DAILY_V4_21July29 4. CB_DAILY_V1_21July29 | 100% | Completed
29 | 2021-07-29 | RPA GSPN | The below mentioned tasks are work in progress: 1. ACTIVITY_CUSTOMER_TOKEN_DAILY_V3_21July29 2. ACTIVITY_DAILY_V3_21July29 | 70% | Completed
30 | 2021-07-30 | RPA GSPN | The new changes has been implemented at the below mentioned tasks due to new changes in browser at GSPN site: 1. STOCK_OVERVIEW_MONTHLY_V1_21July30 2. DRS_WEEKLY_V2_21July30 3. ACTIVITY_DAILY_V3_21July30 4. ACTIVITY_CUSTOMER_TOKEN_DAILY_V3_21July30 | 100% | Completed

## AUG-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-08-02 | RPA GSPN | The new changes (POPUP at GSPN) has been implemented at the below mentioned tasks and they are tested and they are running smoothly: 1. DRS_MONTHLY_V2_21Aug02 2. SAW_DISCOUNT_MONTHLY_V1_21Aug02 | 100% | Completed
2 | 2021-08-02 | RPA GSPN | 3. OTHER_SALES_MONTHLY_V4_21Aug02 task is work in progress | 50% | WIP
3 | 2021-08-03 | RPA GSPN | 1. Correction Received from Activity task due to wrong selection during updation and it has been fixed, tested and it is running smoothly | 100% | Completed
4 | 2021-08-03 | RPA GSPN | The new changes (POPUP at GSPN) has been implemented at the below mentioned tasks and they are tested and they are running smoothly: 1. OTHER_SALES_MONTHLY_V4_21Aug03 | 100% | Completed
5 | 2021-08-04 | RPA DEMO | 1. Establishing the RPADEMO project structure and customising the InvoiceUpdate task under General Ledger is work in progress, 2. The new changes (POPUP at GSPN) has been implemented at InvoiceUpdate task | 60% | WIP
6 | 2021-08-05 | RPA GSPN | 1. The new requirment task named as ServiceOrderCancelled_V1 has been completed, tested from download, converting xls to CSV file and to upload and it is running smoothly, 2. ServiceOrderCancelled_V1_21Aug05 | 100% | Completed
7 | 2021-08-06 | RPA DEMO | 1. InvoiceUpdate Monthly task has been done till PDF files are downloaded and text extraction from PDF files and InvoiceUpdate.csv file has been created and comparison is pending and it is work in progress | 70% | WIP
8 | 2021-08-09 | RPA GSPN | 1. Correction received at ServiceOrder Cancelled tasks to windows not closing after ending the task and from date has been extended to five days and it has been fixed, tested and it is running smootthly | 100% | Completed
3 | 2021-08-09 | RPA GSPN | 2. Correction received for the Othersales due to wrong from date and todate and it has been fixed, tested and it is running smoothly | 100% | Completed
| 2021-08-09 | RPA DEMO | Thefile InvoiceUpdate.xlsx summary has been created and Integrating with template is work in progress | 70% | WIP
| 2021-08-10 | RPA DEMO | 1. The interation of the Invoiceupdate with template has been completed, testing is work in progress | 90%
| 2021-08-10 | RPA GSPN | 2. Correction received for the ServiceOrderCancelled task due to record count mismatching and it has been fixed , tested and it is running smoothly. | 100% | Completed
| 2021-08-11 | RPA GSPN | 1.The vendor ledger file(xls) is having html tags, hence we are working on that to extract data and convert into csv and read it in pandas to filter based on the doc_type are in progress for the InvoiceUpdate task of the GL, And sometime, we may get xls file as executive file and here also we have to do modification for the received client file. The both are work in progress | 90% | WIP
| 2021-08-12 | RPA GSPN | 1.The vendor ledger file(xls) is having html tags, hence we are working on that to extract data and convert into csv and read it in pandas to filter based on the doc_type are in progress for the InvoiceUpdate task of the GL, And sometime, we may get xls file as executive file and here also we have to do modification for the received client file. The both are work in progress | 100% | Completed
| 2021-08-16 | RPA GSPN | Correction Received for the Communication board task due to the failed while browser launching and it has been fixed for the both tasks like daily and weekly and they are running smoothly. 1. CB_DAILY_V1_21Aug16 2. CB_WEEKLY_V1_21Aug16 | 100% | Completed
| 2021-08-16 | RPA DEMO | 1. Customizing the DRS , Warranty and Extended warranty tasks to download are work in progress which is the part of P&L | 20% | WIP
| 2021-08-17 | RPA DEMO | 1. Downloading DRS, Warranty and Extended warranty tasks are work in progress | 30% | WIP
| 2021-08-17 | RPA DEMO | 2. Integration of GL tasks has been completed, tested and they are generating reports smoothly | 100% | Completed
| 2021-08-17 | RPA DEMO | 3. GL reports are Checked with Rahman san | 100% | Completed
| 2021-08-18 | RPA DEMO | 1. Integration of DRS and Warranty has been completed 2. Merging of DRS csv and Warranty csv files are done 3. and xls to csv also done, tested and it is running smoothly 4. CallsCount Report is work in progress | 60% | WIP
| 2021-08-19 | RPA DEMO | 1. Calls Count Report has been generated for P and L | 100% | Completed
|  |  | 2. Extended warranty task is work in progress | 50% | WIP
|  |  | 3. Supported to Mohan san to establish RPADemo project at server side (for the invoice update task) | 100% | Completed
| 2021-08-20 | RPA DEMO | 1. Extended warranty task has been completed and the test is work in progress for the P&L | 70% | WIP
|  |  | 2. Prepared and supported to RPA demo to the client | 100% | Completed
| 2021-08-23 | RPA DEMO | 1. Extended warranty task has been tested and it is running smoothly 2. Integration of task of drs and warranty are work in progress 3. Integration of extended warranty is work in progress for the P&L | 80%
| 2021-08-24 | RPA DEMO | 1. Integration of DRS and Warranty has been completed for the P&L 2. Integration of Extended Warranty has been completed for the P&L 3. Whereas the testing is work in progress (with entire P&L tasks) | 90%
| 2021-08-25 | RPA DEMO | 1. Integration of P&L with entire tasks has been tested and it is running smoothly and the updated source code had been shared | 100% | Completed
|  |  | 2. Creating RPAManagement template report is work in progress | 70% | WIP
| 2021-08-26 | RPA DEMO | 1. Integration of RPAManagement template has been completed, tested and it is running smoothly and also sending the email with attachment are success, The updated source code has been shared | 100% | Completed
|  |  | 2. whereas the correction received for the GL and PL tasks for the email configuration and etc and it is work in progress | 20% | WIP
| 2021-08-27 | RPA DEMO | Corrections received for the Email sending for GL, PL and RPAManagement, whereas, 1. P&L has been corrected to send email and email with attachment are success, 2. GL and Mgmt templates are work in progress for the email sending as little complexity Note: The RPA management template is sending email with attachment is success as stand alone program | 50% | WIP
| 2021-08-30 | RPA DEMO | 1. Email customization task has been completed for the GL, P&L and Management Template, tested and it is functioning well. | 100% | Completed
| 2021-08-31 | RPS GSPN | Correction received for the below mentioned tasks due to holiday issue and it has been fixed, tested and they are running smoothly. The date issue has been fixed for the below mentioned tasks: 1. SERVICE_ORDER_CANCELLED_DAILY_V1_21Aug31, 2. GRS_SUMMARY_DETAILS_DAILY_V1_21Aug31 3. WARRANTY_DAILY_V3_21Aug31 | 100% | Completed

## SEP-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-09-01 | RPA GSPN | The correction received for the below mentioned tasks due to date issue and it has been fixed, tested and it is running smoothly 1. SERVICE_ORDER_CANCELLED_DAILY_V1_21Sep01 2. WARRANTY_DAILY_V3_21Aug31 | 100% | Completed
2 | 2021-09-01 | RPA GSPN | The Sawdiscount task has been received for the data issue at csv during upload and it is work in progress | 50% | WIP
3 | 2021-09-02 | RPA GSPN | 1. Correction Received for the saw discount has been fixed and error was the double quotes in string of csv file and now it is corrected and tested in all SSCs and it is running smoothly. | 100% | Completed
4 | 2021-09-02 | RPA GSPN | The customiszation of the rlogic tasks has been started and it is work in progress | 10% | WIP
5 | 2021-09-03 | RPA SONY | 1. Correction Received for Sony Scheduling Report daily tasks(11 tasks) due to upload failure and it has been fixed by increasing delay with try/except and it is tested and it is running smoothly. 2. Correction Received for Sony Stock List Monthly task due to upload failure and it has been fixed, tested and it is running smoothly | 100% | Completed
6 | 2021-09-03 | RLOGIC | 1. Downloading has been done for GL and it is completed | 100% | Completed
7 | 2021-09-06 | RPA Demo | 1. Correction Received for the email issue for the GL, P&L, and Management template are work in progress | 70% | WIP
8 | 2021-09-06 | RPA SONY | 2. Correction Received for Sony SchedulingReport daily (11 tasks) for the upload failure and it has been completed, testing is going on | 100% | Completed
9 | 2021-09-07 | RPA SONY | 1. Correction supported for Sony SchedulingReport daily task and also checked with Mohan's san system and it is running smoothly for the task 115 | 100% | Completed
10 | 2021-09-07 | RPA Demo | 2. Downloading DRS and Warranty files are completed for the daily report to the RLOGIC, whereas sending attachment in email is work in progress | 70% | WIP
11 | 2021-09-08 | RPA Demo | 1. Downloading DRS and Warranty files completed 2. Email sending is success 3. Running multiple centers are success 4. Placing tasks at Window Scheduler is success 5. Still few more tests are going on 6. Management Template is completed, whereas testing is work in progress | 100% | Completed
12 | 2021-09-09 | RPA Demo | 1. The entire testing has been done for the GL, P&L, and Management template and all are success 2. DRS and Warranty Daily task has been placed at Task Scheduler and it was executed success and result of it, email with attachments are done and success | 100% | Completed
13 | 2021-09-09 | RPA Demo | 3. Running multiple are to be implemented which is work in progress | 60% | WIP
14 | 2021-09-13 | RPA Demo | 1. Rlogic codes are tested to run multiple centers based on the inputs and it is success ( that is GL, P&L are done) 2. Saw Discount daily report has been downloaded, and it send it in email with attachment and it is success | 100% | Completed
15 | 2021-09-14 | RPA Demo | 1. Running multiple centers are tested for GL, P&L and Management template and they are functioning smooth. | 100% | Completed
|  |  | 2. Developing a program for task execution status is work in progress(success,failed,nodata,data,start time, end time, attached filename etc) | 20% | WIP
16 | 2021-09-15 | RPA Demo | 1. Developed an user-defined function to record task execution steps in csv file, and it has been completed, tested and it is implemented at DRS and Warranty Daily tasks and the testing is going on | 90% | WIP
17 | 2021-09-16 | RPA Demo | 1. Logs report of rlogic has been tested and it is implemented in DRS, WARRANTY and SAW DISCOUNT tasks and it is running smoothly | 100% | Completed
18 | 2021-09-20 | RPA Demo | 1.For macro conversion has been done to the invoiceupdate task of GL using pandas, tested and it is success | 100% | Completed
|  |  | 2. Also supported to the Mr Kalaiarasan and Mr Kabilan towards the Python Learning | 100% | WIP
|  |  | 3. The Other macros are work in progress | 10% | WIP
19 | 2021-09-21 | RPA Demo | 1. macro for copy invopiceupdate and update at summary sheet has been completed and named as gspn_invoice_summary(filename) | 100% | Completed
|  |  | 2. macro of sumtotal has been converted to summary_sumtotal(filename), tested and it is running smoothly | 100% | Completed
|  |  | 3. Also supported to the Mr Kalaiarasan and Mr Kabilan towards the Python Learning process | 100% | Completed
20 | 2021-09-22 | RPA Demo | 1. macro for inserttosummary has been converted into python, tested and it is running smoothly. 2. Also supported to the Mr Kalaiarasan and Mr Kabilan towards the Python Learning process | 100% | Completed
21 | 2021-09-23 | RPA Demo | 1. macro conversion of extended warranty of PL task has been done and named as ew_warranty, tested and it is success | 100% | Completed
|  |  | 2. macro Conversion of text to number macro at Call Wise Data sheet has been completed, and named as callwisedata_text_numbers, and it is tested and it is running smoothly | 100% | Completed