## APR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/06/2021 | QMVAR | 20 issues fixed and tested
2 | 02/06/2021 | QMVAR | 12 issues fixed, tested and sent to deployment
3 | 03/06/2021 | QMVAR | GoogleApis analysis the scenario and 15 implementation done
4 | 04/06/2021 | QMVAR | Google Apis url from internet to local system implemented 20 files
5 | 05/06/2021 | WeekEnd
6 | 06/06/2021 | WeekEnd
7 | 07/06/2021 | QMVAR | GoogleApis 15 files changed in our local applications
8 | 08/06/2021 | QMVAR | GoogleApis 20 files changed and implemented and sent file to deployment
9 | 09/06/2021 | QMVAR | Image conversion from internet url to local should be implemented in all pages in QMVar application.
10 | 10/06/2021 | QMVAR | Mobile View gathering req and analysis the scenario going on
11 | 11/06/2021 | QMVAR | Mobile View finding the root cause going on
12 | 12/06/2021 | WeekEnd
13 | 13/06/2021 | WeekEnd
14 | 14/06/2021 | QMVAR | Mobile View Login screen and dashboard screen done
15 | 15/06/2021 | QMVAR | Navbar and menubar done and 5 screens alignment issues done
16 | 16/06/2021 | QMVAR | Mobile view task done and sent files for deployment
17 | 17/06/2021 | QMVAR | Mobile view task implemented in latest file in Qmvar given by mohansan and tested
18 | 18/06/2021 | QMVAR | Mobile view task sent to deployment and Weekly Revenue report document study started.
19 | 19/06/2021 | WeekEnd
20 | 20/06/2021 | WeekEnd
21 | 21/06/2021 | QMVAR | Weekly Revenue Report gather requirements and analysis the scenario going on.
22 | 22/06/2021 | QMVAR | Weekly Revenue Report analysis the scenario going on.
23 | 23/06/2021 | QMVAR | Weekly Revenue Report db analysis and implementation going on
24 | 24/06/2021 | QMVAR | Weekly Revenue Report db datas checked and tested for all service centers
25 | 25/06/2021 | QMVAR | Weekly Revenue Report Service centers calculation checking going on
26 | 26/06/2021 | WeekEnd
27 | 27/06/2021 | WeekEnd
28 | 28/06/2021 | QMVAR | Weekly Revenue Report Service centers datas Validation implementation going on
29 | 29/06/2021 | QMVAR | Weekly Revenue Report Service centers datas Validation implementation done
30 | 30/06/2021 | QMVAR | Weekly Revenue Report Service centers for report calculation implementation going on
31