## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | VASTU | Checking date time issue | 100% | Completed
2 | 2020-10-01 | RPA Dotnet | Project set up | 100% | Completed
3 | 2020-10-05 | QMVAR | DRS Count - Saw Discount changes and Issue | 100% | Completed
4 | 2020-10-06 | QMVAR | DRS Count - Saw Discount Summary & Details | 50% | WIP
5 | 2020-10-07 | QMVAR | DRS - Daily Revenue | 20% | WIP
6 | 2020-10-08 | QMVAR | DRS - Daily Revenue | 40% | WIP
7 | 2020-10-09 | QMVAR | DRS - Daily Revenue | 50% | WIP
8 | 2020-10-12 | QMVAR | DRS - Daily Revenue | 65% | WIP
9 | 2020-10-13 | QMVAR | DRS - Daily Revenue | 80% | WIP
10 | 2020-10-14 | QMVAR | DRS - Daily Revenue | 100% | Completed
15 | 2020-10-15 | SONIA | Go through Soica Project MDB File Application | 100% | Completed
16 | 2020-10-16 | SONIA | Check Suma Email and Start work application | 10% | WIP
17 | 2020-10-19 | SONIA | Access DB Migration - BIC CAMERA - 1 | 10% | WIP
18 | 2020-10-20 | SONIA | Access DB Migration - BIC CAMERA - 1 | 30% | WIP
19 | 2020-10-21 | SONIA | Access DB Migration - BIC CAMERA - 1 | 50% | WIP
20 | 2020-10-22 | SONIA | Access DB Migration - BIC CAMERA - 1 | 60% | WIP
21 | 2020-10-23 | SONIA | Access DB Migration - BIC CAMERA - 1 | 70% | WIP
22 | 2020-10-27 | SONIA | Access DB Migration - BIC CAMERA - 1 | 85% | WIP
23 | 2020-10-28 | SONIA | Access DB Migration - BIC CAMERA - 1 | 100% | Completed
24 | 2020-10-29 | SONIA | Analyze DB Migration for without Form DB
25 | 2020-10-29 | QMVAR | Help Balaji San for PL Tracking Sheet SONY
Status
WIP
Pending
Completed
Hold

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | SONIA | Changes completed in Bic_Report_soukatsu Project | 100% | Completed
2 | 2020-11-03 | SONIA | Set up file created for BIC CAMERA Module | 100% | Completed
3 | 2020-11-04 | SONIA | Analysis Bic Report Ivc | 100% | Completed
4 | 2020-11-05 | SONIA | Working Bic Report Ivc | 10% | WIP
5 | 2020-11-06 | SONIA | Working Bic Report Ivc | 20% | WIP
6 | 2020-11-09 | SONIA | Working Bic Report Ivc | 30% | WIP
7 | 2020-11-10 | SONIA | Working Bic Report Ivc | 40% | WIP
8 | 2020-11-11 | SONIA | Working Bic Report Ivc | 60% | WIP
9 | 2020-11-12 | SONIA | Working Bic Report Ivc | 80% | WIP
10 | 2020-11-13 | SONIA | Working Bic Report Ivc | 100% | Completed
11 | 2020-11-16 | SONIA | MS Access Program Issue fix | 50% | WIP
12 | 2020-11-17 | SONIA | MS Access Program Issue fix | 100% | Completed
13 | 2020-11-18 | SONIA | Bic_Report_soukatsu | 50% | WIP
14 | 2020-11-19 | SONIA | Bic_Report_soukatsu | 100% | Completed
15 | 2020-11-20 | SONIA | Best_Report_Ivc | 50% | WIP
16 | 2020-11-23 | SONIA | Best_Report_Ivc | 100% | Completed
17 | 2020-11-24 | nMAVAR | nMAVAR Project issue | 100% | Completed
18 | 2020-11-25 | SONIA | Best_Report_Ivc Latest DB issue fixed | 100% | Completed
19 | 2020-11-26 | SONIA | Bic_Report_soukatsu Latest DB issue fixed | 100% | Completed
20 | 2020-11-27 | SONIA | Coordinate SONIA issue | 100% | Completed