## JAN-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-01-03 | RPA RLOGIC | 1. Working on beautification tasks for the P&L summary and GL summary and it is work in progress | 60% | WIP
|  |  | 2. For P&L, Downloaded DRS and Warranty file and merged the DRS,Warranty, InvoiceUpdate and Saw file to create a Call Wise Data for the MLR done | 100% | Completed
2 | 2022-01-04 | RPA RLOGIC | 1. Creating Borders and applying styles to the Summary of the General Ledger and it has been completed, implemented and tested | 100% | Completed
|  |  | 2. Creating Borders and applying styles to the Summary of the Profit and Loss report and it has been completed, implemented and tested | 100% | Completed
3 | 2022-01-05 | RPA RLOGIC | 1. Integration of merging tasks of DRS, Invoice update and Saw files with Warranty are work in progress and it has to be done before creating the callwise data for the P&L(already done) | 90% | WIP
4 | 2022-01-06 | RPA RLOGIC | 1. Created a sample P&L report with new logic for the MLR and BLR without expenses | 100% | Completed
|  |  | 2. P&L report of the HYD is work in progress | 50% | WIP
5 | 2022-01-07 | RPA RLOGIC | 1. P&L reports has been generated for all three centers | 100% | Completed
6 | 2022-01-10 | RPA RLOGIC | 1. Expenses data has been added to the P&L report as separate sheet like callwise data sheet | 100% | Completed
|  |  | 2. Deleted the backup files of the Rlogic daily reports from Sep2021 to Dec2021 | 100% | Completed
|  |  | 3. Deleted the log files from Sep2021 to Dec2021 | 100% | Completed
7 | 2022-01-11 | RPA RLOGIC | 1. Generated the Accounting Statements for the three centers and shared to Rahaman san to verify | 100% | Completed
|  | RPA GSS | 2. Uploading the pdf files task is work in progress for ESA | 10% | WIP
8 | 2022-01-12 | RPA RLOGIC | 1. Correction received for the Accounting Statements for the three centers and completed the correction and shared to Rahaman san to verify | 100% | Completed
|  | RPA GSS | 2. Uploading the pdf files task is work in progress for ESA and it is around 50% has been completed | 50% | WIP
9 | 2022-01-13 | RPA GSS | 1. Uploading PDF files task has been completed, tested and it is uploading smoothly | 100% | Completed
10 | 2022-01-17 | RPA RLOGIC | 1. Removing rows where minus sign at Other Column in the warranty monthly files has been done during append to the previous month file | 100% | Completed
|  |  | 2. ESA task has been tested success at Mohan san's system and confirmed for the ESA today | 100% | Completed
11 | 2022-01-19 | RPA RLOGIC | 1. Generated the Accounting Statements for the three centers and the same had been triggered success | 100% | Completed
|  |  | 2. Generated the P&L reports of the Dec21 for the three centers and shared to Rahman san for the verification | 100% | Completed
12 | 2022-01-21 | RPA RLOGIC | 1. Enhancing the knowledge of Openpyxl and Pandas frameworks towards the RPA automation to handle excel manipulation and involved in the calculation activities | 100% | Completed
|  |  | 2. Also, we are working date filtering with new logic to obtain previous month data if vendor ledger is having three months data and it is work in progress for the GL | 30% | WIP
13 | 2022-01-24 | RPA RLOGIC | 1. P&L has been triggered for the all 3 centers and it is done today | 100% | Completed
|  |  | 2. RPA Management template has been triggered for the all 3 centers and it is done today | 100% | Completed
|  |  | 3. Getting Last month closing balance and taking as current month opening balance, this steps has been implemented at GL and etc | 100% | Completed
|  |  | 4. Some more filtering to be done at Vendor Ledger file for GL to implement is work in progress | 20% | WIP
14 | 2022-01-25 | RPA RLOGIC | 1. A few fine tuning works are work in progress for P&L and GL | 30% | WIP
15 | 2022-01-25 | RPA GSS | 2. New Change request has been received from Mohan san to do customization at GSPN tasks and it is work in progress | 5% | WIP
16 | 2022-01-27 | RPA GSS | We have received the change request for the customization parts at GSPN tasks as follows on 25.01.2022 from Mohan san:
1. We have to fetch the data and upload from the day was working till previous day if the previous day is holiday.
2. if holidays are more than 3 days or more, then we have to split days and download and upload with date splitting
3. if record counts is more than 5000, then again the divide the date or split the date and do the download and upload
|  |  | Note: point 1. has been completed, whereas the testing has been done with Warranty daily task, and other tasks are pending. | 20% | WIP
17 | 2022-01-28 | RPA GSS | 1. Implementation of Public holidays has been done at Warranty task and it is tested and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of Public holidays has been done at ACTIVITY_DAILY task(Token system) and the testing is work in progress | 70% | WIP
18 | 2022-01-31 | RPA GSS | 1. Implementation of Public holidays at GSPN task is work in progress | 20% | WIP

## FEB-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-02-01 | RPA GSS | 1. Correction received from the DRS-Monthly tasks due to 5000 records issue, and it has been fixed, tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
|  |  | 2. Implementation of public holidays is work in progress | 30% | WIP
2 | 2022-02-02 | RPA GSS | 1. Implementation of public holidays is work in progress for the Warranty daily tasks and now the task aimed (based on Mohan san's suggestion) to run on every invidual days on the working day from the last running date and the testing is going on for the warranty daily task | 40% | WIP
3 | 2022-02-03 | RPA RLOGIC | 2. Authentication issue is exist at RLOGIC MLR after recieving the new userid and pwd, we have tested and found that a few menus are missing and it has been noticed to the rlogic today and waiting for the response.
3. Downloading the GL and P&L documenents are started already for the BLR and HYD of the Jan2022.
4 | 2022-02-03 | RPA GSS | 1. 5000 thousands records issue was fixed at DRS Monthly task when record count is equal to 5000 and the testing is going intermittently as the new bot is occupied by Vijay san and Nirmal san, | 90% | WIP
|  |  | 2. Implementation of Public holidays are work in progress | 40% | WIP
5 | 2022-02-04 | RPA GSS | 1. DRS Monthly task has been tested for the 5000 records and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of public holidays has been done Warranty Daily task, tested and running smoothly | 100% | Completed
|  |  | 3. Implementation of public holidays has been done Activity Daily task, tested and running smoothly | 100% | Completed
|  |  | 4. Implementation of public holidays at GRD task(GRSummary with Details task) is work in progress | 10% | WIP
6 | 2022-02-04 | RPA RLOGIC | 5. Cutomization at P&L is work in progress | 30% | WIP
7 | 2022-02-07 | RPA GSS | 1. Implementation of public holidays in GRS_Details is work in progress (50%) (Generating advance date done based on the last run date, and splitting the range of date into groups for the each three days with fdate and tdate as input from the last run) | 50% | WIP
8 | 2022-02-08 | RPA GSS | 1. Implementation of public holidays has been completed at GRS-Details daily task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
9 | 2022-02-09 | RPA GSS | 1. Customization due to Multi-Factor Authentication has been implemented at GRS-Details, tested and it is running smoothly | 100% | Completed
10 | 2022-02-10 | RPA GSS | 1. A 12 daily tasks has been customised due to MFA issue, completed, tested and they are running smoothly | 100% | Completed
11 | 2022-02-11 | RPA GSS | 1. A six weekly tasks has been customised due to MFA issue, completed, tested and they are running smoothly 2. Also modified the reading OTP based on the SSCCODE and email to address, and it is tested and it is running smoothly | 100% | Completed
12 | 2022-02-14 | RPA RLOGIC | 1. We have generated the Accounting statements for all three centers (MLR, BLR and HYD) of the January 2022 and the same had been shared to Rahman san for verification | 100% | Completed
13 | 2022-02-15 | RPA RLOGIC | 1. Reading OTP from the GMAIL is work in progress. | 30% | WIP
14 | 2022-02-16 | RPA RLOGIC | 1. Customization due to Multi-Factor Authentication has been implemented at DAILY-tasks (DRS, WARRANTY, SAW_DISCOUNT, SERVICE_ORDER_MANAGEMENT BULK, COMMUNICATION BOARD CLEAR TASK), and waiting for the OTP process | 80% | WIP
15 | 2022-02-17 | RPA RLOGIC | 1. Research and Development is going on general Captcha issue | 10% | WIP
16 | 2022-02-18 | RPA GSS | The task of Invoice Generation is work in progress | 10% | WIP
17 | 2022-02-21 | RPA GSS | 1. Getting data from the multiple excel files has been done based on the data requirements and whereas updating master file is work in progress for the invoice generation task. | 60% | WIP
18 | 2022-02-22 | RPA GSS | 1. The updating master data file has been completed 50% and other process is work in progress | 70% | WIP
|  |  | 2. Getting cell value along with column number is work in progress | 70% | WIP
19 | 2022-02-23 | RPA GSS | 1. Updating master data file is work in progress as new suggestion has been received from Mohan san, ( we have to extract data pagewise and update to be done based on the configuration file) | 75% | WIP
|  |  | 2. Supported to Captcha issue at token system (RPA GSS)( Now the login is getting success from the six to ten captcha images) and still the task to be tested. | 60% | WIP
20 | 2022-02-24 | RPA GSS | 1. All 11 tasks of monthly has been implemented with MFA with OTP reading, and upload status, tested and it is running smoothly | 100% | Completed
|  |  | 2. Whereas , the task of invoice generation is work in progress | 60% | WIP
21 | 2022-02-25 | RPA GSS | 1. Mr Kabilan san has completed the captcha issue at token system based on the sony captcha code( whereas I have supported to that logical approach and testing), it is tested and running smoothly | 100% | Completed
|  |  | 2. Task of invoice generation has been completed, tested and it is updating at master file success, whereas the integration and formatting the data is work in progress | 80% | WIP
22 | 2022-02-28 | RPA GSS | 1. The task of invoice generation has been completed, tested and it is running smoothly, whereas during testing, mohan san suggesting that after creating csv file, we need to update the master file to avoid memory craking (now it is done dynamically getting data and updating master file dynamically) and it is work in progress | 80% | WIP
2. Athough the captching is working fine, still Mohan has suggested to check 30 or 50 times of the captcha intead of continues checking and we need to enhance the captcha
23 | 2022-03-01 | RPA GSS | 1. In invoice generation task, while updating the master file from the csv file is throwing error : | 85% | WIP
whereas no merging is taking place during update, but, still error is throwing
2. After using lower version of openpyxl, the master file is getting updated success, but somewhere a few formulas are getting error or issue.
Hence, i have uninstalled lower version of openpyxl and it is work in progress.

## MAR-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-03-01 | RPA GSS | 1. In invoice generation task, while updating the master file from the csv file is throwing error : | 85% | WIP
whereas no merging is taking place during update, but, still error is throwing
2. After using lower version of openpyxl, the master file is getting updated success, but somewhere a few formulas are getting error or issue.
Hence, i have uninstalled lower version of openpyxl and it is work in progress.
2 | 2022-03-02 | RPA GSS | 1. In invoice generation task, updating the master file from the csv file has been completed, 2. once updates are over, input files will be moved to backup folder also done, 3. before updating the master file, copy of the master file will be moved to backup folder also done 4. whereas, applying logg is work in progress | 90% | WIP
|  |  | 5. Correction Received for Invoice Update PDF has been fixed, tested and it is running smoothly from download to upload | 100% | Completed
3 | 2022-03-03 | RPA GSS | 1. Invoice_generation has been completed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Task of Service Order Pending is work in progress | 10% | WIP
4 | 2022-03-04 | RPA GSS | 1. Analysing has been done for the task of Service Order Pending from SSC1 to SSC11 at GSPN site
2. No Data Found issue due to no record found
3. No Data Found due to Assigned Engineer row is not presented
4. Fetching row number from the specific location is work in progress
5 | 2022-03-07 | RPA GSS | 1. The task of Service Order Pending is work in progress, and clicking at each cell is success whereas click at each row is having stale error issue. It is a challenging for us to download. |  | WIP
|  | RPA RLOGIC | 1. MFA issue has been fixed at BLR center only, and Following that the daily tasks are success, and we have downloaded the Feb22 files for the GL and PL files are going on for the BLR. | 90% | WIP
6 | 2022-03-08 | RPA GSS | 1. Till downloading the excel files has been completed for the Service Order Pending task after clicking at each row and each cell, 2. Conversion of xls to csv file is work in progress. | 50% | WIP
7 | 2022-03-09 | RPA GSS | 1. The correction of the invoice generation has been updated and tested and it is updating smoothly | 100% | Completed
|  |  | 2. P&L reports has been generated for the BLR | 100% | Completed
|  |  | 3. Service Order Pending task is work in progress | 50% | WIP
8 | 2022-03-10 | RPA GSS | 1. Service Order Pending task is work in progress | 70% | WIP
|  | RPA RLOGIC | 1. P&L reports has been generated for all three centers (waiting for data verification from the Rahman san) | 100% | Completed
9 | 2022-03-11 | RPA GSS | 1. Service Order Pending task is work in progress , whereas, downloading and uploading testing is going | 80% | WIP
|  | RPA RLOGIC | 1. General Ledger reports has been triggered today for all three centers. | 100% | Completed
10 | 2022-03-14 | RPA GSS | 1. Service Order Pending Task has been completed ( from download to upload) and there was a issue during upload at aging input box in QVMAR, now, it has been fixed, whereas the testing is progress in all SSCs | 85% | WIP
2. Moving uploaded and downloaded files to backup and applying logs are work in progress.
11 | 2022-03-15 | RPA GSS | 1. The Service Order Pending task has been completed, tested in all SSCs and it is running smoothly from download, converting xls to csv file, and uploading the multiple files sequentially and the source code has been shared to Mohan san now. | 100% | Completed
12 | 2022-03-16 | RPA GSS | 1. Impelementation of public holidays has been completed at ACTVITY_DAILY task, tested in all SSCs and it is running smoothly100% | 100% | Completed
13 | 2022-03-17 | RPA GSS | 1. Correction Received for the Service Order Pending Task to implement the reason with aging status in the filename during file moving to backup folder and also to write all uploaded filenames at log file and it has been completed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of the public holidays is work in progress | 20% | WIP
|  | RPA RLOGIC | 1. Correction updated at P&L reports at MLR for the Jan22
14 | 2022-03-18 | RPA GSS | 1. Implementation of public holidays has been completed at WARRANTY_DAILY and GRS_SUMMARY_DETAILS_DAILY tasks, tested in all SSCs and it is running smoothly | 100% | Completed
|  | RPA RLOGIC | 2. Accounting statements has been generated for the GL of the Jan22 for all three centers and shared to Rahman san to validate data | 100% | Completed
15 | 2022-03-21 | RPA GSS | 1. Correction Received for the Warranty Daily task due to no data found issue at SAMSUNG site for the all SSCs, it has been fixed, tested in all SSCs and it is running smoothly | 100% | Completed
|  |  | 2. Public holidays has been implemented at Warranty, Activity and GRS_Details tasks, it has been tested and it is running smoothly. | 100% | Completed
|  |  | 3. In Rlogic, no data failure issue at warranty task due to samsung site, and it has been fixed, tested and it is running smoothly | 100% | Completed
16 | 2022-03-22 | RPA GSS | 1. Implementation of Public holidays at Activity Customer_token system task is work in progress | 50% | WIP
|  |  | 2. Correction Received for the duplicate record at database (as task running twice) is work in progress | 10% | WIP
|  |  | 3. For the RLOGIC, General ledger has been triggered for all three centers of the Feb22 | 100% | Completed
17 | 2022-03-23 | RPA GSS | 1. Correction received from the GRS-Details task due to multiple time database has been updated for single running, Now it has been fixed, tested and it is running smoothly and a few logs are implemented | 100% | Completed
|  |  | 2. Public holidays has been implemented at Customer Visit token task, it has been tested and it is running smoothly, whereas a few captcha correction works is work in progress | 30% | WIP
|  |  | 3. Activity Daily has been received to enhance the task running logic and it is work in progress for multiple centers | 50% | WIP
|  | RPA RLOGIC | 4. Rlogic, email issue exists and yet to be fixed.
18 | 2022-03-24 | RPA GSS | 1. Correction Received for the new updates in database query and update in the source for the GRS-Details, Warranty and Activity daily and it is work in progress | 90% | WIP
|  |  | 2. P&L Reports has been generated for the BLR of the Feb22 and shared to Rahman san and yet to be generated for MLR and HYD | 30% | WIP
19 | 2022-03-25 | RPA GSS | 1. Correction Received for new updates in database, and it has been completed at GRS-Details, Warranty and Activity daily tasks and it is tested in all SSCs and they are running smoothly and the updated source code has been shared to Mohan san. | 100% | Completed
20 | 2022-03-28 | RPA GSS | A). Implementation of the public holidays is not done for the below mentioned tasks and instead of that the log information has been recorded at log file and they are tested and they running smoothly 1. Credit_info 2. Credit_details 3. DRS daily 4. PR Summary daily 5. Service Order cancelled | 100% | Completed
|  | RPA RLOGIC | 1. MLR daily tasks are not executed due to password is matching and after receiving the passwords, we have rerun the daily task of MLR | 100% | Completed
|  |  | 2. In addition to warranty daily task, in saw discount task also table structured changed at GSPN and due to that no data found is occurred and it has been fixed by Kabilan san. | 100% | Completed
21 | 2022-03-29 | RPA GSS | A). Implementation of the public holidays is not the below mentioned tasks and instead of that the log information has been recorded at log file and they are tested and they running smoothly 1. DRS-WEEKLY 2. POC_DAILY 3. INVOICE_UPDATE_OOW_WEEKLY_V1_22Mar29 4. PR_DETAILS_10DAYS_V1_22Mar29 5. PR_SUMMARY_10DAYS_V1_22Mar29 6. SERVICE_PART_RETURN_DAILY_V4_22Mar29 | 100% | Completed