## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-04-29 | RPA Dotnet | [Backend] CRM | 30% | WIP | 1. CRM Table is created for the News Letter type 2. email id are fetched from the database based on condition of either existisng customer or general customer type and displayed to the textarea, 3,some onchange events to be implemented to select customer type and based on that email id will be fetched from the databas and placed in the textarea is in progress
|  |  | Excel macros |  |  | 4. Purely Excel Macro has been developed to create a header.csv file for the japanese language 5. replaceall macro has been developed To remove emspace characters in japanese text
|  |  | Excel macros |  |  | 1. Userform designed and development etc
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-05-06 | MujiStore | Subnet Integration for Troubleshooting | 10% | WIP
Status
WIP
Pending
Completed
Hold

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-06-05 | Hayaai | Integration with MVC | 40% | WIP
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-02-05 | Hayaai | Instant fix(IF) home screen UI and displaying Product types | 100% | Completed
2 | 2020-03-05 | Hayaai | 1. IF - Selection of Brands, models, series, warranty type,issue, service center screen UI. 2. IF - Displaying and selecting of Brands, Series, Model | 100% | Completed
3 | 2020-04-05 | Hayaai | 1. IF- Display and selection of Issues and service centers. 2. IF- UI of Price selection screen. 3. Navigation to Dashboard and Locate service center screens from instant fix screen. | 100% | Completed
4 | 2020-05-05 | Hayaai | 1. IF- Functionality of Price selection screen, 2. IF- UI and functionality of checkout screen, 3. IF- Tracking screen implementation | 90% | Completed
5 | 2020-06-05 | Hayaai | 1. IF - Tracking screen implementation issue resolved. Instant fix full flow implemented. | 100% | Completed
Status
WIP
Pending
Completed
Hold