## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-04-29 | RPA Dotnet | [Backend] CRM | 30% | WIP | Tables are created at RPA Sale database, whereas relationship is penidng, after discussing with Mr Bharathi san, it will be over, if any changes or modification can be done.
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | MujiStore | MujiStore - Authorization for Stores video | 30% | WIP
2 | 2020-04-30 | MujiStore | MujiStore - Authorization for Stores video | 50% | WIP
Status
WIP
Pending
Completed
Hold

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
2 | 2020-05-04 | Hayaai | Website design- Business page | 100% | Completed
2 | 2020-05-05 | Hayaai | Website design- Contact page & Business page popup | 60% | WIP
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-30 | DOTNET APP | Video | 70% | WIP
2 | 2020-05-04 | DOTNET APP | Video | 30% | Completed
2 | 2020-05-04 | DOTNET APP | Presentation | 40% | WIP
3 | 2020-05-05 | DOTNET APP | Presentation | 45% | WIP
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
1 | 29/04/2020 | Rever B2C | IF full flow with technician tracking integration | 100% | Completed | APK sent.
Status
WIP
Pending
Completed
Hold