## JAN-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-01-03 | RPA RLOGIC | 1. Working on beautification tasks for the P&L summary and GL summary and it is work in progress | 60% | WIP
|  |  | 2. For P&L, Downloaded DRS and Warranty file and merged the DRS,Warranty, InvoiceUpdate and Saw file to create a Call Wise Data for the MLR done | 100% | Completed
2 | 2022-01-04 | RPA RLOGIC | 1. Creating Borders and applying styles to the Summary of the General Ledger and it has been completed, implemented and tested | 100% | Completed
|  |  | 2. Creating Borders and applying styles to the Summary of the Profit and Loss report and it has been completed, implemented and tested | 100% | Completed
3 | 2022-01-05 | RPA RLOGIC | 1. Integration of merging tasks of DRS, Invoice update and Saw files with Warranty are work in progress and it has to be done before creating the callwise data for the P&L(already done) | 90% | WIP
4 | 2022-01-06 | RPA RLOGIC | 1. Created a sample P&L report with new logic for the MLR and BLR without expenses | 100% | Completed
|  |  | 2. P&L report of the HYD is work in progress | 50% | WIP
5 | 2022-01-07 | RPA RLOGIC | 1. P&L reports has been generated for all three centers | 100% | Completed
6 | 2022-01-10 | RPA RLOGIC | 1. Expenses data has been added to the P&L report as separate sheet like callwise data sheet | 100% | Completed
|  |  | 2. Deleted the backup files of the Rlogic daily reports from Sep2021 to Dec2021 | 100% | Completed
|  |  | 3. Deleted the log files from Sep2021 to Dec2021 | 100% | Completed
7 | 2022-01-11 | RPA RLOGIC | 1. Generated the Accounting Statements for the three centers and shared to Rahaman san to verify | 100% | Completed
|  | RPA GSS | 2. Uploading the pdf files task is work in progress for ESA | 10% | WIP
8 | 2022-01-12 | RPA RLOGIC | 1. Correction received for the Accounting Statements for the three centers and completed the correction and shared to Rahaman san to verify | 100% | Completed
|  | RPA GSS | 2. Uploading the pdf files task is work in progress for ESA and it is around 50% has been completed | 50% | WIP
9 | 2022-01-13 | RPA GSS | 1. Uploading PDF files task has been completed, tested and it is uploading smoothly | 100% | Completed
10 | 2022-01-17 | RPA RLOGIC | 1. Removing rows where minus sign at Other Column in the warranty monthly files has been done during append to the previous month file | 100% | Completed
|  |  | 2. ESA task has been tested success at Mohan san's system and confirmed for the ESA today | 100% | Completed
11 | 2022-01-19 | RPA RLOGIC | 1. Generated the Accounting Statements for the three centers and the same had been triggered success | 100% | Completed
|  |  | 2. Generated the P&L reports of the Dec21 for the three centers and shared to Rahman san for the verification | 100% | Completed
12 | 2022-01-21 | RPA RLOGIC | 1. Enhancing the knowledge of Openpyxl and Pandas frameworks towards the RPA automation to handle excel manipulation and involved in the calculation activities | 100% | Completed
|  |  | 2. Also, we are working date filtering with new logic to obtain previous month data if vendor ledger is having three months data and it is work in progress for the GL | 30% | WIP
13 | 2022-01-24 | RPA RLOGIC | 1. P&L has been triggered for the all 3 centers and it is done today | 100% | Completed
|  |  | 2. RPA Management template has been triggered for the all 3 centers and it is done today | 100% | Completed
|  |  | 3. Getting Last month closing balance and taking as current month opening balance, this steps has been implemented at GL and etc | 100% | Completed
|  |  | 4. Some more filtering to be done at Vendor Ledger file for GL to implement is work in progress | 20% | WIP
14 | 2022-01-25 | RPA RLOGIC | 1. A few fine tuning works are work in progress for P&L and GL | 30% | WIP
15 | 2022-01-25 | RPA GSS | 2. New Change request has been received from Mohan san to do customization at GSPN tasks and it is work in progress | 5% | WIP
16 | 2022-01-27 | RPA GSS | We have received the change request for the customization parts at GSPN tasks as follows on 25.01.2022 from Mohan san:
1. We have to fetch the data and upload from the day was working till previous day if the previous day is holiday.
2. if holidays are more than 3 days or more, then we have to split days and download and upload with date splitting
3. if record counts is more than 5000, then again the divide the date or split the date and do the download and upload
|  |  | Note: point 1. has been completed, whereas the testing has been done with Warranty daily task, and other tasks are pending. | 20% | WIP
17 | 2022-01-28 | RPA GSS | 1. Implementation of Public holidays has been done at Warranty task and it is tested and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of Public holidays has been done at ACTIVITY_DAILY task(Token system) and the testing is work in progress | 70% | WIP
18 | 2022-01-31 | RPA GSS | 1. Implementation of Public holidays at GSPN task is work in progress | 20% | WIP

## FEB-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-02-01 | RPA GSS | 1. Correction received from the DRS-Monthly tasks due to 5000 records issue, and it has been fixed, tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
|  |  | 2. Implementation of public holidays is work in progress | 30% | WIP
2 | 2022-02-02 | RPA GSS | 1. Implementation of public holidays is work in progress for the Warranty daily tasks and now the task aimed (based on Mohan san's suggestion) to run on every invidual days on the working day from the last running date and the testing is going on for the warranty daily task | 40% | WIP
3 | 2022-02-03 | RPA RLOGIC | 2. Authentication issue is exist at RLOGIC MLR after recieving the new userid and pwd, we have tested and found that a few menus are missing and it has been noticed to the rlogic today and waiting for the response.
3. Downloading the GL and P&L documenents are started already for the BLR and HYD of the Jan2022.
4 | 2022-02-03 | RPA GSS | 1. 5000 thousands records issue was fixed at DRS Monthly task when record count is equal to 5000 and the testing is going intermittently as the new bot is occupied by Vijay san and Nirmal san, | 90% | WIP
|  |  | 2. Implementation of Public holidays are work in progress | 40% | WIP
5 | 2022-02-04 | RPA GSS | 1. DRS Monthly task has been tested for the 5000 records and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of public holidays has been done Warranty Daily task, tested and running smoothly | 100% | Completed
|  |  | 3. Implementation of public holidays has been done Activity Daily task, tested and running smoothly | 100% | Completed
|  |  | 4. Implementation of public holidays at GRD task(GRSummary with Details task) is work in progress | 10% | WIP
6 | 2022-02-04 | RPA RLOGIC | 5. Cutomization at P&L is work in progress | 30% | WIP
7 | 2022-02-07 | RPA GSS | 1. Implementation of public holidays in GRS_Details is work in progress (50%) (Generating advance date done based on the last run date, and splitting the range of date into groups for the each three days with fdate and tdate as input from the last run) | 50% | WIP
8 | 2022-02-08 | RPA GSS | 1. Implementation of public holidays has been completed at GRS-Details daily task and it is tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
9 | 2022-02-09 | RPA GSS | 1. Customization due to Multi-Factor Authentication has been implemented at GRS-Details, tested and it is running smoothly | 100% | Completed
10 | 2022-02-10 | RPA GSS | 1. A 12 daily tasks has been customised due to MFA issue, completed, tested and they are running smoothly | 100% | Completed
11 | 2022-02-11 | RPA GSS | 1. A six weekly tasks has been customised due to MFA issue, completed, tested and they are running smoothly 2. Also modified the reading OTP based on the SSCCODE and email to address, and it is tested and it is running smoothly | 100% | Completed
12 | 2022-02-14 | RPA RLOGIC | 1. We have generated the Accounting statements for all three centers (MLR, BLR and HYD) of the January 2022 and the same had been shared to Rahman san for verification | 100% | Completed
13 | 2022-02-15 | RPA RLOGIC | 1. Reading OTP from the GMAIL is work in progress. | 30% | WIP
14 | 2022-02-16 | RPA RLOGIC | 1. Customization due to Multi-Factor Authentication has been implemented at DAILY-tasks (DRS, WARRANTY, SAW_DISCOUNT, SERVICE_ORDER_MANAGEMENT BULK, COMMUNICATION BOARD CLEAR TASK), and waiting for the OTP process | 80% | WIP
15 | 2022-02-17 | RPA RLOGIC | 1. Research and Development is going on general Captcha issue | 10% | WIP
16 | 2022-02-18 | RPA GSS | The task of Invoice Generation is work in progress | 10% | WIP
17 | 2022-02-21 | RPA GSS | 1. Getting data from the multiple excel files has been done based on the data requirements and whereas updating master file is work in progress for the invoice generation task. | 60% | WIP
18 | 2022-02-22 | RPA GSS | 1. The updating master data file has been completed 50% and other process is work in progress | 70% | WIP
|  |  | 2. Getting cell value along with column number is work in progress | 70% | WIP
19 | 2022-02-23 | RPA GSS | 1. Updating master data file is work in progress as new suggestion has been received from Mohan san, ( we have to extract data pagewise and update to be done based on the configuration file) | 75% | WIP
|  |  | 2. Supported to Captcha issue at token system (RPA GSS)( Now the login is getting success from the six to ten captcha images) and still the task to be tested. | 60% | WIP
20 | 2022-02-24 | RPA GSS | 1. All 11 tasks of monthly has been implemented with MFA with OTP reading, and upload status, tested and it is running smoothly | 100% | Completed
|  |  | 2. Whereas , the task of invoice generation is work in progress | 60% | WIP
21 | 2022-02-25 | RPA GSS | 1. Mr Kabilan san has completed the captcha issue at token system based on the sony captcha code( whereas I have supported to that logical approach and testing), it is tested and running smoothly | 100% | Completed
|  |  | 2. Task of invoice generation has been completed, tested and it is updating at master file success, whereas the integration and formatting the data is work in progress | 80% | WIP
22 | 2022-02-28 | RPA GSS | 1. The task of invoice generation has been completed, tested and it is running smoothly, whereas during testing, mohan san suggesting that after creating csv file, we need to update the master file to avoid memory craking (now it is done dynamically getting data and updating master file dynamically) and it is work in progress | 80% | WIP
2. Athough the captching is working fine, still Mohan has suggested to check 30 or 50 times of the captcha intead of continues checking and we need to enhance the captcha
23 | 2022-03-01 | RPA GSS | 1. In invoice generation task, while updating the master file from the csv file is throwing error : | 85% | WIP
whereas no merging is taking place during update, but, still error is throwing
2. After using lower version of openpyxl, the master file is getting updated success, but somewhere a few formulas are getting error or issue.
Hence, i have uninstalled lower version of openpyxl and it is work in progress.

## MAR-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-03-01 | RPA GSS | 1. In invoice generation task, while updating the master file from the csv file is throwing error : | 85% | WIP
whereas no merging is taking place during update, but, still error is throwing
2. After using lower version of openpyxl, the master file is getting updated success, but somewhere a few formulas are getting error or issue.
Hence, i have uninstalled lower version of openpyxl and it is work in progress.
2 | 2022-03-02 | RPA GSS | 1. In invoice generation task, updating the master file from the csv file has been completed, 2. once updates are over, input files will be moved to backup folder also done, 3. before updating the master file, copy of the master file will be moved to backup folder also done 4. whereas, applying logg is work in progress | 90% | WIP
|  |  | 5. Correction Received for Invoice Update PDF has been fixed, tested and it is running smoothly from download to upload | 100% | Completed
3 | 2022-03-03 | RPA GSS | 1. Invoice_generation has been completed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Task of Service Order Pending is work in progress | 10% | WIP
4 | 2022-03-04 | RPA GSS | 1. Analysing has been done for the task of Service Order Pending from SSC1 to SSC11 at GSPN site
2. No Data Found issue due to no record found
3. No Data Found due to Assigned Engineer row is not presented
4. Fetching row number from the specific location is work in progress
5 | 2022-03-07 | RPA GSS | 1. The task of Service Order Pending is work in progress, and clicking at each cell is success whereas click at each row is having stale error issue. It is a challenging for us to download. |  | WIP
|  | RPA RLOGIC | 1. MFA issue has been fixed at BLR center only, and Following that the daily tasks are success, and we have downloaded the Feb22 files for the GL and PL files are going on for the BLR. | 90% | WIP
6 | 2022-03-08 | RPA GSS | 1. Till downloading the excel files has been completed for the Service Order Pending task after clicking at each row and each cell, 2. Conversion of xls to csv file is work in progress. | 50% | WIP
7 | 2022-03-09 | RPA GSS | 1. The correction of the invoice generation has been updated and tested and it is updating smoothly | 100% | Completed
|  |  | 2. P&L reports has been generated for the BLR | 100% | Completed
|  |  | 3. Service Order Pending task is work in progress | 50% | WIP
8 | 2022-03-10 | RPA GSS | 1. Service Order Pending task is work in progress | 70% | WIP
|  | RPA RLOGIC | 1. P&L reports has been generated for all three centers (waiting for data verification from the Rahman san) | 100% | Completed
9 | 2022-03-11 | RPA GSS | 1. Service Order Pending task is work in progress , whereas, downloading and uploading testing is going | 80% | WIP
|  | RPA RLOGIC | 1. General Ledger reports has been triggered today for all three centers. | 100% | Completed
10 | 2022-03-14 | RPA GSS | 1. Service Order Pending Task has been completed ( from download to upload) and there was a issue during upload at aging input box in QVMAR, now, it has been fixed, whereas the testing is progress in all SSCs | 85% | WIP
2. Moving uploaded and downloaded files to backup and applying logs are work in progress.
11 | 2022-03-15 | RPA GSS | 1. The Service Order Pending task has been completed, tested in all SSCs and it is running smoothly from download, converting xls to csv file, and uploading the multiple files sequentially and the source code has been shared to Mohan san now. | 100% | Completed
12 | 2022-03-16 | RPA GSS | 1. Impelementation of public holidays has been completed at ACTVITY_DAILY task, tested in all SSCs and it is running smoothly100% | 100% | Completed
13 | 2022-03-17 | RPA GSS | 1. Correction Received for the Service Order Pending Task to implement the reason with aging status in the filename during file moving to backup folder and also to write all uploaded filenames at log file and it has been completed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of the public holidays is work in progress | 20% | WIP
|  | RPA RLOGIC | 1. Correction updated at P&L reports at MLR for the Jan22
14 | 2022-03-18 | RPA GSS | 1. Implementation of public holidays has been completed at WARRANTY_DAILY and GRS_SUMMARY_DETAILS_DAILY tasks, tested in all SSCs and it is running smoothly | 100% | Completed
|  | RPA RLOGIC | 2. Accounting statements has been generated for the GL of the Jan22 for all three centers and shared to Rahman san to validate data | 100% | Completed
15 | 2022-03-21 | RPA GSS | 1. Correction Received for the Warranty Daily task due to no data found issue at SAMSUNG site for the all SSCs, it has been fixed, tested in all SSCs and it is running smoothly | 100% | Completed
|  |  | 2. Public holidays has been implemented at Warranty, Activity and GRS_Details tasks, it has been tested and it is running smoothly. | 100% | Completed
|  |  | 3. In Rlogic, no data failure issue at warranty task due to samsung site, and it has been fixed, tested and it is running smoothly | 100% | Completed
16 | 2022-03-22 | RPA GSS | 1. Implementation of Public holidays at Activity Customer_token system task is work in progress | 50% | WIP
|  |  | 2. Correction Received for the duplicate record at database (as task running twice) is work in progress | 10% | WIP
|  |  | 3. For the RLOGIC, General ledger has been triggered for all three centers of the Feb22 | 100% | Completed
17 | 2022-03-23 | RPA GSS | 1. Correction received from the GRS-Details task due to multiple time database has been updated for single running, Now it has been fixed, tested and it is running smoothly and a few logs are implemented | 100% | Completed
|  |  | 2. Public holidays has been implemented at Customer Visit token task, it has been tested and it is running smoothly, whereas a few captcha correction works is work in progress | 30% | WIP
|  |  | 3. Activity Daily has been received to enhance the task running logic and it is work in progress for multiple centers | 50% | WIP
|  | RPA RLOGIC | 4. Rlogic, email issue exists and yet to be fixed.
18 | 2022-03-24 | RPA GSS | 1. Correction Received for the new updates in database query and update in the source for the GRS-Details, Warranty and Activity daily and it is work in progress | 90% | WIP
|  |  | 2. P&L Reports has been generated for the BLR of the Feb22 and shared to Rahman san and yet to be generated for MLR and HYD | 30% | WIP
19 | 2022-03-25 | RPA GSS | 1. Correction Received for new updates in database, and it has been completed at GRS-Details, Warranty and Activity daily tasks and it is tested in all SSCs and they are running smoothly and the updated source code has been shared to Mohan san. | 100% | Completed
20 | 2022-03-28 | RPA GSS | A). Implementation of the public holidays is not done for the below mentioned tasks and instead of that the log information has been recorded at log file and they are tested and they running smoothly 1. Credit_info 2. Credit_details 3. DRS daily 4. PR Summary daily 5. Service Order cancelled | 100% | Completed
|  | RPA RLOGIC | 1. MLR daily tasks are not executed due to password is matching and after receiving the passwords, we have rerun the daily task of MLR | 100% | Completed
|  |  | 2. In addition to warranty daily task, in saw discount task also table structured changed at GSPN and due to that no data found is occurred and it has been fixed by Kabilan san. | 100% | Completed
21 | 2022-03-29 | RPA GSS | A). Implementation of the public holidays is not the below mentioned tasks and instead of that the log information has been recorded at log file and they are tested and they running smoothly 1. DRS-WEEKLY 2. POC_DAILY 3. INVOICE_UPDATE_OOW_WEEKLY_V1_22Mar29 4. PR_DETAILS_10DAYS_V1_22Mar29 5. PR_SUMMARY_10DAYS_V1_22Mar29 6. SERVICE_PART_RETURN_DAILY_V4_22Mar29 | 100% | Completed
22 | 2022-03-30 | RPA GSS | A). Implementation of the public holidays is not done at the below mentioned tasks and instead of that the log information has been recorded at log file and also changes made to run on holidays and they are tested and they running smoothly 1. DEBIT_NOTE_REGISTER_MONTHLY_V1_22Mar30 2. DRS_MONTHLY_V2_22Mar30 3. INVOICE_UPDATE_EXC_IW_MONTHLY_V2_22Mar30 4. INVOICE_UPDATE_IW_MONTHLY_V2_22Mar30 5. INVOICE_UPDATE_OOW_MONTHLY_V2_22Mar30 6. INVOICE_UPDATE_PDF_MONTHLY_V1_22Mar30 7. OTHER_SALES_MONTHLY_V4_22Mar30 8. PARTS_IO_MONTHLY_V1_22Mar30 9. RETURN_CREDIT_MONTHLY_V1_22Mar30 10. SAW_DISCOUNT_MONTHLY_V1_22Mar30 11. SERVICE_ORDER_PENDING_MONTHLY_V1_22Mar30 12. STOCK_OVERVIEW_MONTHLY_V1_22Mar30 | 100% | Completed
23 | 2022-03-31 | RPA GSS | A). Implementation of the public holidays is not done at the below mentioned tasks and instead of that the log information has been recorded at log file and they are tested and they running smoothly 1. DEBIT_NOTE_REGISTER_MONTHLY_V1_22Mar30 2. DRS_MONTHLY_V2_22Mar30 3. INVOICE_UPDATE_EXC_IW_MONTHLY_V2_22Mar30 4. INVOICE_UPDATE_IW_MONTHLY_V2_22Mar30 5. INVOICE_UPDATE_OOW_MONTHLY_V2_22Mar30 6. INVOICE_UPDATE_PDF_MONTHLY_V1_22Mar30 7. OTHER_SALES_MONTHLY_V4_22Mar30 8. PARTS_IO_MONTHLY_V1_22Mar30 9. RETURN_CREDIT_MONTHLY_V1_22Mar30 10. SAW_DISCOUNT_MONTHLY_V1_22Mar30 11. SERVICE_ORDER_PENDING_MONTHLY_V1_22Mar30 12. STOCK_OVERVIEW_MONTHLY_V1_22Mar30
|  |  | 13. MFA work is work in progress | 10% | WIP

## APR-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-04-01 | RPA GSS | 1. Research and Development is going on for the MFA and it is work in progress, 2. ARCHON Emulator has been installed, whereas still app initialization issue exist. (install-archon-run-android-apps-pc-using-chrome-browser) | 85% | WIP
|  | RPA RLOGIC | 3. GL Files are downloaded except InvoicePDF as it is having issue | 80% | WIP
|  |  | 4. Downloading P&L is going on. | 70% | WIP
2 | 2022-04-04 | RPA GSS | 1. Archon runtime has been installed, tested and it is running only in lower version of chrome browser towards GSPN MFA issue | 100% | Completed
|  |  | 2. Correction Received from Activity daily task due to date input and it has been fixed, tested and it is running smoothly | 100% | Completed
|  |  | 3. A few changes has been requested by Mohan san for the Service Order Pending task and it is work in progress. | 50% | WIP
3 | 2022-04-05 | RPA GSS | 1. Modification at Service Order Pending task is work in progress | 50% | WIP
|  |  | 2. Removing the date hard coded for the GSPN monthly task has been done by Kabilan san | 100% | Completed
4 | 2022-04-06 | RPA GSS | 1. Modification at Service Order Pending task is work in progress | 50% | WIP
|  |  | 2. A new changes received from Mohan san as warranty excel has 130 column instead 138 and due to that upload error is arise and hence we have modified to at code level to convert xls to csv file and now testing is going on | 90% | WIP
|  | RPA RLOGIC | 3. P&L Reports has been generated and shared to Rahman san for all three centers to verify. | 100% | Completed
5 | 2022-04-07 | RPA GSS | 1. Modification at Service Order Pending task is work in progress and it is completed with 70% | 70% | Completed
|  |  | 2. Correction received from the warranty task due to no data found issue, fixed, testd and it is running smoothly | 100% | Completed
6 | 2022-04-08 | RPA GSS | 1. Modification at Service Order Pending task has been completed, tested and it is running smoothly and the updated source code has been shared to Mohan san | 100% | Completed
7 | 2022-04-11 | RPA GSS | Task of Service Order Parts Number is work in progress (around 20% of the workflow has been completed towards searching parts number based on the ASC_REF number the source file) | 20% | WIP
8 | 2022-04-12 | RPA GSS | 1. Task of Service Order Parts Number is work in progress, and while fetching data from this site, differently appearing the closing page before next iteration for the each SSCs with no data found or data found and trying to fix it | 30% | WIP
9 | 2022-04-13 | RPA GSS | 1. Task of Service Order Parts Number is work in progress, and parts has been extracted and stored in csv file and around 40% works has been completed. | 40% | WIP
10 | 2022-04-13 | RPA RLOGIC | 1. P&L and Management Reports has been triggered successfully. | 100% | Completed
11 | 2022-04-18 | RPA GSS | 1. Task of Service Order Parts Number is work in progress, and parts has been extracted and stored in csv file and around 50% works has been completed. | 50% | WIP
|  | RPA RLOGIC | 1. Supported to Generate the Accounting Statement reports for the BLR, HYD and MLR centers and shared to Rahman san to verify the data
2. Based on Rahman san request, we are triggering the warranty excel files from 21-03-2022 to 06-04-2022 to the Rlogic as no data was found for the foresaid date.
12 | 2022-04-19 | RPA GSS | 1. Task of Service Order Parts Number has been extracted and downloading the ASC_REF numbers from QMVAR is work in progress | 60% | WIP
|  | RPA RLOGIC | 1. Accounting statements reports has been triggered for all 3 centers for the Mar22 (GL) | 100% | Completed
|  |  | 2. P&L reports are generated without expenses details and shared to Rahman san | 60% | WIP
13 | 2022-04-20 | RPA GSS | Downloading the ASC_REF numbers from QMVAR and Uploading the Parts number at QMVAR are work in progress | 70% | WIP
14 | 2022-04-21 | RPA GSS | Downloading the ASC_REF numbers from QMVAR and Uploading the Parts number at QMVAR are work in progress | 80% | WIP
15 | 2022-04-25 | RPA GSS | Development of Service Order Parts number task has been completed and the testing is work in progress | 90% | WIP
16 | 2022-04-26 | RPA GSS | The Service Order Parts numbers task has been completed, whereas due to few failures during testing, we are splitting the downloading/extracting the parts numbers, and few changes are doing and work in progress. | 95% | WIP
17 | 2022-04-27 | RPA GSS | The Service Order Parts numbers task has been completed, whereas the testing is work in progress | 100% | WIP
18 | 2022-04-28 | RPA GSS | The Service Order Parts Numbers task has been completed, tested and it is running smoothly and the source code has been shared to Mohan san | 100% | Completed
19 | 2022-04-29 | RPA GSS | Working on Exe conversion for the GL, P&L, and Management Template works etc and it is work in progress | 50% | WIP
|  | RPA RLOGIC | Registered and Three instances are created to run daily tasks manually for the rlogic tasks | 100% | Completed

## MAY-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-05-02 | RPA GSS | 1. Service Order Parts Number task has been executed to extract the Parts number and uploading the csv files for SSC1 and SSC3, whereas the other SSCs are work in progress | 100% | Completed
|  |  | 2. Working on Exe conversion for the GL, P&L, and Management Template works etc and it is work in progress | 60% | WIP
2 | 2022-05-04 | RPA GSS | 1. Service Order Parts Number task has been executed to extract the Parts number and uploading the csv files for SSC6,SSC8 and SSC9, whereas the other SSCs are work in progress(SSC10 is running now) | 100% | Completed
3 | 2022-05-05 | RPA GSS | 1. Service Order Parts Number task has been executed to extract the Parts number and uploading the csv files for SSC10 and it is work in progress (SSC10 is running now) | 80% | WIP
4 | 2022-05-05 | RPA DEMO SG | 1. Prepared for the RLOGIC demo to SG | 100% | Completed
5 | 2022-05-06 | RPA GSS | 1. Downloading and Uploading of the GRS-Details daily task has been completed for SSC10,SSC11,SSC8,SSC9 from 24-04-2022 to 05-05-2022 as requested Mohan san, whereas the other service centers are work in progress | 70% | WIP
|  |  | 2. Supported and Attended A RPA demo with Ramesh san and Rahman san and Kabilan san | 100% | Completed
6 | 2022-05-09 | RPA GSS | 1. InvoiceUpdate PDF downloading task to download and upload with MFA authentication testing has been done and tested in all SSCs, it was throwing new error as no data exist and it will be fixed after completion of monthly task based on mohan san suggestion | 50% | WIP
|  |  | 2. The Debit Note Register monthly task has been fixed with MFA authentication, tested in all SSCs and they are running smoothly and shared the updated code to mohan san. | 100% | Completed
7 | 2022-05-10 | RPA GSS | 1. Downloading and Uploading of the OtherSales monthly task has been completed for SC1,SSC3,SSC6,SSC8,SSC9 are completed from 01-04-2022 to 30-04-2022 as requested Mohan san, whereas the other service centers are work in progress | 80% | WIP
8 | 2022-05-11 | RPA GSS | 1. Supported to Clear the communication board tasks for SSC1, SSC2,SSC3,SSC6,SSC8,SSC9,SSC10 and SSC11 and also implemented the MFA authentication, tested and it is running smoothly. | 100% | Completed
|  |  | 2. Supported to OtherSales task to extract the Extended warranty data and uploaded for SSC10 and SS11 and it is success manually | 100% | Completed
9 | 2022-05-12 | RPA GSS | 1. The MFA authentication has been implemented at InvoiceUpdate PDF task, also fixed the No data exist, tested and it is running smoothly, whereas we need to run this one more before this month end to download the PDF and upload as it has not been approved by the management at respective SSCs. | 100% | Completed
2. The MFA authentication has been implemented at OtherSales task, whereas during test, it is doing same operation (extraction) instead of unit price searching and hence it is work in progress
10 | 2022-05-13 | RPA GSS | 1.The MFA authentication has been implemented at OtherSales task, also fixed the issue of three logins to single login to extract EW data and Unit Price data and tested in SSCs and it is running smoothly and also time delay has been reduced to 130 to 30 seconds for the each unit price | 100% | Completed
11 | 2022-05-16 | RPA GSS | 1. The MFA authentication has been implemented at INVOICEUPDATEPDF and ServiceOrderPartsNumbers tasks, tested in different SSCs and they are functioning smoothly and the updated source code has been shared | 100% | Completed
12 | 2022-05-17 | RPA GSS | 1. The MFA authentication has been implemented at PR summary and Details tasks, tested in few SSCs and they are running smoothly. | 100% | Completed
|  |  | 2. The issue at InvoiceUpdatePDF Monthly task, partsnumber textbox is having empty and not accessible due to javascript code only some time at this place. it is a new error and it has been fixed, tested and it is running smoothly. | 100% | Completed
|  |  | 3. This issue has been fixed at Service Order Parts Number capturing task by renaming filename after downloading, this is due to at QMVAR side the downloaded filename has changed from # C:\Users\Administrator\Downloads\SSC10_ASC_NO202204.csv to # C:\Users\Administrator\Downloads\SSC10_ASC_NO_202204.csv (this was the issue), now it is fixed, tested and it is running. | 100% | Completed
13 | 2022-05-18 | RPA GSS | 1. In the Service Order Parts number task, The no data found issue is occurring due to no parts numbers are presented and it has been fixed, tested and it is running smoothly. | 100% | Completed
|  |  | 2. Supported to implement MFA at password management task and it is work in progress. | 20% | WIP
14 | 2022-05-19 | RPA GSS | 1. The MFA authentication has been implemented at Password changes and password check tasks, tested and it is functioning smoothly | 100% | Completed
|  |  | 2. Service Order Parts Number task testing is going on and it will be completed by 18:30 | 100% | Completed
15 | 2022-05-20 | RPA GSS | 1. The MFA authentication has been implemented at DRS-Monthly and DebitNoteRegister tasks, tested in all SSCs and they are functioning smoothly. | 100% | Completed
|  |  | 2. The Service Order Parts Number task has been tested and it is running smoothly. | 100% | Completed
16 | 2022-05-23 | RPA GSS | 1. The MFA authentication has been implemented at INVOICE_UPDATE_EXC_IW_MONTHLY_V2_22May23, INVOICE_UPDATE_IW_MONTHLY_V2_22May23, INVOICE_UPDATE_OOW_MONTHLY_V2_22May23 tasks and tested in all SSCs and it is running smoothly | 100% | Completed
17 | 2022-05-24 | RPA GSS | 1. Correction Received from the Password management task due to loginstatus was false and hence task was repeating indefinitely and it has been fixed, tested and it is running smoothly | 100% | Completed
|  |  | 2. The MFA authentication has been implemented at Stock Over View, tested in all SSCs and it is running smoothly. | 100% | Completed
18 | 2022-05-25 | RPA GSS | 1. New Requirements(RAO) to the stock over view task has been received and the task is started to get data from QMVAR and other process are work in progress | 10% | WIP
19 | 2022-05-26 | RPA GSS | 1. For RAO StockOverView task, getting information from QMVAR has been completed, tested with single and multiple centers based on the 'NOT RUN' status and it is running smoothly, whereas with no record found to be tested and it is work in progress | 70% | WIP
2. Sending email is yet to starts
20 | 2022-05-27 | RPA GSS | 1. For RAO StockOverView task, it has been completed, (getting information from QMVAR and running the task based on schedules, downloading and uploading and email sendings are tested and it is running smoothly. The updated source code has been shared to Mohan san | 100% | Completed
21 | 2022-05-30 | RPA GSS | 1. The MFA authentication has been implemented at Service Order Pending and InvoiceUpdate PDF tasks, tested in all SSCs and it is running smoothly. | 100% | Completed
|  |  | 2. A modification received for the RAO StockOverView task to send an attachment in email once CSV upload is done if email id exist and it is work in progress | 10% | WIP
22 | 2022-05-31 | RPA GSS | The MFA authentication has been implemented at the below mentioned tasks, tested and it is running smoothly. 1. SAW_DISCOUNT_MONTHLY_V1_22May31 2. PARTS_IO_MONTHLY_V1_22May31 3. RETURN_CREDIT_MONTHLY_V1_22May31 | 100% | Completed
|  |  | 4. The sending email with attachment has been implemented at RAO stockoverview task, tested and it is running smoothly. Please find the updated source code for the same. | 100% | Completed

## JUNE-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-06-01 | RPA GSS | 1. Correction Received for the status update issue when no schedule has been planned, it has been fixed now, tested and it is updating at RPALIVELOG table in QMVAR and it is running smoothly for the Task of RAO StockOverView | 100% | Completed
|  |  | 2. Service Order Parts Number task execution is going on to fetch Parts Number. The SSC1 has been completed whereas the other SSCs are work in progress to fetch Parts Number | 20% | WIP
2 | 2022-06-02 | RPA GSS | 1. Service Order Parts Number task execution is going on to fetch Parts Number. The SSC6 is running now and it will be completed by 21:00 tonight | 80% | WIP
3 | 2022-06-03 | RPA GSS | 1. A new modification received for RAO_ Stock Over View task, to update complete status after uploading csv when data exist and no data found scene, now it has been fixed for data found status , whereas no data found issue is work in progress | 90% | WIP
4 | 2022-06-06 | RPA SONY | 1. Doing Research and Development for the sony task as it has to run in Microsoft edge browser. Till now, we can able to access the sony site using edge browser and it is success, whereas clicking at certificate popup alert is work in progress.
|  | RPA Rlogic | 2. We have triggered the GL reports to the RLOGIC for all three centers (MLR,BLR and HYD) | 100% | Completed
5 | 2022-06-07 | RPA GSS | 1. Corrections: The issue at communication board task due to less return (arguments) from the main function when no records found and it has been fixed and it is tested in all SSCs and it is running smoothly. | 100% | Completed
|  | RPA SONY | 2. For the sony task, clicking at certificate popup alert is work in progress. | 30% | WIP
6 | 2022-06-08 | RPA SONY | 1. For the sony task, doing some Research and development for clicking Ok button to select certificate to enter into sony site and it is fixed by Mohan san, whereas the task testing is pending. | 40% | WIP
|  | RPA Rlogic | 2. Supported to Rlogic Extended warranty task as records counts are missmatching, now an additional logs are recorded in the log file and the task is rerunning
7 | 2022-06-09 | RPA GSS | 1. Correction received for the PR-Details task due to task failed during upload, and it has been fixed, tested and it is running smoothly from download to upload. | 100% | Completed
|  | RPA SONY | 2. Migration from IE to Edge browser task has been completed for the SONY_APNEWSIS_DAILY_V2 task, tested and it is running smoothly from download to upload (Inbound daily task, outbound task, and RPSI inquiry task includes) | 100% | Completed
8 | 2022-06-10 | RPA SONY | 1. SONY_PASSWORD_CHANGE_10DAYS_V1_22June10 (test completed and success) 2. SONY_PASSWORD_CHECK_10DAYS_V1_22June10 (test completed and success) task, tested and it is running smoothly | 100% | Completed
|  |  | 3. Migration from IE to Edge browser task has been completed for the SONY_APNEWSISREPORT_DAILY_V2_22June10 (test pending due to issue) | 50% | WIP
9 | 2022-06-13 | RPA GSS | 1. Doing Research and Development for the GSPN tasks to integrate as single task to run many subtasks with one time login and it is work in work in progress | 20% | WIP
10 | 2022-06-14 | RPA GSS | 1. GSPN task execution for the DRS Daily tasks has been completed from download to upload( SSC1, SSC2,SSC3,SSC6,SSC8,SSC9,SSC10 and SSC11) | 100% | Completed
|  |  | 2. GSPN task execution for the ACTIVITY DAILY task from 11-06-2022 to 13-06-2022 till SSC6 has been completed from download to upload, whereas SSC9, SSC10,SSC11 are yet to be done | 70% | WIP
11 | 2022-06-15 | RPA GSS | 1. GSPN task execution for the ACTIVITY DAILY task from 11-06-2022 to 14-06-2022 has been completed from download to upload for the SSC10 and SSC11
2. GSPN task execution for the ACTIVITY DAILY task from 14-06-2022 to 14-06-2022 has been completed from download to upload for the all SSCs
|  |  | 3. Converting multiple tasks into Single task with subtasks with one time login is work in progress | 20% | WIP
12 | 2022-06-16 | RPA GSS | 1. Converting multiple tasks into Single task with subtasks with one time login is work in progress and it is completed around 50% | 50% | WIP
13 | 2022-06-17 | RPA GSS | 1. Converting multiple tasks into Single task with subtasks with one time login is work in progress and it is completed around 60% | 60% | WIP
|  |  | 2. Correction received for Warranty daily task due to csv convertion and it is work in progress | 60% | WIP
14 | 2022-06-22 | RPA GSS | 1. Correction received for the warranty daily task due to extra columns at SSC3 and result of it, getting error during upload. Now, it has been fixed, still some issue is exists during test and upload, and hence, csv file has been shared to Prabhu san to verify and it is work in progress | 80% | WIP
15 | 2022-06-23 | RPA GSS | 1. The issue at Warranty daily task has been fixed and the issue was extra columns at SSC3 xls file and it has been fixed, tested and it is running smoothly. | 100% | Completed
16 | 2022-06-24 | RPA GSS | 1. Converting multiple tasks into Single task with subtasks with one time login is work in progress and it is completed around 70% | 70% | WIP
(Now, DRS and Warranty tasks has been integrated as single task, downloading, uploading and files moving etc are success. Whereas the failed task to be executed separately and it is work in progress)
17 | 2022-06-27 | RPA GSS | 1. The DRS and Warranty tasks has been integrated as single task, downloading, uploading and files moving etc are success. Whereas the failed task to be executed separately and it is work in progress, recording no data found, data found, failed status, uploading status are work in progress | 80% | WIP
18 | 2022-06-28 | RPA GSS | The Integrating tasks of the DRS and Warranty has been completed around 85%. (recordcount, nodata found and data found are completed, running multiple SSCs are completed, whereas the failed and rerun tasks are work in progress | 85% | WIP
19 | 2022-06-29 | RPA GSS | 1. The Integrating tasks of the DRS and Warranty has been completed around 90%, whereas the failed and rerun tasks are work in progress | 90% | WIP
2. A few suggestion has been received from Mohan san today to enhance the development for the tasks integration works, and it is work in progress
3. Though the tasks has been integrated as single file, still we need to keep each functionality as separate file for easy maintainence in future when need and it is work in progress
4. Now the task will run for download, upload, data fount, no data found, results are storing at database are completed and tested in a few SSCs
20 | 2022-06-30 | RPA GSS | The though the converted multi tasks into single task and it is running smoothly except failure case implementation (pending), but it is a single file. In future, if correction is coming, then it will be a problem to find errored line and Hence Mohan san has suggested to disintegrate this file based on functionality and reintegrate as single package with each file and it is work in progress. | 40% | WIP

## JULY-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-07-01 | RPA GSS | The conversion of multi tasks into single task is work in progress and around 70% has been completed | 70% | Completed
2 | 2022-07-04 | RPA GSS | 1. Mohan san asked me to run Service Order Parts Number monthly task, only 100 records are obtained out of 1957 and it is work in progress | 10% | WIP
|  |  | 2. Correction received for the InvoiceUpdate PDF downloading task due to GSPN site has got updated and it is work in progress | 30% | WIP
3 | 2022-07-05 | RPA GSS | 1. Correction received for the InvoiceUpdate PDF downloading task due to GSPN site has got updated and it has been fixed, tested in few SSCs and it is running smoothly from download to upload | 100% | Completed
|  |  | 2. Correction received for the Service Order Pending task due to not uploaded status at log file and etc, and it is working in progress | 60% | WIP
4 | 2022-07-06 | RPA GSS | 1. The Correction has been completed at ServiceOrderPending task to upload separately with bulk files and it is running smoothly. | 100% | Completed
5 | 2022-07-07 | RPA GSS | 1. The uploading the bulk files for the Service Order Pending has been completed (SSC6,SSC8,SSC9,SSC10) today | 100% | Completed
|  |  | 2. As need to find root cause for the issue as per Mohan san request sir and it is work in progress for the Service Order Pending task to fix the uploading issue with content error etc | 60% | WIP
6 | 2022-07-08 | RPA GSS | 1. Corrections received for the Service Order Pending Task due to contents issue during upload and uploading fails issue, now it has been fixed, tested and it is running smoothly. | 100% | Completed
7 | 2022-07-11 | RPA GSS | 1. The enhancement for service order pending xls files to upload separately in case failed instead of downloading and uploading and it has been enhanced and fixed, tested and it is running smoothly, this is a separate script file to upload separately in case failure occurs at the Service Order Pending task. | 100% | Completed
|  |  | 2. Software has been installed at the oldbot like Pycharm, python etc and configuration also done, now the testing is going on to get a system ready and the oldbot is ready to do GSS tasks like a newbold machine, whereas testing the sony task are pending | 70% | WIP
8 | 2022-07-12 | RPA GSS | 1. The conversion of multi tasks into single task is work in progress and (DRS and Warranty tasks are separated like simple one to integrate functionality alone, and whereas the failure status, success status and upload status based on the return status, the logs will be recorded and updated in database also and these stattus are yet to be implemented) | 30% | WIP
9 | 2022-07-13 | RPA GSS | 1. The Converion of multitasks itno single task has been supported till lunch. |  | WIP
|  |  | 2. The new requeirments has been received for the SRN with stock overview tasks from Mohan san and it is work in progress | 10% | WIP
10 | 2022-07-14 | RPA GSS | 1. Till downloading at SRN task has been reached, and other process are work in progress. (First we have to download the stockoverview file and we have to click each link and dowload, rename file , convert into csv and merge as single file and find a difference between stockoverview file with Parts number and save the record from SRN file if it is matching at stockoverview and sending the report in email etc) | 30% | WIP
|  |  | 2. Correction received for the Service Order Parts Number fetching tasks due to date issue and it has been fixed, tested and it is running smoothly. | 100% | WIP
11 | 2022-07-15 | RPA GSS | 1. The SRN task is work in progress and around 40% has been completed | 40% | WIP
12 | 2022-07-18 | RPA GSS | 1. The SRN task has been completed till merging the csv files and other process is work in progress. | 50% | WIP
13 | 2022-07-19 | RPA GSS | 1. The SRN task has been completed till merging, whereas in the merging few fine tuning is going on to find difference between the stockoverview and SRN output file. | 55% | WIP
14 | 2022-07-20 | RPA GSS | 1. The SRN task has been completed till finding difference between two files and fetching the matching one and stored in result file and sending the attachment, whereas the other process is work in progress. | 70% | WIP
15 | 2022-07-21 | RPA GSS | 1. The SRN task has been completed till sending email and it is success, whereas the testing is going on for each SSC to avoid data type issue during conversion. | 80% | WIP
2. Once this testing is done, we will be starting with QMVAR integration with this task to fetch data from this url and run specific center task on specific date and also obtain email id.
16 | 2022-07-22 | RPA GSS | 1. The development for the SRN task has been completed, whereas the testing is work in progress. | 90% | WIP
17 | 2022-07-25 | RPA GSS | 1. The test at SRN task is going on and during test, we are facing the pagination issue means records are presented on multiple pages and whereas after clicking back button it is going to home page instead of currect page, I am working on this issue to fix and it is a complex one. | 95% | WIP
18 | 2022-07-26 | RPA GSS | 1. The SRN task has been completed to download multiple files, finding differnece between stock overview and return parts files and also from multiple pages, and sending email with attachments, tested and it is running smoothly, whereas the latest suggestion is working progress (start from the last downloaded in case failed task during download) | 95% | WIP
2. The updated source code has been shared to Mohan san now.
19 | 2022-07-27 | RPA GSS | 1. Correction received for the SRN process task due to new folder creation like SRN under temp folder and all the files will be processed here before sending an attachment and it is done now, and another process to verifying that whether the stock overview file is downloaded or not and it is work in progress. | 80% | WIP
20 | 2022-07-28 | RPA GSS | 1. Correction received for the SRN process task to verify whether the stock over view file is downloaded and Following that, the SRN files are getting downloaded and moved to backup, these are verified and it is going smooth, and other correction is about email sending function to fetch email credential from database is work in progress | 90% | WIP
|  |  | 2. We are downloading the files for the SRN Process and sending in email, right now the SSC8 is running and other SSCs are completed | 90% | WIP
21 | 2022-07-29 | RPA GSS | 1. Correction received from the SRN Process task due to email sending modification, it has been completed, tested and it is running smoothly. | 100% | WIP

## AUG-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-08-01 | RPA GSS | The correction received from the SRN task due to improper ending with an error when no data was found during task execution, now it has been fixed, tested in all SSCs and it is running smoothly and the updated code has been shared to Mohan san | 100% | Completed
2 | 2022-08-02 | RPA GSS | 1. Running the Service Order Parts Number task to fetch parts number and it is going on at GSPN site (around 821 records (Parts number) to fetch) | 50%
|  | DOTNET Learning | 1. Downloaded and Installation of Visual Studio 2022 has been done
|  |  | 2. Learning the C# has been started | 10%
3 | 2022-08-03 |  | 1. Running the Service Order Parts Number task to fetch parts number and it is going on at GSPN site (around 500 records or Parts numbers are fetched and others records are fetching progress)
2. Learning the data types (premitive) etc.
4 | 2022-08-04 | RPA GSS | 1. Correction received from SRN task due to download page is not displayed due to internet slow or page is not loading properly and now it has been fixed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Running the Service Order Parts Number task to fetch parts number and it is going on at GSPN site (around 690 records or Parts numbers are fetched and others records are fetching progress) | 80% | WIP
5 | 2022-08-08 | RPA GSS | 1. Correction received from the Service Order Parts number task due to gspn is not loading at SSC3, now it has been fixed, tested and it is running smoothly. | 100 | Completed
|  |  | 2. Running the Service Order Parts Number task to fetch parts number and it is going on at GSPN site (around 250 records or Parts numbers are fetched and others records are fetching progress) (for SSC8 and SSC6) and Now SSC6 is going on | 60% | WIP
3. Learning the C# (control statements and doing some practices).
6 | 2022-08-09 | RPA GSS | 1. Executed the task of Service Order Parts Number task to fetch parts number for the SSC6 and SSC3 has been completed, a few issues at SSC3 also fixed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Learning the C# ( control statements, constructor and doing some practices). |  | WIP
7 | 2022-08-10 | RPA GSS | 1. Integration of the multiple tasks into Single is work in progress and creating a each task with minimal functionality to integrate later. | 20% | WIP
8 | 2022-08-11 | RPA GSS | 1. Creating a separate task for each task with minimal functionality, it is done for the DRS and Warranty, whereas updating at Database is work in progress | 25 | WIP
2. Attended zoom meeting with Rlogic Singapore to get requirments
9 | 2022-08-12 | RPA GSS | 1. A few changes receieved from the SRN process task and it has been completed around 70%, and other process is work in progress. | 70% | WIP
10 | 2022-08-17 | RPA GSS | 1. A few changes requests (changes) has been implemented based on the client request in the final report at the SRN Process task, completed, tested and it is running smoothly | 100% | Completed
|  |  | 2. Preparation has been done for the PREDEMO | 100% | Completed
|  |  | 3. Supported to create PPT for the DRS workflow from download to upload. | 100% | Completed
11 | 2022-08-18 | RPA GSS | 1. A few new updates or changes are received for the SRN Process task, and it has been completed, tested and it is running smoothly | 100% | Completed
2. Attended zoom meeting with Rlogic Singapore to get requirments (RPA Demo)
12 | 2022-08-19 | RPA GSS | 1. A few changes updates are requested by Mohan san like bringing a Delivery Number during merge and, Multiply with MAP amount as new column and it has been implemented, tested and it is running smoothly, (whereas row count is mismatching difference is there and am looking a solution for this).
13 | 2022-08-22 | RPA GSS | 1. Correction received from the SRN process for the merge issue and it has been fixed, tested, and it is running smoothly( Development was correct whereas the wrong file has been delivered for the merging file with filtered and it was supposed to be a without filter) | 100% | Completed
|  |  | 2. I am running for SSC3 to give a merge file for the SRN process task and it is work in progress | 10% | WIP
14 | 2022-08-23 | RPA GSS | 1. A few updates are done at SRN process to send attachment after merging all the xls files to the client along with final files. (Merged_orginal",and SRN final file) | 100% | Completed
15 | 2022-08-24 | RPA GSS | 1. A few email sending corrections were receievd for the SRN Process to send multiple recipients and it has been completed as the columns are changed in database. | 50% | WIP
|  |  | 2. The Task integration is work in progress( Recording at database has been completed at RPALIVELOG and RPALIVESTATUS table) | 80% | WIP
16 | 2022-08-25 | RPA GSS | 1. The task integration has been completed for the DRS and Warranty, recording at database is success, logs writing etc and tested in few SSCs and it is running smoothly. | 100% | Completed
|  |  | 2. Integrating the POC task is work in progress. | 10% | WIP
17 | 2022-08-26 | RPA GSS | 1. Creating a POC task with minimal functionality has been done. | 100% | Completed
|  |  | 2. Integration of the POC task has been completed and the testing is work in progress. | 80% | WIP
18 | 2022-08-29 | RPA GSS | 1. The task integration has been completed for the POC task and PR Summary task, recording at database is success, logs writing etc and tested in few SSCs and it is running smoothly, whereas the testing at PR summary is work in progress | 80% | WIP
19 | 2022-08-30 | RPA GSS | 1. The task integration has been completed for the Service Order Cancelled task, recording at database is success, logs writing etc and tested in few SSCs and it is running smoothly, whereas the testing at Service Order Cancelled task is work in progress | 80% | WIP
20 | 2022-09-01

## SEP-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-09-01 | RPA GSS | 1. Five tasks are integrated successfully for the GSPN dailies. | 100% | Completed
2. Correction received for the SAW DISCOUNT task due to index error and it is work in progress.
2 | 2022-09-02 | RPA GSS | 1. The issue at Saw Discount has been fixed, tested and it is running smoothly | 100% | Completed | ( issue was if records are 1000)
|  |  | 2. Correction Received from the OtherSales due to non approval of invoice, it has been fixed, tested and it is running smoothly | 100% | Completed | (issue was non approval of GRN status instead of SalesInvoice)
|  |  | 3. Extracting the parts number task is work in progress. | 20%
3 | 2022-09-05 | RPA GSS | 1. A few Enhancement has been done at SAW DISCOUNT Task to filter to select saw status xls files and it is tested and it is running smoothly | 100% | Completed
|  |  | 2. Running the Service Order Parts number extraction task since 12:30, around 250 parts numbers are fetched and other is in progress | 20% | WIP
4 | 2022-09-06 | RPA GSS | 1. Running the Service Order Parts Number extraction task is in progress, so far 837 records were extracted out of 1122, whereas above 300 records is yet to fetch and it is going on. | 70% | WIP
5 | 2022-09-07 | RPA GSS | 1. Execution of the Service Order Parts Number task has been completed for the SSC10 and uploaded the csv file is success | 100% | WIP
|  |  | 2. A few enhancement has been implemented at Service Order Pending task based on Mohan san request and it is tested and it is running smoothly. | 100% | Completed
|  |  | 3. Other task of task integration is work in progress | 60% | WIP
6 | 2022-09-08 | RPA GSS | 1. Integrating the RAO Stock Over View task is work in progress | 30% | WIP
7 | 2022-09-12 | RPA GSS | 1. Integrating the RAO Stock Over View task has been completed, whereas the testing is work in progress | 80% | WIP
8 | 2022-09-13 | RPA GSS | 1. In Integration task for RAO stockoverview task is going on as it having different workflow with complexity and and it is work in progress, | 90% | WIP
9 | 2022-09-14 | RPA GSS | 1. All most is completed task integration whereas the testing is work in progress. | 95% | WIP
2. Due to internet issue, we could not do our regular activities at the newbot remotely. it is affected more today.
10 | 2022-09-15 | RPA GSS | 1. The RAO Stock Over View task has been integrated, tested and it is running smoothly. | 100% | Completed
11 | 2022-09-16 | RPA GSS | 1. The task integration is work in progress for Communication board clear task | 30% | WIP
12 | 2022-09-19 | RPA GSS | 1. Six tasks are integrated for the dailies task, whereas the testing is going on at integrated task | 100% | Completed
|  |  | 2. A correction received from SRN process, the task has been executed, it is not creating any error in the reports and Mohan san is re-running the same task at server side and it is going on, we will do based on the recent execution once he confirm us. | 100% | Completed
|  |  | 3. The task integration is work in progress for Communication board clear task | 30% | WIP
13 | 2022-09-20 | RPA GSS | 1. After re-running the SRN process task, no isssue has been found and it is fine. | 100% | Completed
2. The task integration is work in progress for Communication board clear task
14 | 2022-09-21 | RPA GSS | 1. Created a communication board clear task with minimal function, tested in few SSCs and it is running smoothly, whereas the integration process is work in progress | 70% | WIP
15 | 2022-09-22 | RPA GSS | 1. Task integration has been completed for the Communication board cleared task, tested and it is running smoothly, so far, we have integrated only seven tasks for the dailies, whereas final testing is going on for the entire workflow of the integration. | 100% | Completed
16 | 2022-09-23 | RPA GSS | 1. The sample test has been completed for seven integrated tasks, it is running smoothly, task statuses are recorded in database, logs are writing properly for the dailies | 100% | Completed
|  |  | 2. Integration of the activity task will be started soon. | 10% | WIP
17 | 2022-09-26 | RPA GSS | 1. Integration of the activity task is work in progress, Analyzing the activity task to create activity task with minimal functionality and other processes are work in progress towards the task integration steps. | 10% | WIP
18 | 2022-09-27 | RPA GSS | 1. Integration of the activity task is work in progress | 15% | WIP
|  |  | 2. A correction was received from the DRS Daily task due to more than 5000 records, they are not downloading and now the logic has been changed and implemented, tested and it is downloading a more than 5000 records and uploading smoothly | 100% | Completed
|  |  | 3. Whereas to implement the same at DRS Monthly is work in progress | 10% | WIP
19 | 2022-09-28 | RPA GSS | 1. A correction received from the ACTIVITY Daily task due to DRS daily file is getting overlapped with this task, now it has been fixed by avoiding drs file at activity task, tested in all SSCs and it is running smoothly. | 100% | Completed
|  |  | 2. A DRS Monthly task has been received due to the above records are not getting downloaded and uploaded, now it has been fixed by implementing new logic, tested in all SSCs and it is running smoothly. | 100% | Completed
20 | 2022-09-29 | RPA GSS | 1. Created an activity task with minimal functionality, recording at the database, writing at log file are completed, whereas the integration process is work in progress. | 100% | Completed
21 | 2022-09-30 | RPA GSS | 1. The task integration has been completed, whereas the testing is work in progress. | 70% | WIP

## OCT-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-10-03 | RPA GSS | 1. A Correction received from the DRS Daily and DRS Monthly tasks due to DRS Excel file is overlapping with StockOverView file and hence it is failed. Now it has been fixed by filtering to select a DRS file only and it is tested in all SSCs and it is running smoothly | 100% | Completed
| 2022-10-06 | RPA GSS | 1. A Correction received from the Service Order pending task for the SSC11 as it was failed during upload, it is work in progress as it has 130 files to download etc . | 70% | WIP
| 2022-10-07 | RPA GSS | 1. Root cause has been found at Service Order Pending task, this task was failed during upload that one date column is not having proper format ( it is having all zeros instead of proper date) | 70% | WIP
2. Now new logic has been suggested, based on that, the failed Excel files will be bypassed and right files will be uploaded, and it has been fixed now, whereas other steps are work in progress
| 2022-10-10 | RPA GSS | Running the Service Order Pending task is going smooth and it will be completed by 7:30 PM mostly for the SSC11 | 100% | Completed
| 2022-10-11 | RPA RLOGIC | 1. The POC for the RLOGIC RPA has been completed from Login to till email pasting, and around 60R% task is completed. | 60% | WIP
and other steps are work in progress.
| 2022-10-12 | RPA RLOGIC | 1. Except the phone number field, all fields are inserted, whereas duplicate entry alert is coming in new window before saving the records, and i am working on to close and it is work in progress. | 80% | WIP
|  | RPA GSS | 1. One correction received from DRS daily due to downloading error, it is fixed by increasing delay before copying the downloaded file, tested, and it is running smoothly. | 100% | Completed
| 2022-10-13 | RPA RLOGIC | 1. For the POC process of the RLOGIC-SG has been completed from Login to till saving data dynamically success, whereas the reading data from excel file to insert into the website is work in progress and applying are logs are pending. | 90% | WIP
| 2022-10-14 | RPA RLOGIC | 1. Supported to the Rlogic POC process
|  | RPA GSS | 2. A modifications has been received from the SRN process today and it is work in progress | 20% | WIP
| 2022-10-17 | RPA GSS | 1. Delivery Date column has been placed at the Final report for the SRN Process | 100% | Completed
|  |  | 2. Downloading the PartsIO Excel has been completed, whereas the converting the xls to CSV is work in progress for the SRN task | 40% | WIP
| 2022-10-18 | RPA GSS | 1. Converting the PartsIO excel file has been completed, whereas the generating the final report is work in progress for the SRN Process task | 60% | WIP
| 2022-10-19 | RPA GSS | 1. The new modification has been completed for the SRN process, whereas the testing is going on to compare the PartsIo report with SRN final reports and it is work in progress. | 80% | WIP
| 2022-10-20 | RPA GSS | 1. The new modification for the SRN Process has been completed, generated report and compared with PartsIO report and shared to Mohan san to validate, whereas one more calculation is work in progress based on new suggestion from Mohan san. | 90% | WIP
| 2022-10-21 | RPA GSS | 1. The downloaded files and csv files are moved to backup folder once email sending is success dynamically for the SRN Modification process. | 100% | Completed
2. The updated source code has been shared to Mohan san now.
| 2022-10-25 | RPA GSS | Supported to SRN Modification process today for the below mentioned points: | 60% | WIP
1. removing duplicate records after merging the all SRN downloaded files
2. subtracting previous qty with war house qty
3. multiplying the map amount by point no:2 results etc
and it is work in progress.
| 2022-10-26 | RPA GSS | 1. Corrections at SRN process task is work in progress at SSC11 | 70% | WIP
|  |  | 2. DRS correction at SSC10 is work in progress. | 80% | WIP
| 2022-10-27 | RPA GSS | 1. Supported to SRN Modification process based on the Mohan san suggestion, completed, testing is going on except SSC9.
2. A few customization has been done at SSC9 separately as SSC9 has been combined with SSC8, and few more steps or development to be done to download SSC9 data for SRN process and it is work in progress
| 2022-10-28 | RPA GSS | 1. A two new script file has been created (customized due to combined SSC9 with SSC8) to download at SSC8 and SSC9 files from GSPN separately, tested, and it is running smoothly | 100% | Completed
| 2022-10-31 | RPA GSS | 1. The issue at DRS daily (downloading issue) has been fixed by increasing the delay after click at search, after clicking at Download and before renaming the downloaded file, tested in all SSCs and it is running smoothly.

## NOV-22
Date | Application | Task | % of completion | Status | Comments
2022-11-01 | RPA GSS | 1. A correction received from the DRS Daily task due to date issue. The issue at DRS Daily was the date function, it has been fixed, tested in few SSCs and it is running smoothly. | 100% | Completed
|  | 2. SSC1 has been executed for the Service Order Pending task and it is completed from download to upload | 100% | Completed
|  | 3. SSC11 is running now of the Service Order Pending task and it will be completed by 9:00 PM today. (now the uploading is going on and it has a around 130 files to upload) | 70% | WIP
2022-11-02 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly is going on and around 250 parts numbers are fetched out of 922 parts number and remaining is in progress for the SSC11. | 50% | WIP | (3&4 are leave)
2022-11-07 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly is going on and around 290 parts numbers are | 40% | WIP
fetched out of 1117 parts number and remaining is in progress for the SSC10.
2022-11-08 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly is going on and around 900 parts numbers are fetched out of 1117 parts number and remaining is in progress for the SSC10 and it will be completed and will be uploaded by 9:30PM today | 80% | WIP
2022-11-09 | RPA GSS | 1. Creating activity task with minimal functionality has been completed and testing is in progress, once the testing is over, we will start integration steps for the same. | 60% | WIP
2022-11-10 | RPA GSS | 1. The testing has been completed for the Activity daily task before integration and it is success | 100% | Completed
|  | 2. The integration has been completed, tested and it is running smoothly for the Activity daily task | 100% | Completed
2022-11-11 | RPA GSS | 1. The task integration process is work in progress for the GRSummary and GRDetails daily task. | 20% | WIP
2022-11-14 | RPA GSS | 1. Created a GRS and GRDetails task with minimal functionality to extract, download and convert xls files to clsv and it is uploading the both GRS and GRD files smoothly as individual task, and now, the testing is work in progress, once it is over, we will integrate it and test it once again. | 60% | WIP
2022-11-15 | RPA GSS | 1. The testing has been completed for the GRSummary and GRDetails daily task before integration, also the integration has been completed for the GRS and GRD and also tested this task after integration and it is success. | 100% | Completed
2022-11-16 | RPA GSS | 1. A correction received from DRS daily task due to downloading error and it has been fixed, tested in all SSCs and it is running smoothly from download to upload.
|  | 2. Creating a SERVICE_PART_RETURN_DAILY task with minimal functionality towards the task integration process is work in progress | 20% | WIP
2022-11-17 | RPA GSS | 1. A correction received from DRS daily task due to downloading error at SSC6 and it has been fixed by approaching new logic and implemented at Search place and download place, and it is tested in all SSCs and it is running smoothly from download to upload. | 100% | Completed
|  | 2. The downloading portion has been completed for SERVICE_PART_RETURN_DAILY task towards the task integration process, whereas the converting xls to csv and uploading process are work in progress | 25% | WIP
2022-11-18 | RPA GSS | 1. Correction received from DRS daily task, and it has been fixed, tested and it is running smoothly. | 100% | Completed
|  | 2. SERVICE_PART_RETURN_DAILY task towards the task integration process, whereas the converting xls to csv and uploading process are work in progress(recording at database and etc is work in progress. | 30% | WIP
2022-11-21 | RPA GSS | 1. A correction received from the DRS Daily task due to the issue( no excel file is downloaded) at in SSC3 ( has been fixed by placing the downloading code twice in else portion in addition to if portion, tested in all SSCs, and it is running smoothly. | 100% | Completed
|  |  | 60% | WIP
2022-11-22 | RPA GSS | 1. The integration process has been completed, tested in all SSCs for the SERVICE_PART_RETURN_DAILY TASK and it is running smoothly. Till now, the below mentioned tasks are integrated and completed for the Daily tasks | 100% | Completed
1. DRS Daily,
2. WARRANTY Daily,
3. POC Daily
4. PR SUMMARY Daily
5. Service Order Cancelled Daily
6. RAO Stock Over View
7. Communication Board Clear task,
8. Activity Daily task,
9. GRSummary and GRDetails Daily task is work in progress
10. SERVICE_PART_RETURN_DAILY is pending
2022-11-23 | RPA GSS | 1. Correction received from the DRS daily task due to status is not updated at database for the SSC1, SSC2 and SSC10, and it has been fixed, tested in few SSCs and the status is getting updated at database and it is running smoothly. | 100% | Completed
|  | 2. The task integration process is work in progress for the Weekly task. | 10% | WIP
2022-11-24 | RPA GSS | 1. Created a INVOICE_UPDATE_OOW_WEEKLY_Task with minimal functionality to download, converting xls to CSV and uploading to QMVAR has been completed and the testing is work in progress. | 50% | WIP
2022-11-25 | RPA GSS | 1. The task integration process for the INVOICE_UPDATE_OOW_WEEKLY_Task has been completed, tested it as single task in all SSCs and it is running smoothly, whereas the integration process is work in progress and the following one more testing will be done once integration is done. | 80% | WIP
|  | 2. The updated source code for the daily tasks has been shared to Mohan san | 100% | Completed
2022-11-28 | RPA GSS | 1. The task integration process for the INVOICE_UPDATE_OOW_WEEKLY_Task has been completed, we are getting an error during updating a database and the checking is work in progress. | 90% | WIP
2022-11-29 | RPA GSS | 1. The task integration has been completed for the INVOICE_UPDATE_OOW_WEEKLY_TASK, and the testing is going on and it may be completed by 8:00 pm and this test was only to run this task without any issue along with daily task, | 100% | Completed
|  | 2. whereas to run on only specific day based on the previous week executed date, we need to check with database to decide whether the task was executed or not, the task should not run if already the task was success based on the database status or else it should run for the previous week, this is the logic to be implemented and it is work in progress for the weekly. | 50% | WIP
2022-11-30 | RPA GSS | 1. For the INVOICE_UPDATE_OOW_WEEKLY_TASK - the task integration process has been completed, tested and it is running smoothly from download to upload.
|  | 2. Created a user-defined function to check whether this task was executed already or not, if not it will run or else it will be paused as it is integrated with daily task. | 100% | Completed

## DEC-22
Date | Application | Task | % of completion | Status | Comments
2022-12-01 | RPA GSS | 1. Created a PR_SUMMARY_10DAYS_TASK with minimal functionality to download, converting xls to csv file and uploading CSV at QMVAR2 towards the task integration process and it is tested in all SSCs and it is running smoothly | 60% | WIP
2. Whereas the integration process and other steps are work in progress
2022-12-02 | RPA GSS | 1. The integration process has been completed, tested in Few SSCs and it is running smoothly for the PR_SUMMARY_10DAYS_TASK, whereas a new logic to be implemented to avoid running with daily tasks, we have to create a user-defined function to run on specified date (three times in a month) and it is work in progress. | 80% | WIP
2022-12-07 | RPA GSS | 1. The integration process has been completed, tested in few SSCs and it is running smoothly for the PR_SUMMARY_10DAYS_TASK, In addition to this, we have created a userdefined function to check whether this task is executed or not on each day as it has been integrated with daily task. it will be running the entire task if the task is not executed for the past 10 days, likewise it will check and run whenever the 10days are completed. | 100% | Completed
2022-12-08 | RPA GSS | 1. Created a PR_DETAILS_10DAYS_TASK with minimal functionality to download, converting xls to csv file and uploading CSV at QMVAR2 towards the task integration process and it is tested in all SSCs and it is running smoothly
2. whereas the integration process and other steps are work in progress
2022-12-09 | RPA GSS | 1. Following the completion of the integration for the PR_DETAILS_10DAYS_TASK, it has been tested in few SSCs as individually and also with multiple SSCs, and it is running smoothly. | 100% | Completed
2. This task will run on every 10 days even this task is integrated with daily task, and such a way the logic has been implemented. ( it will be running the entire task if the task is not executed for the past 10 days, likewise it will check and run whenever the 10days are completed)
3. With this, the weekly and 10days tasks are completed
4. The following tasks are weekly and 10days tasks: 1. INVOICE_UPDATE_OOW_WEEKLY_TASK 2. PR _SUMMARY_10DAYS_TASK 3. PR_SUMMARY_10DAYS_TASK
2022-12-12 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly task has been completed for the SSC10 and it has a 228 records and the csv file has been uploaded at QMVAR smoothly | 100% | Completed
2.and whereas the SSC11 is running now and it is having a around 838 records.
2022-12-13 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly task for the SSC11 and around a 250 records are fetched from 838 records and the remaining records are in progress | 30% | WIP
2022-12-14 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly task for the SSC11 and around a 768 records are fetched from 838 records and the remaining records are in progress | 60% | WIP
2. This will be completed by tonight mostly.
2022-12-15 | RPA GSS | 1. Running the Service Order Part Number Capturing monthly task has been completed for the SSC11 and it has a 838 records and the csv file has been uploaded at QMVAR smoothly | 100% | Completed
|  | 2. The issue at Service Order Pending Monthly Task is work in progress | 30% | WIP
2022-12-16 | RPA GSS | 1. Following the corrections received, We have implemented to record at txt file in SOP folder during task run to check whether the downloaded files are uploaded or not, and also it will record details about downloaded files list as well as uploaded files list and also recorded failed files list in case failed upload files for the Service Order Pending task. | 100% | Completed
2022-12-19 | RPA GSS | 1. Created a DRS_MONTHLY_Task with minimal functionality to download, converting xls to CSV and uploading to QMVAR has been completed and the testing is work in progress. | 60% | WIP
2022-12-20 | RPA GSS | 1. The integration process has been completed for DRS Monthly task, tested in few SSCs and it is running smoothly to download and upload (also implemented to run only once in a month if not run already), | 100% | Completed