## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/01/2021 | Holiday | New Year
2 | 02/01/2021 | WeekEnd
3 | 03/01/2021 | WeekEnd
4 | 04/01/2021 | Hayaai | Image issue discussed with syed san and understand database tables
5 | 05/01/2021 | Hayaai and Github | Old image not populating as per Nirmal san mail checked in database and sent mail, gitup looking for source code integration
6 | 06/01/2021 | Hayaai and Github | As per matheswari san mail send screenshot for images from db and Github integration going on
7 | 07/01/2021 | Hayaai,QMVar and Github | As per syed san mail send screenshot for different series id, gathering QMVar requirments from Mohan san and github integration process going on
8 | 08/01/2021 | QMVar and Github | Discussed with Mohan san about requirements clarifications for sony and samsung and github integration going on
9 | 09/01/2021 | WeekEnd
10 | 10/01/2021 | WeekEnd
11 | 11/01/2021 | Github | Github integration done from local to server code fetched and giving permission process going on
12 | 12/01/2021 | Github | Github integration done in Ram system and prabu system is in process.
13 | 13/01/2021 | Github | Github integration done in Prabu system and admin previliges also completed
14 | 14/01/2021 | Holiday | Pongal festival
15 | 15/01/2021 | Holiday | Pongal festival
16 | 16/01/2021 | WeekEnd
17 | 17/01/2021 | WeekEnd
18 | 18/01/2021 | Github | Soniya integration with Github going on
19 | 19/01/2021 | Github | Soniya integration with Github going on
20 | 20/01/2021 | Github | Soniya integration in Github done
21 | 21/01/2021 | QMVar | Setup New service center development going on
22 | 22/01/2021
23 | 23/01/2021 | WeekEnd
24 | 24/01/2021 | WeekEnd
25 | 25/01/2021
26 | 26/01/2021
27 | 27/01/2021
28 | 28/01/2021
29 | 29/01/2021
30 | 30/01/2021 | WeekEnd
31 | 31/01/2021 | WeekEnd

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold