## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-10-01 | RPA SAMSUNG | Correction Received for DRS-Monthly, SAW Discount Monthly and ReturnCredit Monthly tasks | 100% | Completed
2 | 2020-10-01 | RPA SONY | A 7 files are uploaded with customization in single approach for Scheduling Reports tasks | 70% | WIP
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | VASTU | Checking date time issue | 100% | Completed
2 | 2020-10-01 | RPA Dotnet | Project set up | 100% | Completed
3 | 2020-10-05 | QMVAR | DRS Count - Saw Discount changes and Issue | 100% | Completed
4 | 2020-10-06 | QMVAR | DRS Count - Saw Discount Summary & Details | 50% | WIP
5 | 2020-10-07 | QMVAR | DRS - Daily Revenue | 20% | WIP
6 | 2020-10-08 | QMVAR | DRS - Daily Revenue | 40% | WIP
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-01-10 | QMVAR-RPA | InvoiceUpdate IW/OW error correction | 100% | Completed
2 | 2020-05-10 | HAYAAI-B2B | New API for inserting job sheet details for Pickup | 50% | wip
3 | 2020-06-10 | HAYAAI-B2B | New API for inserting job sheet details for Pickup | 100% | Completed
4 | 2020-07-10 | HAYAAI-B2B | Correction Job Details API to get Pickup Ack information | 100% | Completed
5 | 2020-08-10 | HAYAAI-B2C | In /instantfix/create and instantfix/update: Have added "warranty_type":"OUT" ,so please pass this argument to this APIs, Also in Service request have updated job_id also now status would Requested instead of Job_in_progress,also Warranty_type is stored in RST_JOB Also in updateimei-> API whatever parameters are passed it is stored in warranty information,the one as same as in add devices | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | QMVAR | Application- Login page designed | 100% | Completed
2 | 2020-10-05 | QMVAR | Application- Login page and Front end sample Layout design. Sample completed | 100% | Completed
3 | 2020-10-06 | QMVAR | Application- Front end sample 2nd Layout design. Sample completed | 100% | Completed
4 | 2020-10-07 | QMVAR , Hayaai | Application- login design and Hayaai Flyer design | 40% | WIP
5 | 2020-10-08 | Hayaai | Two sample Flyer design | 80% | WIP
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | Selenium log file | Selenium log file count , and Return Credit(Issue Checking and Solving QMVAR) | 100% | Completed | Daily and Monthly tasks Checking
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | QMVAR | DRS Count Design | 100% | Completed
2 | 2020-10-01 | RPA | Testing Data | 100% | Completed
2 | 2020-10-02 |  | Holiday
3 | 2020-10-03 |  | Week off
4 | 2020-10-04 |  | Week off
5 | 2020-10-05 | Soniya | creating Setup file | 50% | WIP
6 | 2020-10-06 | Soniya | creating Setup file | 100% | Completed
5 | 2020-10-07 | QMVAR | Layout Designing |  | WIP
Status
| WIP | WIP
Pending
| Completed | Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Nirmal
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C app, Hayaai site and Load Testing on B2C app | 50% | WIP
2 | 2020-10-02 |  | Holiday
3 | 2020-10-03 |  | Week off
4 | 2020-10-04 |  | Week off
5 | 2020-10-05 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C app, Hayaai site and Load Testing on B2C app | 100% | Completed
6 | 2020-10-06 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C app and Hayaai site | 100% | Completed
7 | 2020-10-07 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C app and Hayaai site | 100% | Completed
8 | 2020-10-08 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C app and Hayaai site | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Balaji
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold