## Aug-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/08/2021 | WeekEnd
2 | 02/08/2021 | QMVAR | Weekly Report some alignment issues handled in graph page
3 | 03/08/2021 | QMVAR | Weekly Report checked datas various months and sent to deployment
4 | 04/08/2021 | QMVAR | Call Load Requirment gathering going on
5 | 05/08/2021 | Leave | Sick Leave
6 | 06/08/2021 | QMVAR | Call Load Requirment analysis going on
7 | 07/08/2021 | WeekEnd
8 | 08/08/2021 | WeekEnd
9 | 09/08/2021 | QMVAR | Calload analysis and implementation going on
10 | 10/08/2021 | QMVAR | Call load analysis design page done and code implementation going on
11 | 11/08/2021 | QMVAR | Call load db implementaion going on
12 | 12/08/2021 | QMVAR | Call load db implementaion done and code implemetation going on
13 | 13/08/2021 | QMVAR | Call load code implementaion done and testing going on
14 | 14/08/2021 | WeekEnd | Call load testing done and sent to deployment
15 | 15/08/2021 | WeekEnd
16 | 16/08/2021 | Leave | Personal Leave
17 | 17/08/2021 | QMVAR | Monthly Target Screen added Call load count field in page and implementation going on
18 | 18/08/2021 | QMVAR | Monthly Target screen db added two fields and implementation done
19 | 19/08/2021 | QMVAR | Monthly Target Screen Search button added and implementaion going on
20 | 20/08/2021 | QMVAR | Monthly Target Screen logic added and implemented
21 | 21/08/2021 | WeekEnd
22 | 22/08/2021 | WeekEnd
23 | 23/08/2021 | QMVAR | Monthly Target screen Search button issues and weekly and Call load report alignment based on JP report going on
24 | 24/08/2021 | QMVAR | Monthly Target screen Search button issues and weekly and Call load report alignment based on JP report done
25 | 25/08/2021 | Leave | Sick Leave
26 | 26/08/2021 | Leave | Sick Leave
27 | 27/08/2021 | QMVAR | Mobile View Alignment issues going on
28 | 28/08/2021 | WeekEnd
29 | 29/08/2021 | WeekEnd | Mobile View Alignment issues going on
30 | 30/08/2021 | QMVAR | Mobile View Alignment issues going on
31 | 31/08/2021 | QMVAR