## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | Soniya | DB Checking for Best Denki - best_mnt_vdr,best_mnt_shop | 100% | Completed
2 | 2020-09-02 | Soniya | DB Checking for Best Denki - best_mnt_cat,best_mnt_menu | 100% | Completed
3 | 2020-09-03 | Soniya | DB Checking for Best Denki - best_close,best_close_return | 50% | Completed
4 | 2020-09-04 | Soniya | DB Checking for Best Denki - best_err_mnt,best_exp_SB02 | 100% | Completed
5 | 2020-09-05 | Sat & Sun
6 | 2020-08-06
7 | 2020-09-07 | Soniya | DB Checking for Best Denki - best_exp_SB03,best_input | 100% | Completed
8 | 2020-09-08 | Soniya | DB Checking for Best Denki - best_ivc_close,best_ivc_close_return | 100% | Completed
9 | 2020-09-09 | Soniya | DB Checking for Best Denki - best_ivc_err_mnt,best_ivc_export | 100% | Completed
10 | 2020-09-10 | Soniya | DB Checking for Best Denki - best_ivc_import,best_ivc_input | 100% | Completed
11 | 2020-09-11 | Soniya | DB Checking for Best Denki - best_ivc_menu,best_ivc_report | 100% | Completed
12 | 2020-09-12 | Sat & Sun
13 | 2020-09-13
14 | 2020-09-14 | Soniya | DB Checking for Best Denki - best_ivc_search,best_report | 100% | Completed
15 | 2020-09-15 | Soniya | DB Checking for Best Denki - best_search,best_search_setup | 100% | Completed
16 | 2020-09-16 | Soniya | DB Checking for Best Denki - best_wrn_new | 100% | Completed
17 | 2020-09-17 | Soniya | DB Checking for Best Denki - best_yamada_import | 100% | Completed
18 | 2020-09-18 | Soniya | DB Checking for Best Denki 2 - best_intl_search | 100% | Completed
19 | 2020-09-19 | Sat & Sun
20 | 2020-09-20
21 | 2020-09-21 | QMVAR | QMVAR Monthly_Adandon(File Upload And Export) | 100% | Completed
22 | 2020-09-22 | Vastu | Vastu - Fixed Suman san raised issues | 100% | Completed
23 | 2020-09-23 | Vastu | Vastu - Fixed Suman san raised issues | 100% | Completed
24 | 2020-09-24 | Vastu | Vastu - Fixed Suman san raised issues | 100% | Completed
25 | 2020-09-25 | nQGCare | Analyzed nQGCare | 100% | Wip

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | Sonia | Setup file creation for best_close,best_close_return,best_err_mnt | 100% | Completed
2 | 2020-10-02 | Sonia | Setup file creation for best_exp_sb02,best_exp_sb03 | 100% | Completed
3 | 2020-10-05 | Sonia | Setup file creation for best_imput,best_ivc_close | 100% | Completed
4 | 2020-10-06 | Sonia | Setup file creation for best_ivc_close_return,best_ivc_err_mnt | 100% | Completed
5 | 2020-10-07 | Sonia | Setup file creation for best_ivc_export,best_ivc_import | 100% | Completed
6 | 2020-10-08 | Sonia | Setup file creation for best_ivc_input,best_ivc_menu | 100% | Completed
7 | 2020-10-09 | Sonia | Setup file creation for best_ivc_report,best_ivc_search | 100% | Completed
8 | 2020-10-12 | Sonia | Setup file creation for best_mnt_cat,best_mnt_menu | 100% | Completed
9 | 2020-10-13 | Sonia | Setup file creation for best_mnt_shop,best_search | 100% | Completed
10 | 2020-10-14 | Sonia | Setup file creation for best_mnt_vdr,best_report | 100% | Completed
11 | 2020-10-15 | Sonia | Setup file creation for best_close_report | 100% | Completed
12 | 2020-10-16 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
13 | 2020-10-20 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
14 | 2020-10-21 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
15 | 2020-10-22 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
16 | 2020-10-23 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
17 | 2020-10-27 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
18 | 2020-10-28 | Sonia
19 | 2020-10-29 | Sonia
Status
WIP
Pending
Completed
Hold

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-01 |  | Week off
2 | 2020-11-02 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | WIP
3 | 2020-11-03 | Sonia | Acces DB conversion - 20_BEST商品・・渡集計 |  | COMPLETED
4 | 2020-11-04 | Sonia | Acces DB conversion - bic_txt_分割_・信日 |  | WIP
5 | 2020-11-05 | Sonia | Acces DB conversion - bic_txt_分割_・信日 |  | WIP
6 | 2020-11-06 | Sonia | Acces DB conversion - bic_txt_分割_・信日 |  | COMPLETED
7 | 2020-11-07 | Sonia | Week off
8 | 2020-11-08 | Sonia
9 | 2020-11-09 | Sonia | Issue fixing - Kanyu Project |  | WIP
10 | 2020-11-10 | Sonia | Issue fixing - Ivc_err_mnt Project |  | WIP
11 | 2020-11-11 | Sonia | Issue fixing - Kanyu Project |  | WIP
12 | 2020-11-12 | Sonia | Issue fixing - Kanyu Project |  | WIP
13 | 2020-11-13 | Sonia | Issue fixing - Kanyu Project |  | COMPLETED
14 | 2020-11-14 | Sonia | Week off
15 | 2020-11-15 | Sonia
16 | 2020-11-16 | Sonia | Leave |  | WIP
17 | 2020-11-17 | Sonia | Issue fixing - Ivc_err_mnt Project |  | WIP
18 | 2020-11-18 | Sonia | Issue fixing - Ivc_err_mnt Project |  | COMPLETED
19 | 2020-11-19 | Sonia | Issue fixing -Hosyou Project |  | WIP
20 | 2020-11-20 | Sonia | Issue fixing -Hosyou Project |  | WIP
21 | 2020-11-21 | Sonia | Week off
22 | 2020-11-22 | Sonia
23 | 2020-11-23 | nMvar | nMVAR |  | WIP
24 | 2020-11-24 | Sonia | Issue fixing -Hosyou Project |  | WIP
25 | 2020-11-25 | Sonia | Issue fixing -Hosyou Project |  | WIP
26 | 2020-11-26 | Sonia | Issue fixing -Hosyou Project |  | COMPLETED
27 | 2020-11-27 | Sonia | Issue Fixing For Best_IVC_REPORT,Best_mnt_cat |  | COMPLETED

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | Sonia | Issue Fixing Sonia Best_Report_ivc |  | COMPLETED
2 | 2020-12-02 | Sonia | Issue Fixing Sonia Best_Report_ivc |  | COMPLETED
3 | 2020-12-03 | Sonia | Issue Fixing Sonia Best_Report_ivc |  | COMPLETED
4 | 2020-12-04 |  | Leave
5 | 2020-12-05 |  | Week off
6 | 2020-12-06 |  | Week off
7 | 2020-12-07 | nMvar | Nmvar Active Reports Conversion |  | COMPLETED
8 | 2020-12-08 | nMvar | Nmvar Active Reports Conversion |  | COMPLETED
9 | 2020-12-09 | nMvar | Nmvar Active Reports Conversion |  | COMPLETED
10 | 2020-12-10 | nMvar | Nmvar Active Reports Conversion |  | COMPLETED
11 | 2020-12-11 | nMvar | Nmvar Active Reports Conversion |  | COMPLETED
12 | 2020-12-12 |  | Week off
13 | 2020-12-13 |  | Week off
14 | 2020-12-14 | Qmvar | Dashbord - Qmwar 2.0 |  | COMPLETED
15 | 2020-12-15 | Qmvar | Dashbord - Qmwar 2.0 |  | COMPLETED
16 | 2020-12-16 | Qmvar | Dashbord - Qmwar 2.0 |  | COMPLETED
17 | 2020-12-17 | Qmvar | Dashbord - Qmwar 2.0 |  | COMPLETED
18 | 2020-12-18 | Qmvar | Dashbord - Qmwar 2.0 |  | COMPLETED
19 | 2020-12-19 |  | Week off
20 | 2020-12-20 |  | Week off
21 | 2020-12-21 | Nmvar | Nmvar Active Reports Conversion |  | COMPLETED
22 | 2020-12-22 | nmvar | Nmvar Active Reports Conversion |  | COMPLETED
23 | 2020-12-23 | nMvar | Nmvar Active Reports Conversion |  | COMPLETED
24 | 2020-12-24 | nmvar | Nmvar Active Reports Conversion |  | COMPLETED
25 | 2020-12-25 |  | Holiday
26 | 2020-12-26 |  | Week off
27 | 2020-12-27 | Qmvar | Dashbord creation - Qmwar 2.0 |  | COMPLETED
28 | 2020-12-28 | Qmvar | Dashboard creation -Qmvar 2.0 |  | COMPLETED
29 | 2020-12-29 | Qmvar | Dashboard creation -Qmvar 2.0 |  | COMPLETED
30 | 2020-12-30 | Qmvar | Dashboard creation -Qmvar 2.0 |  | COMPLETED
31 | 2020-12-31 | Qmvar | Dashboard creation -Qmvar 2.0 |  | COMPLETED

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-01 |  | Holiday
2 | 2021-01-02 |  | Week off
3 | 2021-01-03 |  | Week off
4 | 2021-01-04 | Qmvar | Dashbord - Right based creation |  | WIP
5 | 2021-01-05 | Qmvar | Dashbord - Right based creation |  | WIP
6 | 2021-01-06 | Qmvar | Dashbord - Right based creation |  | WIP
7 | 2021-01-07 | Qmvar | Dashbord - Right based creation |  | WIP
8 | 2021-01-08 | Qmvar | Dashbord - Right based creation |  | WIP
9 | 2021-01-09 |  | Week off
10 | 2021-01-10 |  | Week off
11 | 2021-01-11 | Mujistore | Offline Download |  | WIP
12 | 2021-01-12 | Mujistore | Offline Download |  | WIP
13 | 2021-01-13 | Mujistore | Offline Download |  | WIP
14 | 2021-01-14 |  | Holiday
15 | 2021-01-15 |  | Holiday
16 | 2021-01-16 |  | Week off
17 | 2021-01-17 |  | Week off
18 | 2021-01-18 | Mujistore | Offline Download |  | WIP
19 | 2021-01-19 | Mujistore | Offline Download |  | WIP
20 | 2021-01-20 | Mujistore | Offline Download |  | WIP
21 | 2021-01-21 | Mujistore | Offline Download |  | WIP
22 | 2021-01-22 | Mujistore | Offline Download |  | Completed
23 | 2021-01-23 |  | Week off
24 | 2021-01-24 |  | Week off
25 | 2021-01-25 | Qmvar | Dashboard |  | WIP
26 | 2021-01-26 |  | Holiday
27 | 2021-01-27 | Sonia | Issue fix for Best_ivc_repot |  | Completed
28 | 2021-01-28 |  | Holiday
29 | 2021-01-29 | Sonia | Issue fix for Best_ivc_repot |  | Completed
30 | 2021-01-30 |  | Week off
31 | 2021-01-31 |  | Week off