## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | VastuShastra & ISMI | 1) Mobile view - issue 2) ISMI Document Translation | 2) 60% | WIP
2 | 2020-09-02 | VastuShastra & ISMI | 1) Checked for Nav bar and Search vastu page fixed for Mobile view 2) ISMI Document Translation | 1)10% 2) 100% | Completed
3 | 2020-09-03 | VastuShastra | 1) Home,Search vastu,home vastu page fixed for Mobile view 2) working in Vastu tips and vastu report page | 2) 40% | WIP
4 | 2020-09-04 | VastuShastra | Admin panel back to application button fixed and working in Feedback and vastu report page | 40% | WIP
5 | 2020-09-07 | VastuShastra | mobile view in progress. | 75% | WIP
6 | 2020-09-08 | VastuShastra | mobile view in progress and issues are cleared in vastu. | 85% | WIP
7 | 2020-09-09 | VastuShastra | mobile view Login page background image need to fix and User manual created for Sonia | 100% | Completed
8 | 2020-09-10 | VastuShastra | mobile view feedback page fixed | 100% | WIP
9 | 2020-09-11 | VastuShastra | Checking for mobile view alignment issues | 70% | WIP
10 | 2020-09-14 | VastuShastra | Checking for mobile view alignment issues | 75% | WIP
11 | 2020-09-15 | VastuShastra | Checking for mobile view alignment issues | 80% | WIP
12 | 2020-09-16 | VastuShastra | Checking for mobile view alignment issues.Fixed few issues. | 85% | WIP
13 | 2020-09-17 | VastuShastra | mobile view issues closed | 95% | WIP
14 | 2020-09-18 | VastuShastra | All Issues fixed | 100% | Completed
15 | 2020-09-21 | VastuShastra , QMVAR | Issues fixed and QMVAR - ACCT_STMT in progress | 60% | WIP
16 | 2020-09-22 | QMVAR, Hayaai app | 1) QMVAR - ACCT_STMT 2)QMVAR - Daily_repairsetSetNP in progress. 3)Hayaai app screen designed | 1) 100% , 2) 60% , 3) 100% | WIP
17 | 2020-09-23 | QMVAR | QMVAR - Daily_repairsetSetNP | 100% | Completed
18 | 2020-09-24 | HAYAAI | WebsiteTranslation | 35% | WIP
19 | 2020-09-25 | HAYAAI | WebsiteTranslation | 70% | WIP
20 | 2020-09-28 | HAYAAI | WebsiteTranslation | 100% | Completed
20 | 2020-09-29 | HAYAAI | Login , nMVAR started | 30% | WIP
21 | 2020-09-30 | HAYAAI | Login issue only cleared , working in nMVAR | 50% | WIP
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | QMVAR | Application- Login page designed | 100% | Completed
2 | 2020-10-02 |  | Holiday
3 | 2020-10-03 |  | Week off
4 | 2020-10-04 |  | Week off
5 | 2020-10-05 | QMVAR | Application- Login page and Front end sample Layout design. Sample completed | 100% | Completed
6 | 2020-10-06 | QMVAR | Application- Front end sample 2nd Layout design. Sample completed | 100% | Completed
7 | 2020-10-07 | QMVAR , Hayaai | Application- login design and Hayaai Flyer design | 40% | WIP
8 | 2020-10-08 | Hayaai | Two sample Flyer design | 80% | WIP
9 | 2020-10-09 | Hayaai | 1) Flyer design completed 2) ID card created 3) Name card created | 100% | Completed
10 | 2020-10-10 |  | Week off
11 | 2020-10-11 |  | Week off
12 | 2020-10-12 | QMVAR | Analysis - File Upload - Design completed | 100% | Completed
13 | 2020-10-13 | Hayaai | Website Translation replaced in php file | 100% | Completed
14 | 2020-10-14 | Hayaai ,QMVAR | 1) Contact Card 2 samples designed 2) QMVAR - 2pages design completed | 100% | Completed
15 | 2020-10-15 | Hayaai ,QMVAR | 1) Acknowledgement screen designed 2) QMVAR - Activity Report page design completed | 100% | Completed
16 | 2020-10-16 | QMVAR | QMVAR -Analysis Data page design and alignment issues completed | 100% | Completed
17 | 2020-10-10 |  | Week off
18 | 2020-10-11 |  | Week off
19 | 2020-10-19 | QMVAR | QMVAR -Alignment fixed and Analysis Data Devlopment | 100% | Completed
20 | 2020-10-20 | QMVAR | QMVAR -Alignment issues RPA modules | 50% | WIP
21 | 2020-10-21 | QMVAR | QMVAR -RPA module | 100% | Completed
22 | 2020-10-22 | QMVAR,HAYAAI | 1) QMVAR -Alignments and design issues 2) Hayaai - Offer icon and Add icon created | 1) 45% 2) 100% | Completed
23 | 2020-10-23 | QMVAR,HAYAAI | 1) QMVAR -Alignments and design issues 2) Hayaai - Repair screen processing flow designed | 1)60% 2) 100% | Completed
24 | 2020-10-24 |  | Week off
25 | 2020-10-25 |  | Week off
26 | 2020-10-26 |  | Holiday
27 | 2020-10-27 | QMVAR | QMVAR - alignment issues | 70% | Completed
28 | 2020-10-28 | QMVAR | QMVAR -Alignment issues fixing | 80% | Completed
29 | 2020-10-29 | QMVAR | QMVAR -issues fixing | 90% | Completed
30 | 2020-10-30 | QMVAR | QMVAR -Newly highlidhted issues fixing | 80% | Completed
31 | 2020-10-31 |  | Week off
Status
WIP
Pending
Completed
Hold

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-01 |  | Week off
2 | 2020-11-02 | nMVAR , Hayaai | 1)Hayaai flyer design Editted 2)nMVAR_Invc Started | 2) 20% | WIP
3 | 2020-11-03 | nMVAR , QMVAR | 1)QMVAR - dropdown issue fixed 2)nMVAR_Invc Started | 2) 30% | WIP
4 | 2020-11-04 | nMVAR | nMVAR_QA started | 30% | WIP
5 | 2020-11-05 | nMVAR | nMVAR_QA | 50% | WIP
6 | 2020-11-06 | nMVAR | 1) nMVAR_QA 2)nMVAR_Export_bat | 80% | WIP
7 | 2020-11-07 |  | Week off
8 | 2020-11-08
9 | 2020-11-09 | nMVAR | 1) nMVAR_QA 2)nMVAR_Export_bat | 100% | COMPLETED
10 | 2020-11-10 | nMVAR | nMVAR_Import_bat | 40% | WIP
11 | 2020-11-11 | nMVAR | nMVAR_Import_bat testing with import file | 70% | WIP
12 | 2020-11-12 | nMVAR | Tested for Biccamera report soukatu - Japanese text 2) nMVAR_TSS | 2)70% | WIP
13 | 2020-11-13 | nMVAR | nMVAR_TSS | 100% | COMPLETED
14 | 2020-11-14 |  | Week off
15 | 2020-11-15
16 | 2020-11-16 | nMVAR | QA_import_bat- Errors checking | 70% | WIP
17 | 2020-11-17 |  | Leave
18 | 2020-11-18 | nMVAR | QA_import_bat - Errors completed | 100% | COMPLETED
19 | 2020-11-19 | nMVAR | QA_import_bat , QA_export_bat - tested | 100% | COMPLETED
20 | 2020-11-20 | nMVAR | nMVAR_QA tested fully | 100% | COMPLETED
21 | 2020-11-21 |  | Week off
22 | 2020-11-22
23 | 2020-11-23 | nMVAR | nMVAR_Import_bat, nMVAR_Export_bat tested and created EXE file | 100% | COMPLETED
24 | 2020-11-24 | nMVAR | nMVAR_QA - issues fixed | 100% | COMPLETED
25 | 2020-11-25 | nMVAR | nMVAR-Exe files created | 70% | COMPLETED
26 | 2020-11-26 | nMVAR | nMVAR-Exe files issues check | 100% | COMPLETED
27 | 2020-11-27 | nMVAR | Soniya Setup files created | 90% | COMPLETED
28 | 2020-11-28 |  | Week off
29 | 2020-11-29
30 | 2020-11-30 | nMVAR | Soniya Setup files created and tested | 100% | COMPLETED
Status
WIP
Pending
Completed
Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | SONIYA, nQGCare , nMVAR | SONIYA setup tested. nQGCare Setup files created | 100% | COMPLETED
2 | 2020-12-02 | nQGCare , nMVAR | nQGCare,nMVAR Setup files created | 100% | COMPLETED
3 | 2020-12-03 | nQGCare , nMVAR | nQGCare, nMVAR Report generate tested | 60% | WIP
4 | 2020-12-04 | nQGCare , nMVAR | nQGCare, nMVAR Report generate tested | 100% | COMPLETED
5 | 2020-12-05 |  | Week off
6 | 2020-12-06
7 | 2020-12-07 | nMVAR | nMVAR issues checking | 50% | WIP
8 | 2020-12-08 | nMVAR | nMVAR issues checking | 75% | WIP
9 | 2020-12-09 | nMVAR | nMVAR issues checking | 90% | WIP
10 | 2020-12-10 | nMVAR | nMVAR issues checking | 100% | COMPLETED
11 | 2020-12-11 | GSS Website | website changes are updated, Document created for Project report | 80% | WIP
12 | 2020-12-12 |  | Week off
13 | 2020-12-13
14 | 2020-12-14 | GSS, Hayaai Website | website changes are updated | 100% | COMPLETED
15 | 2020-12-15 | QMVAR, YEARLY REPORT | QMVAR issues checked , Yearly report-2020 created | 80% | WIP
16 | 2020-12-16 | YEARLY REPORT, GSS Website | 1) Yearly report-2020 created, 2) GSS website News page edited | 1) 90% 2) 30% | WIP
17 | 2020-12-17 |  | Leave
18 | 2020-12-18
19 | 2020-12-19 |  | Week Off
20 | 2020-12-20
21 | 2020-12-21 | YEARLY REPORT, GSS Website | 1) Yearly report-2020 created, 2) GSS website News page edited 3) SONIYA exe files rechecking | 1) 90% 2) 100% | WIP
22 | 2020-12-22 | YEARLY REPORT | Yearly report-2020 created | 100% | COMPLETED
23 | 2020-12-23 | Hayaai, QMVAR | 1) QMVAR- Issues checking , 2) Hayaai-B2B new design - Login page | 2) 30% | WIP
24 | 2020-12-24 | Hayaai, Yearly Report - Hayaai | 1) Hayaai - mobile new models images edited , 2) Hayaai-Yearly report creating | 1)100% 2) 50% | WIP
25 | 2020-12-25 |  | Holiday
26 | 2020-12-26 |  | Week Off
27 | 2020-12-27
28 | 2020-12-28 | Hayaai, Yearly Report - Hayaai | 1) B2B - new layout started 2) Hayaai-Yearly report creating | 1)20% 2) 70% | WIP
29 | 2020-12-29 | Hayaai, Yearly Report - Hayaai | 1) Hayaai - B2B new layout for login and dashboard designed , 2) Hayaai-Yearly report | 1)40% 2) 100% | WIP
30 | 2020-12-30 | Hayaai | 1) Hayaai - B2B new layout for login and dashboard designed, 2) Design template created | 1)50% | WIP
31 | 2020-12-31 | Hayaai | Hayaai - B2B new layout | 70% | WIP
Status
WIP
Pending
Completed
Hold

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-01 |  | Holiday
2 | 2021-01-02 |  | Week Off
3 | 2021-01-03
4 | 2021-01-04 | Hayaai | Hayaai - B2B new layout |  | WIP
5 | 2021-01-05 | Muji Store | Fixing Alignment issues | 40% | WIP
6 | 2021-01-06 | Muji Store | Fixing Alignment issues | 100% | Completed
7 | 2021-01-07 | Muji Store | User Manual creating | 50% | WIP
8 | 2021-01-08 | Muji Store | User Manual creating | 80% | WIP
9 | 2021-01-09 |  | Week Off
10 | 2021-01-10
11 | 2021-01-11 | Muji Store | User Manual creating | 100% | Completed
12 | 2021-01-12 | SONIA | Creating User manual | 20% | WIP
13 | 2021-01-13 | SONIA | Creating User manual, MS access Document | 40% | WIP
14 | 2021-01-14 |  | Holiday
15 | 2021-01-15
16 | 2021-01-16 |  | Week Off
17 | 2021-01-17
18 | 2021-01-18 | SONIA | Sonia - MS access Document creation | 80% | WIP
19 | 2021-01-19 | SONIA | Sonia - 1 ) MS access Document , 2) User manual | 1) 100% 2) 50% | WIP
20 | 2021-01-20 | SONIA | 1) Sonia - User manual ,2) Logo designed | 1)65% 2)100% | WIP
21 | 2021-01-21 | SONIA | Sonia - User manual | 80% | WIP
22 | 2021-01-22 | SONIA | Sonia - User manual | 100% | Completed
23 | 2021-01-23 |  | Week Off
24 | 2021-01-24
25 | 2021-01-25 | SONIA | Sonia - User manual - Modifications | 100% | Completed
26 | 2021-01-26 |  | Holiday
27 | 2021-01-27 | QMVAR-2.0 | QMVAR - ChangePassword Screen | 40% | WIP
28 | 2021-01-28 |  | Holiday
29 | 2021-01-29 | QMVAR-2.0 | QMVAR - ChangePassword Screen | 100% | Completed
30 | 2021-01-30 |  | Week Off
31 | 2021-01-31
Status
WIP
Pending
Completed
Hold

## FEB-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-02-01 | GSS , Qmvar-2.0 | GSS Website Backup, Qmvar - overall alignments checked | 100% | Completed
2 | 2021-02-02 | Hayaai, Qmvar-2.0 | Hayaai Website Backup, Qmvar -Changes Requested completed | 100% | Completed
3 | 2021-02-03 | Sonia | Sonia Issues traker | 40% | WIP
4 | 2021-02-04 | Sonia | Sonia Issues traker | 100% | Completed
5 | 2021-02-05 | Hayyai - B2B | New Layout - Login screen and Main screen | 100% | Completed
6 | 2021-02-06 |  | Week Off
7 | 2021-02-07
8 | 2021-02-08 | Hayyai - B2B | New Layout - Registration - Add New Product screen | 100% | Completed
9 | 2021-02-09 | Hayyai - B2B , nMVAR | 1) New Layout - Registration - View Registration screen 2) nMVAR - UAT issues tracker created | 2) 100% | Completed
10 | 2021-02-10 | Hayyai - B2B | New Layout - Token system design and flow | 40% | WIP
11 | 2021-02-11 | Hayyai - B2B | New Layout - Registration - View Registration screen | 100% | Completed
12 | 2021-02-12 | Hayyai - B2B | New Layout -Registration - Search Registration Screen | 50% | WIP
13 | 2021-02-13 |  | Week Off
14 | 2021-02-14
15 | 2021-02-15 | Hayyai - B2B | New Layout -Registration - Search Registration Screen | 100% | Completed
16 | 2021-02-16 | Hayyai - B2B | New Layout -Registration - View and Search Registration Screen modified full design | 100% | Completed
17 | 2021-02-17 | Hayyai - B2B | New Layout -Service Job Management - Acknowledgement & Engineer Assign, create Job - 2 screens designed | 70% | WIP
18 | 2021-02-18 | Hayyai - B2B | New Layout -Service Job Management - Acknowledgement & Engineer Assign, create Job - 2 screens Modification | 100% | Completed
19 | 2021-02-19 | Hayyai - B2B | Modification in Registration layout | 100% | Completed
20 | 2021-02-20 |  | Week Off
21 | 2021-02-21
22 | 2021-02-22 | Hayyai - B2B | Service Job Management - Serach Job screen new layout | 80% | WIP
23 | 2021-02-23 | Hayyai - B2B | Dashboard - Pending calls screen | 100% | Completed
24 | 2021-02-24 | Hayyai - B2B | Dashboard - Main screen designed and View details screen | 100% | Completed
25 | 2021-02-25 | Hayyai - B2B | Service Job Management - Serach Job screen new layout | 100% | Completed
26 | 2021-02-26 | Hayyai - B2B | Parts Infromation Screen | 70% | WIP
27 | 2021-02-27 |  | Week Off
28 | 2021-02-28
Status
WIP
Pending
Completed
Hold

## MAR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-03-01 | Hayaai B2B | Parts Information pending | 80% | WIP
2 | 2021-03-02 | Hayaai B2B | B2B new layout Document and Design Modifications | 20% | WIP
3 | 2021-03-03 | Hayaai B2B | Service Job management Screen modification | 100% | Completed
4 | 2021-03-04 | Hayaai B2B | Warranty Extention - View & download screen | 100% | Completed
5 | 2021-03-05 | Hayaai B2B | Warranty Extention - EW invoice Details, Create new Job screen | 100% | Completed
6 | 2021-03-06 |  | Week Off
7 | 2021-03-07
8 | 2021-03-08 | Muji Store | Japanese version fully tested | 100% | Completed
9 | 2021-03-09 | Muji Store,Sonia,Nmvar | Japanese version fully tested, Sonia and Nmvar - UAT issues doc modified | 100% | Completed
10 | 2021-03-10 | nMVAR,Hayaai B2B | nMVAR UAT issues Doc translated, Warranty Extention | 100% | Completed
11 | 2021-03-11 | Hayaai B2B | Parts Information screen | 85% | Completed
12 | 2021-03-12 | Hayaai B2B | Existing Screen - Jobs Screen designed fully | 70% | Completed
13 | 2021-03-13 |  | Week Off
14 | 2021-03-14
15 | 2021-03-15 | Hayaai B2B | Existing Screen - Jobs, Dashboard Screen designed fully | 100% | Completed
16 | 2021-03-16 | Hayaai-RPA | Creating Hayaai Rpa Proposal for Rlogic | 70% | WIP
17 | 2021-03-17 | Hayaai-RPA , B2B | Creating Hayaai Rpa Proposal for Rlogic, Modifiaction screens | 85% | WIP
18 | 2021-03-18 | Hayaai-RPA | Creating Hayaai Rpa Proposal for Rlogic | 100% | Completed
19 | 2021-03-19 | Hayaai-B2B | Modifiaction screens | 100% | Completed
20 | 2021-03-20 |  | Week Off
21 | 2021-03-21
22 | 2021-03-22 | Hayaai | Created Hayaai LetterHead | 100% | Completed
23 | 2021-03-23 | Hayaai -B2B | Modification screen | 90% | WIP
24 | 2021-03-24 | Qmvar-2.0 | design issues checked | 90% | WIP
25 | 2021-03-25 | nMVAR | nMVAR UAT issues Doc translated | 100% | Completed
26 | 2021-03-26 | Qmvar-2.0 | Dropdown menu design issues checked | 90% | WIP
27 | 2021-03-27 |  | Week Off
28 | 2021-03-28
29 | 2021-03-29 | Hayaai | Invoice Design created | 80% | WIP
30 | 2021-03-30 | Hayaai | Invoice Design created, Job sheet | 100% | Completed
31 | 2021-03-31 | Hayaai | Jobsheet , Delivery Report created | 100% | Completed
Status
WIP
Pending
Completed
Hold

## APR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-04-01 | Hayaai | Advance Payment Receipt created | 100% | Completed
2 | 2021-04-02 |  | Holiday
3 | 2021-04-03 |  | Week Off
4 | 2021-04-04
5 | 2021-04-05 | Hayaai | Report designs all created in Jasper tool | 100% | Completed
6 | 2021-04-06 |  | Holiday
7 | 2021-04-07 | Hayaai | Advance Payment information and Billing Information screen design | 70% | WIP
8 | 2021-04-08 | Hayaai,nMVAR,SONIA | nMVAR,SONIA - UAT issues listed Hayaai- B2B- design | 80% | WIP
9 | 2021-04-09 | Hayaai | Advance Payment information and Billing Information screen design Modifications | 100% | Completed
10 | 2021-04-10 |  | Week Off
11 | 2021-04-11
12 | 2021-04-12 | Hayaai | Advance Payment information modification | 100% | Completed
13 | 2021-04-13 |  | Holiday
14 | 2021-04-14
15 | 2021-04-15 | Mujistore | Muji store checked
16 | 2021-04-16 | Hayaai | Advance payment Receipt design Created in Jasper Tool | 100% | Completed
17 | 2021-04-17 |  | Week Off
18 | 2021-04-18
19 | 2021-04-19 | Mujistore | Translation and design issues fixed | 70% | WIP
20 | 2021-04-20 | Mujistore | Translation and design issues fixed | 80% | WIP
21 | 2021-04-21 | Mujistore | Translation validation messages | 100% | Completed
22 | 2021-04-22 | Mujistore | Translation and design issues fixed | 100% | Completed
23 | 2021-04-23 | Mujistore | Translation and design issues fixed | 100% | Completed
24 | 2021-04-24 |  | Week Off
25 | 2021-04-25
26 | 2021-04-26 | Mujistore,Hayaai | Full test, Reports modified | 100% | Completed
27 | 2021-04-27 | Hayaai | QC new screen designed | 100% | Completed
28 | 2021-04-28 | Hayaai | Sales Invoice Screen designed | 80% | WIP
29 | 2021-04-29 | Hayaai | Sales Invoice Screen Modifications | 90% | Completed
30 | 2021-04-30 | Hayaai | Sales Invoice Screen Modifications | 100% | Completed
Status
WIP
Pending
Completed
Hold

## MAY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-05-01 |  | Week Off
2 | 2021-05-02
3 | 2021-05-03 | Mujistore Hayaai | Full Site checked. Sales Requirement completed | 100% | Completed
4 | 2021-05-04 | Mujistore | User Manual creating | 70% | WIP
5 | 2021-05-05 | Hayaai | Token System requirement discuss and started design | 50% | WIP
6 | 2021-05-06 | Hayaai | Token System requirement discuss and started design | 65% | WIP
7 | 2021-05-07 | Hayaai | Token System design | 85% | WIP
8 | 2021-05-08 |  | Week Off
9 | 2021-05-09
10 | 2021-05-10 | Hayaai | Token System design | 95% | WIP
11 | 2021-05-11 | Hayaai | Token System design | 100% | Completed
12 | 2021-05-12 | Hayaai | Token System design modifications | 100% | Completed
13 | 2021-05-13 | Hayaai | Token System design modifications | 100% | Completed
14 | 2021-05-14 | Hayaai | Token System design modifications | 100% | Completed
15 | 2021-05-15 |  | Week Off
16 | 2021-05-16 |  |  |  | Completed
17 | 2021-05-17 | Hayaai | Token System design | 100% | Completed
18 | 2021-05-18 | Hayaai | Requirement meeting (Sick Leave)
19 | 2021-05-19 |  | Sick Leave
20 | 2021-05-20
21 | 2021-05-21
22 | 2021-05-22 |  | Week Off
23 | 2021-05-23
24 | 2021-05-24 | Hayaai | Token System- requirement doc , TV display deign | 60% | WIP
25 | 2021-05-25 | Hayaai | Token System requirement doc | 100% | Completed
26 | 2021-05-26 | QMVAR2.0 | Issues fixes | 60% | WIP
27 | 2021-05-27 | QMVAR2.0 | Issues fixes | 80% | WIP
28 | 2021-05-28 | Hayaai | Token System requirement doc discussion, Modification | 100% | Completed
29 | 2021-05-29 |  | Week Off
30 | 2021-05-30
31 | 2021-05-31 | Mujistore | Translated newly highlighted issues | 100% | Completed
Status
WIP
Pending
Completed
Hold

## JUNE-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-06-01 | Qmvar | Alignmanet issues fix | 60% | WIP
2 | 2021-06-02 | Qmvar | Alignmanet issues fix | 80% | WIP
3 | 2021-06-03 | RPA | UiPath install and learn to run task , REVER- PPT Created | 10% | WIP
4 | 2021-06-04 | REVER | PPT Created | 100% | Completed
5 | 2021-06-05 |  | Week Off
6 | 2021-06-06
7 | 2021-06-07 | REVER | PPT Modified | 100% | Completed
8 | 2021-06-08 | REVER,QMVAR | 1)PPT Modified 2)qmvar issues fixed | 80% | WIP
9 | 2021-06-09 | REVER | PPT Modified | 100% | Completed
10 | 2021-06-10 | Hayaai | Inventory Sceens design | 30% | WIP
11 | 2021-06-11 | Hayaai | Inventory Sceens design | 50% | WIP
12 | 2021-06-12 |  | Week Off
13 | 2021-06-13
14 | 2021-06-14 | Hayaai | Inventory Sceens design , Worked for Web application Template | 50% | WIP
15 | 2021-06-15 | Hayaai | Inventory Sceens design | 70% | WIP
16 | 2021-06-16 | Hayaai | Inventory Sceens design | 75% | WIP
17 | 2021-06-17 | Hayaai | Inventory Sceens design | 80% | WIP
18 | 2021-06-18 | Mujistore | ChangeRequest | 30% | WIP
19 | 2021-06-19 |  | Week Off
20 | 2021-06-20
21 | 2021-06-21 | Hayaai | Inventory Sceens design | 80% | WIP
22 | 2021-06-22 | REVER_MJA | Proposal Document Created | 45% | WIP
23 | 2021-06-23 | REVER_MJA | Proposal Document Created | 65% | WIP
24 | 2021-06-24 | REVER_MJA | Proposal Document Created | 80% | WIP
25 | 2021-06-25 | REVER_MJA | Proposal Document Created | 100% | Completed
26 | 2021-06-26 |  | Week Off
27 | 2021-06-27
28 | 2021-06-28 |  | Sick Leave
29 | 2021-06-29 | Hayaai | Inventory Sceens 2nd Flow designed | 90% | WIP
30 | 2021-06-30 | Hayaai | Inventory Sceens modifications done | 100% | Completed
Status
WIP
Pending
Completed
Hold

## JULY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-07-01 | HAYAAI | Invenetory - screens designed and alignment fixed | 100% | Completed
2 | 2021-07-02 | HAYAAI | 1) Invenetory - screens designed and alignment fixed 2) Hayaai website - India address changed for both Japanese and english | 100% | Completed
3 | 2021-07-03 |  | Week Off
4 | 2021-07-04
5 | 2021-07-05 | HAYAAI | Invenetory - screens designed and Modification | 100% | Completed
6 | 2021-07-06 | HAYAAI | Invenetory - screens designed and Modification | 100% | Completed
7 | 2021-07-07 | REVER | Proposal document verified,Muji verified | 100% | Completed
8 | 2021-07-08 | MUJISTORE | Compared with original and latest. Created Doc | 50% | WIP
9 | 2021-07-09 | MUJISTORE | Compared with original and latest. Created Doc | 85% | WIP
10 | 2021-07-10 |  | Week Off
11 | 2021-07-11
12 | 2021-07-12 | MUJISTORE | Created Doc | 100% | Completed
13 | 2021-07-13 | MJA | Layout design prepared | 50% | WIP
14 | 2021-07-14 | MJA | Layout design prepared , wireframe designed | 75% | WIP
15 | 2021-07-15 | MJA | wireframe designed | 85% | WIP
16 | 2021-07-16 | MJA | wireframe designed for Employer screens | 100% | Completed
17 | 2021-07-17 |  | Week Off
18 | 2021-07-18
19 | 2021-07-19 | MJA | wireframe designed- Features For employers - Login, Register, Dashboard | 100% | Completed
20 | 2021-07-20 | MJA | wireframe designed- Features For employers - Login, Register, Dashboard - modifications done | 100% | Completed
21 | 2021-07-21 | MJA | WBS created for weekly report | 100% | Completed
22 | 2021-07-22 | MJA | MJA tracker created | 100% | Completed
23 | 2021-07-23 | MJA | Proposal document created | 50% | WIP
24 | 2021-07-24 |  | Week Off
25 | 2021-07-25
26 | 2021-07-26 | MJA | PPT created for Report tracking | 70% | WIP
27 | 2021-07-27 | MJA | PPT created for Report tracking, Proposal create | 100% | Completed
28 | 2021-07-28 | Mujistore | Deployment plan created Pennacement-KT Attended | 100% | Completed
29 | 2021-07-29 | MJA | PPT modified Pennacement-KT Attended | 100% | Completed
30 | 2021-07-30 | MJA | Report created Pennacement-KT Attended | 100% | Completed
31 | 2021-07-31 |  | Week Off
Status
WIP
Pending
Completed
Hold

## AUG-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-08-01 |  | Week Off
2 | 2021-08-02 | MJA | Reports modified | 100% | Completed
3 | 2021-08-03 | Mujistore | Design issues checking and fix | 100% | Completed
4 | 2021-08-04 | Mujistore | Full test - Design and Japanese version | 100% | Completed
5 | 2021-08-05 | Mujistore | Full test - Design and Japanese version | 100% | Completed
6 | 2021-08-06 | Mujistore | Production Activites | 90% | WIP
7 | 2021-08-07 |  | Week Off
8 | 2021-08-08
9 | 2021-08-09 | MJA | Tracker updated. | 50% | WIP
10 | 2021-08-10 | MJA | Sample layout designed | 40% | WIP
11 | 2021-08-11 | MJA | Resume Search screen - UI design Completed | 90% | WIP
12 | 2021-08-12 | MUJISTORE | Production LIVE | 100% | Completed
13 | 2021-08-13 | MJA | Dashboard UI design | 100% | Completed
14 | 2021-08-14 |  | Week Off
15 | 2021-08-15
16 | 2021-08-16 | MUJISTORE | Mobile and Ipad view issues fixing | 70% | WIP
17 | 2021-08-17 | MUJISTORE | Mobile and Ipad view issues fixing | 95% | WIP
18 | 2021-08-18 | MUJISTORE,MJA | Mobile and Ipad view issues fixing MJA - Ui design Job manager screen | 100% | Completed
19 | 2021-08-19 | MUJISTORE | Muji- tested in all browsers | 100% | Completed
20 | 2021-08-20 | MUJISTORE, MJA | Muji- tested in Firefox MJA- UI design | 100% | Completed
21 | 2021-08-21 |  | Week Off
22 | 2021-08-22
23 | 2021-08-23 |  | Sick Leave
24 | 2021-08-24 | MUJISTORE, MJA | Muji- Tested in Firefox MJA- UI design | 100% | Completed
25 | 2021-08-25 | MJA | MJA Tracker completed(Phase-1) | 100% | Completed
26 | 2021-08-26 | MJA | MJA Estimation completed | 100% | Completed
27 | 2021-08-27 | MJA | Requirement Docment created (Sample) | 100% | Completed
28 | 2021-08-28 |  | Week Off
29 | 2021-08-29
30 | 2021-08-30 | MJA, Penna | Mja - Screening questionare Design | 100% | Completed
31 | 2021-08-31 | MJA, Penna | Penna Documents collected Mja - Screening questionare Design | 100% | Completed
Status
WIP
Pending
Completed
Hold

## SEP-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-09-01 | MJA, PENNA | Resume search agent, saved resume - UI Design | 100% | Completed
2 | 2021-09-02 | MJA | Job Manager - Screening Questionnaire UI Design | 100% | Completed
3 | 2021-09-03 | Muji,MJA | Muji- production deployment MJA - DB values doc created | 100% | Completed
4 | 2021-09-04 |  | Week Off
5 | 2021-09-05
6 | 2021-09-06 | Muji | Download original videos for all formats tested in Firefox | 100% | Completed
7 | 2021-09-07 | Penna | Report Created Followups | 100% | Completed
8 | 2021-09-08 | Penna | Follow ups for server access | 100% | Completed
9 | 2021-09-09 | REVER,Penna | REVER - CTDI Discussion Penna - Followups | 100% | Completed
10 | 2021-09-10 |  | HOLIDAY
11 | 2021-09-11 |  | Week Off
12 | 2021-09-12
13 | 2021-09-13 | Penna | Penna- Issue Tracker created | 100% | Completed
14 | 2021-09-14 | MJA | JOBSeeker - Signin Screen UI design | 30% | WIP
15 | 2021-09-15 | MJA | JOBSeeker - Signup Screen UI design | 40% | WIP
16 | 2021-09-16 | MJA | JOBSeeker - Signup Screen UI design | 100% | Completed
17 | 2021-09-17 | MJA | JOBSeeker - Signin Screen UI design | 100% | Completed
18 | 2021-09-18 |  | Week Off
19 | 2021-09-19
20 | 2021-09-20 | MJA, Penna | Mja Tested Jobseeker ui Design Penna - Proposal prepare | 40% | WIP
21 | 2021-09-21 | Kaisokku | Logo Create , PPT | 30% | WIP
22 | 2021-09-22 | Kaisokku | Logo Created Wieframe | 100% 40% | Completed
23 | 2021-09-23 | Kaisokku | Wireframe | 85% | WIP
24 | 2021-09-24 | Kaisokku | Wireframe | 100% | Completed
25 | 2021-09-25 |  | Week Off
26 | 2021-09-26
27 | 2021-09-27 | Kaisokku,Penna | Kaisokku - Proposal PPT Penna - Proposal prepare | 60% | WIP
28 | 2021-09-28 | Kaisokku,Penna | Kaisokku - Proposal PPT Penna - Proposal prepare | 100% | Completed
29 | 2021-09-29 | Kaisokku | UI design | 20% | WIP
30 | 2021-09-30 | Penna | MOM - new requirement. Muji discussion | 100% | Completed
Status
WIP
Pending
Completed
Hold

## OCT-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-10-01 | Kaisokku | UI design | 50% | WIP
2 | 2021-10-02 |  | Week Off
3 | 2021-10-03
4 | 2021-10-04 | Kaisokku | UI design | 100% | Completed
5 | 2021-10-05 |  | Planned Leave
6 | 2021-10-06 | kaisokku | UI design- changes | 100% | Completed
7 | 2021-10-07 | Kaisokku,Muji | 1)Kaisokku-images searched for RPA 2)Design Document | 100% | Completed
8 | 2021-10-08 | Kaisokku | Kaisokku-RPA doc created.Coordinate meeting | 100% | Completed
9 | 2021-10-09 |  | Week Off
10 | 2021-10-10
11 | 2021-10-11 | MJA | Super Admin layout screen | 60% | WIP
12 | 2021-10-12 | Penna,Kaisokku | 1)Penna Proposal Modified 2) Kaisokku Images serached | 100% | Completed
13 | 2021-10-13 | Penna | Middleware Demo html screen created | 100% | Completed
14 | 2021-10-14 |  | Holiday
15 | 2021-10-15
16 | 2021-10-16 |  | Week Off
17 | 2021-10-17
18 | 2021-10-18 | Muji | Design Document verified | 60% | WIP
19 | 2021-10-19 | Penna | Middleware Demo -Ui design created , User Manula created for demo | 100% | Completed
20 | 2021-10-20 | Penna | Clinker Test Certificate - View changes | 100% | Completed
21 | 2021-10-21 | Penna,Kaisokku | 1)Penna FollowUps , Issue Tracker updated 2) Kaisokku Front End | 100% | Completed
22 | 2021-10-22 | Penna,MJA | Penna - Issue Tracker Updated, CronJob and Error Log Monitoring tracker created MJA - Proposal created for Android and IOS version | 100% | Completed
23 | 2021-10-23 |  | Week Off
24 | 2021-10-24
25 | 2021-10-25 | Penna | Penna - Issue Tracker Updated, CronJob and Error Log Monitoring tracker created for Invoice | 100% | Completed
26 | 2021-10-26 | Kaisokku | Signin Ui design | 100% | Completed
27 | 2021-10-27 | Kaisokku | Signin UP design | 100% | Completed
28 | 2021-10-28 | Kaisokku,Penna | Contact Ui design, Penna followup | 100% | Completed
29 | 2021-10-29 | Kaisokku | Home page issues checked. MJA , Penna followup | 100% | Completed
30 | 2021-10-30 |  | Week Off
31 | 2021-10-31
Status
WIP
Pending
Completed
Hold

## NOV-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-11-01 | Kaisokku | 1) Home page design issues 2) Diwali wishes Design created | 70% | WIP
2 | 2021-11-02 | Kaisokku | Home page design issues | 100% | Completed
3 | 2021-11-03 | Penna | Soruce Code Migration Tracker Created | 50% | WIP
4 | 2021-11-04 |  | Diwali Holiday
5 | 2021-11-05 |  | Planned Leave
6 | 2021-11-06 |  | Week Off
7 | 2021-11-07
8 | 2021-11-08 | Penna | Soruce Code Migration Tracker Updates, Penna Followups | 70% | WIP
9 | 2021-11-09 | Kaisokku, Penna | Kaisokku- Design issue, Penna- Followups | 90% | WIP
10 | 2021-11-10 | Penna | FollowUps, Migration Tracker | 50% | WIP
11 | 2021-11-11 | Kaisokku,Penna | Kaisokku- Design issue, Penna- Followups | 70% | WIP
12 | 2021-11-12 | Penna | FollowUps, Migration Tracker | 90% | WIP
13 | 2021-11-13 |  | Week Off
14 | 2021-11-14
15 | 2021-11-15 | Penna | Migration Tracker Timeline filled | 100% | Completed
16 | 2021-11-16 | TechMahindra | List of Projects PPT created with Bricks | 100% | Completed
17 | 2021-11-17 | Penna | Followups, Coordinations | 90% | WIP
18 | 2021-11-18 | Penna,Kaisokku | Followups, Kaisokku- listed in Doc- Logo Fontsize | 100% | Completed
19 | 2021-11-19 | TechMahindra | Requirement Gathering Document | 100% | Completed
20 | 2021-11-20 |  | Week Off
21 | 2021-11-21
22 | 2021-11-22 | Video system,Penna | Video Distribution System- Requirement Gathering Document. Penna- Coordinations | 80% | WIP
23 | 2021-11-23 | Video system,Penna | Video Distribution System- Requirement Gathering Document. Penna- Coordinations, Updated Invoice Doc | 100% | Completed
24 | 2021-11-24 |  | Planned Leave
25 | 2021-11-25 | Penna | Followups, Coordinations | 90% | WIP
26 | 2021-11-26 | MJA,Penna | Mja tracker with ETA for Admin and updated WBS tracker, Penna - Coordinate for Migration server | 100% | Completed
27 | 2021-11-27 |  | Week Off
28 | 2021-11-28
29 | 2021-11-29 | Penna | Followups, Coordinations | 100% | Completed
30 | 2021-11-30 | Penna | Followups, Coordinations | 100% | Completed
Status
WIP
Pending
Completed
Hold

## DEC-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-12-01 | Kyojin Challenger | Kyojin - Brochure created Challenger - Starshield - app timeline Penna - Followups | 90% | WIP
2 | 2021-12-02 | Penna Challenger | Challenger - Starshield - app timeline - Gantt chart Penna - Followups | 100% | Completed
3 | 2021-12-03 | Penna | Penna - Followups, MRP New Project Meeting | 100% | Completed
4 | 2021-12-04 |  | WeekOff
5 | 2021-12-05
6 | 2021-12-06 | Rever,Penna | Yearly Project report - Designed Penna - Followups for Migration, MRP,Middleware | 60% | WIP
7 | 2021-12-07 | Rever,Penna | Yearly Project report - Designed Penna - Followups for Migration, MRP,Middleware | 80% | WIP
8 | 2021-12-08 | GSS,Penna | Expiration- new project flow Document Penna - Followups for Migration, MRP,Middleware | 100% | Completed
9 | 2021-12-09 | App,Penna | Starshield - EW add screens ,Invoice designed in Jasper Penna - Followups for Migration, MRP,Middleware | 80% | WIP
10 | 2021-12-10 | App, Penna | Starshield - EW add screens Penna - Followups for Migration, MRP,Middleware | 90% | WIP
11 | 2021-12-11 |  | WeekOff
12 | 2021-12-12
13 | 2021-12-13 | App,Penna,GSS | Yearly Project report - Designed Starshield - EW add screens Penna - Followups for Migration, MRP,Middleware | 100% | Completed
14 | 2021-12-14 | Penna | MRP printing - Proposal Penna - Followups for Migration, MRP,Middleware | 50% | WIP
15 | 2021-12-15 | App , Penna | Starshield - EW add screens (Pay after registration) Penna Followup for Migration | 80% | WIP
16 | 2021-12-16 | App, Penna | Starshield - EW add screens (Quickpay, Pay after registration) Penna Followup for Migration | 90% | WIP
17 | 2021-12-17 | App , Penna | UI working on CR Penna Followup for Migration | 100% | Completed
18 | 2021-12-18 |  | WeekOff
19 | 2021-12-19
20 | 2021-12-20 | Penna,App | UI working on CR Penna Followup for Migration | 100% | Completed
21 | 2021-12-21 | Penna,App | UI working on CR Penna Followup for Migration | 100% | Completed
22 | 2021-12-22 | MJA, Penna | MJA - Moduels listing Penna Followup | 50% | WIP
23 | 2021-12-23 | GSS, Penna, App | GSS - Yearly Reort created in Excel Penna Followup B2B- UI working on CR | 80% | WIP
24 | 2021-12-24 | MJA, Penna, App | MJA - Moduels listing Penna Followup B2B- UI working on CR | 100% | Completed
25 | 2021-12-25 |  | WeekOff
26 | 2021-12-26
27 | 2021-12-27 | MJA, Penna | New Year Greetings designed Penna Followup, Migration Tracker MJA - Moduels listed, Assienged Task | 100% | Completed
28 | 2021-12-28 | MJA, Penna | Penna Followup, Migration Tracker MJA - Moduels listed, Assienged Task | 100% | Completed
29 | 2021-12-29 | MJA, Penna | Penna Followup, Migration Tracker MJA - Moduels listed, Assienged Task | 100% | Completed
30 | 2021-12-30 | MJA,Penna | Penna Followup, Migration Tracker MJA - Jobseeker- Profile UI | 50% | WIP
31 | 2021-12-31 | MJA,Penna , App | Penna Followup, Migration Tracker MJA - Jobseeker- Profile UI B2B- UI - CR Done | 70% | WIP
Status
WIP
Pending
Completed
Hold

## JAN-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-01-01 |  | WeekOff
2 | 2022-01-02
3 | 2022-01-03 | MJA, Penna | Penna Followup Mails sent, Migration Tracker MJA - Jobseeker- Profile UI | 60% | WIP
4 | 2022-01-04 | MJA, Penna,App | App Followups , Penna Followups MJA - Jobseeker- Profile UI | 75% | WIP
5 | 2022-01-05 | MJA, Penna | Penna Followups MJA - Jobseeker- Profile UI | 80% | WIP
6 | 2022-01-06 | MJA, Penna | Penna Followups MJA - Jobseeker- Profile UI | 90% | WIP
7 | 2022-01-07 | MJA, Penna | Penna Followups MJA - Jobseeker- Profile Completion UI | 100% | Completed
8 | 2022-01-08 |  | WeekOff
9 | 2022-01-09
10 | 2022-01-10 | MJA, Penna | Penna Migration report updated and Followups MJA - Jobseeker- Jobs UI Design | MJA - 40% | WIP
11 | 2022-01-11 | MJA, Penna | Penna Migration and Followups MJA - Jobseeker- Jobs UI Design | MJA - 40% | WIP
12 | 2022-01-12 | MJA, Penna | Penna Migration and Followups MJA - Jobseeker- Jobs UI Design | MJA - 40% | WIP
13 | 2022-01-13 | MJA, Penna | Penna Migration and Followups MJA - Jobseeker- Jobs UI Design | MJA - 40% | WIP
14 | 2022-01-14 |  | WeekOff
15 | 2022-01-15
16 | 2022-01-16
17 | 2022-01-17
18 | 2022-01-18 | Penna,MJA, Starshield | Penna Migration report updated and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design | Starshield - 20% | WIP
19 | 2022-01-19 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design | Starshield - 40% | WIP
20 | 2022-01-20 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design | Starshield - 70% | WIP
21 | 2022-01-21 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design | Starshield - 100% | Completed
22 | 2022-01-22 |  | WeekOff
23 | 2022-01-23
24 | 2022-01-24 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design - Modifications | Starshield - 70% | WIP
25 | 2022-01-25 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design - Modifications | Starshield - 80% | WIP
26 | 2022-01-26 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design - Modifications | Starshield - 100% | Completed
27 | 2022-01-27 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2C - Mobile Ver - UI Design | Starshield - 20% | WIP
28 | 2022-01-28 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2C - Mobile Ver - UI Design | Starshield - 40% | WIP
29 | 2022-01-29 |  | WeekOff
30 | 2022-01-30
31 | 2022-01-31 | Penna,MJA, Starshield | Penna Migration report updated and Followups MJA - Followups Starshield B2B- Mobile Ver - UI Design - Modifications | Starshield - 100% | Completed
Status
WIP
Pending
Completed
Hold

## FEB-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-02-01 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Jobseeker Sign In UI Design Starshield B2C - Mobile Ver - UI Design Starshield B2B - SalesAgent/Partner - Flow Document | Starshield - 60% | WIP
2 | 2022-02-02 | Penna,MJA, Starshield | Penna Migration report updated and Followups MJA - Followups Starshield B2C - Mobile Ver - UI Design Starshield B2B - SalesAgent/Partner - Flow Document | Starshield Document - 100% | Completed
3 | 2022-02-03 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups,Employer Sign In UI Design Starshield B2C - Mobile Ver - UI Design | Starshield - 100% | Completed
4 | 2022-02-04 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2C - Mobile Ver - UI Design - Modification,CR | Starshield - 100% | Completed
5 | 2022-02-05 |  | WeekOff
6 | 2022-02-06
7 | 2022-02-07 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2C - Mobile Ver - UI Design- Sent to Starshield team for confirmation | Starshield - 100% | Completed
8 | 2022-02-08 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B -Tab ver - UI Design | Starshield - 40% | WIP
9 | 2022-02-09 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B -Tab ver - UI Design | Starshield - 60% | WIP
10 | 2022-02-10 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B -Tab ver - UI Design | Starshield - 75% | WIP
11 | 2022-02-11 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2C - Changes and Sent files to Arangala team | 100% | Completed
12 | 2022-02-12 |  | WeekOff
13 | 2022-02-13
14 | 2022-02-14 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Email Templates modification | Starshield - 60% | WIP
15 | 2022-02-15 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Email Templates modification | Starshield - 100% | Completed
16 | 2022-02-16 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield B2B -Tab ver - UI Design | Starshield - 80% | WIP
17 | 2022-02-17 | Penna,MJA | Penna Migration and Followups MJA - Followups, Report MJA - Jobs Search | 50% | WIP
18 | 2022-02-18 | Penna,MJA | Penna Migration and Followups MJA - Followups, Report MJA - Jobs Search | 70% | WIP
19 | 2022-02-19 |  | WeekOff
20 | 2022-02-20
21 | 2022-02-21 | Penna,MJA,Rever | Penna Migration and Followups MJA - Followups, Report REVER-Certificate Design | 70% | WIP
22 | 2022-02-22 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Report Starshield - Email Templates updated content, App UI modifications | 70% | WIP
23 | 2022-02-23 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Report Starshield - Email Templates updated content, App UI modifications | 70% | WIP
24 | 2022-02-24 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Support | 80% | WIP
25 | 2022-02-25 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design Starshield - Email Templates updated content, App UI Screens updated | 100% | Completed
26 | 2022-02-26 |  | WeekOff
27 | 2022-02-27
28 | 2022-02-28 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Admin Masters Starshield - Email Templates updated content, App UI Screens updated | 100% | Completed
Status
WIP
Pending
Completed
Hold

## MAR-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-03-01 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Admin Masters Starshield - Email Templates updated content, App UI Screens updated | 100% | Completed
2 | 2022-03-02 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Admin Masters Starshield - App Docs, Icons, assets all uploaded in Git | 100% | Completed
3 | 2022-03-03 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Admin Job postings Starshield - Followups | 70% | WIP
4 | 2022-03-04 |  | Planned Leave
5 | 2022-03-05 |  | Week Off
6 | 2022-03-06
7 | 2022-03-07 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Admin Job postings Starshield - Followups | 100% | Completed
8 | 2022-03-08 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Job Search Starshield - Followups | MJA- 50% | WIP
9 | 2022-03-09 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Job Search Starshield - Followups | 100% | Completed
10 | 2022-03-10 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Followups | 100% | Completed
11 | 2022-03-11 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Followups | 100% | Completed
12 | 2022-03-12 |  | Week Off
13 | 2022-03-13
14 | 2022-03-14 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Apply Job Starshield - Followups | 100% | Completed
15 | 2022-03-15 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Job Search Starshield - Followups and email templates content modified | 100% | Completed
16 | 2022-03-16 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Followups | 100% | Completed
17 | 2022-03-17 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and Created Report Starshield - Followups | 100% | Completed
18 | 2022-03-18 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Job Alert Starshield - Followups | MJA - 50% | WIP
19 | 2022-03-19 |  | Week Off
20 | 2022-03-20
21 | 2022-03-21 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Job Alert Starshield - Followups | MJA - 80% | WIP
22 | 2022-03-22 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups and UI design for Job Alert Starshield - Followups | MJA - 100% | WIP
23 | 2022-03-23 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Followups | 100% | Completed
24 | 2022-03-24 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Followups | 100% | Completed | 2nd Half - Leave
25 | 2022-03-25 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups Starshield - Followups | 100% | Completed
26 | 2022-03-26 |  | Week Off
27 | 2022-03-27
28 | 2022-03-28 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Tracker updated Starshield - Followups | 100% | Completed
29 | 2022-03-29 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Tracker updated Starshield - Followups | 100% | Completed
30 | 2022-03-30 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Tracker updated Starshield - Followups | 100% | Completed
31 | 2022-03-31 | Penna,MJA, Starshield | Penna Migration and Followups MJA - Followups, Tracker updated Starshield - Followups, UI modifications | 100% | Completed
Status
WIP
Pending
Completed
Hold