## JAN-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-01-03 | RPA RLOGIC | 1. Working on beautification tasks for the P&L summary and GL summary and it is work in progress | 60% | WIP
|  |  | 2. For P&L, Downloaded DRS and Warranty file and merged the DRS,Warranty, InvoiceUpdate and Saw file to create a Call Wise Data for the MLR done | 100% | Completed
2 | 2022-01-04 | RPA RLOGIC | 1. Creating Borders and applying styles to the Summary of the General Ledger and it has been completed, implemented and tested | 100% | Completed
|  |  | 2. Creating Borders and applying styles to the Summary of the Profit and Loss report and it has been completed, implemented and tested | 100% | Completed
3 | 2022-01-05 | RPA RLOGIC | 1. Integration of merging tasks of DRS, Invoice update and Saw files with Warranty are work in progress and it has to be done before creating the callwise data for the P&L(already done) | 90% | WIP
4 | 2022-01-06 | RPA RLOGIC | 1. Created a sample P&L report with new logic for the MLR and BLR without expenses | 100% | Completed
|  |  | 2. P&L report of the HYD is work in progress | 50% | WIP
5 | 2022-01-07 | RPA RLOGIC | 1. P&L reports has been generated for all three centers | 100% | Completed
6 | 2022-01-10 | RPA RLOGIC | 1. Expenses data has been added to the P&L report as separate sheet like callwise data sheet | 100% | Completed
|  |  | 2. Deleted the backup files of the Rlogic daily reports from Sep2021 to Dec2021 | 100% | Completed
|  |  | 3. Deleted the log files from Sep2021 to Dec2021 | 100% | Completed
7 | 2022-01-11 | RPA RLOGIC | 1. Generated the Accounting Statements for the three centers and shared to Rahaman san to verify | 100% | Completed
|  | RPA GSS | 2. Uploading the pdf files task is work in progress for ESA | 10% | WIP
8 | 2022-01-12 | RPA RLOGIC | 1. Correction received for the Accounting Statements for the three centers and completed the correction and shared to Rahaman san to verify | 100% | Completed
|  | RPA GSS | 2. Uploading the pdf files task is work in progress for ESA and it is around 50% has been completed | 50% | WIP
9 | 2022-01-13 | RPA GSS | 1. Uploading PDF files task has been completed, tested and it is uploading smoothly | 100% | Completed
10 | 2022-01-17 | RPA RLOGIC | 1. Removing rows where minus sign at Other Column in the warranty monthly files has been done during append to the previous month file | 100% | Completed
|  |  | 2. ESA task has been tested success at Mohan san's system and confirmed for the ESA today | 100% | Completed
11 | 2022-01-19 | RPA RLOGIC | 1. Generated the Accounting Statements for the three centers and the same had been triggered success | 100% | Completed
|  |  | 2. Generated the P&L reports of the Dec21 for the three centers and shared to Rahman san for the verification | 100% | Completed
12 | 2022-01-21 | RPA RLOGIC | 1. Enhancing the knowledge of Openpyxl and Pandas frameworks towards the RPA automation to handle excel manipulation and involved in the calculation activities | 100% | Completed
|  |  | 2. Also, we are working date filtering with new logic to obtain previous month data if vendor ledger is having three months data and it is work in progress for the GL | 30% | WIP
13 | 2022-01-24 | RPA RLOGIC | 1. P&L has been triggered for the all 3 centers and it is done today | 100% | Completed
|  |  | 2. RPA Management template has been triggered for the all 3 centers and it is done today | 100% | Completed
|  |  | 3. Getting Last month closing balance and taking as current month opening balance, this steps has been implemented at GL and etc | 100% | Completed
|  |  | 4. Some more filtering to be done at Vendor Ledger file for GL to implement is work in progress | 20% | WIP
14 | 2022-01-25 | RPA RLOGIC | 1. A few fine tuning works are work in progress for P&L and GL | 30% | WIP
15 | 2022-01-25 | RPA GSS | 2. New Change request has been received from Mohan san to do customization at GSPN tasks and it is work in progress | 5% | WIP
16 | 2022-01-27 | RPA GSS | We have received the change request for the customization parts at GSPN tasks as follows on 25.01.2022 from Mohan san:
1. We have to fetch the data and upload from the day was working till previous day if the previous day is holiday.
2. if holidays are more than 3 days or more, then we have to split days and download and upload with date splitting
3. if record counts is more than 5000, then again the divide the date or split the date and do the download and upload
|  |  | Note: point 1. has been completed, whereas the testing has been done with Warranty daily task, and other tasks are pending. | 20% | WIP
17 | 2022-01-28 | RPA GSS | 1. Implementation of Public holidays has been done at Warranty task and it is tested and it is running smoothly | 100% | Completed
|  |  | 2. Implementation of Public holidays has been done at ACTIVITY_DAILY task(Token system) and the testing is work in progress | 70% | WIP
18 | 2022-01-31 | RPA GSS | 1. Implementation of Public holidays at GSPN task is work in progress | 20% | WIP

## FEB-22
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-02-01 | RPA GSS | 1. Correction received from the DRS-Monthly tasks due to 5000 records issue, and it has been fixed, tested in all SSCs and it is running smoothly from download to upload | 100% | Completed
2 |  |  | 2. Implementation of public holidays is work in progress | 30% | WIP