## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | Soniya | MrMAX_Mtr, MRMax Wrn | 100% | Completed | Locally Check the Project
2 | 2020-09-02 | Soniya, selenium log file | MRMax Import | 100% | Completed | Locally Check Import Files, DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary, DRS Weekley
3 | 2020-09-03 | Vastu, selenium log file | Vastu pages design, selenium log file count | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary, DRS Weekley
4 | 2020-09-07 | Selenium log file Verifications | Selenium log file count , and Manually Upload Warranty All SSC'S (AUG,SEP(QMVAR)) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary, DRS Weekley,
5 | 2020-09-08 | Selenium log file Verifications | Selenium log file count , and Manually Upload Warranty All SSC'S(JULY(QMVAR)) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
6 | 2020-09-09 | Selenium log file Verifications, Soniya Project | Selenium log file count , and Invoice Update OOW, IW,EXW, record verification, Kuroganeya_INQUIRY | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
7 | 2020-09-10 | Selenium log file Verifications, Soniya Project | Selenium log file count , Soniya Project (Kuroganeya) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
8 | 2020-09-11 | Selenium log file Verifications, Soniya Project | Selenium log file count , Soniya Project (Kuroganeya_REP) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary_10 Days, Pr_Details_10_Days
9 | 2020-09-14 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (STREAM) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary, STRM_import, STRM_Search
10 | 2020-09-15 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (S5, best_ivc_close_return) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
11 | 2020-09-16 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (admin) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
12 | 2020-09-17 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (BIG_Input) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
13 | 2020-09-18 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (Homac_Import), Warranty Issue check(SSC1) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary
14 | 2020-09-21 | Selenium log file Verifications, QMVAR | Selenium log file count , QMVAR Monthly_Reservationvation(File Upload And Export) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary,
15 | 2020-09-22 | Selenium log file Verifications, QMVAR | Selenium log file count , QMVAR Monthly_Repairset(File Upload And Export) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary,
16 | 2020-09-23 | QMVAR | QMVAR Monthly_Repairset(File Upload And Export) | 100% | Completed
17 | 2020-09-24 | Selenium log file Verifications, QMVAR | Selenium log file count , QMVAR SID1 Testing(File Upload And Export) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary,
18 | 2020-09-25 | Selenium log file Verifications, Soniya | Selenium log file count , Soniya(nMVAR_Ai) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary, Tabel Manually Created of Soniya Project
19 | 2020-09-28 | Selenium log file Verifications, Soniya | Selenium log file count , Soniya(nMVAR_Ai) | 100% | Completed
20 | 2020-09-29 | Selenium log file Verifications, Soniya | Selenium log file count , Soniya(nMVAR_Search) | 100% | Completed
21 | 2020-09-30 | Selenium log file Verifications, Soniya | Selenium log file count , Soniya(nMVAR_Search, MrMax File Verification) | 100% | Completed | DRS Daily, ServicePartsReturn, GRSDaily, GRSDaily_Details, WarrantyDaily, POCDaily, PR_Summary,
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | Selenium log file | Selenium log file count , and Return Credit(Issue Checking and Solving QMVAR) | 100% | Completed | Daily and Monthly tasks Checking
2 | 2020-10-05 | Selenium log file, SONY SID, QMVAR Setup File Create | best_search_all8, best_report_all8, SID Sony | 100% | Completed | Sony SID Issue File Checking
3 | 2020-10-06 | Selenium log file, QMVAR | Selenium log file, QMVAR Setup File Create, QMVAR CSS | 100% | Completed | QMVAR CSS Progress
4 | 2020-10-07 | Selenium log file, QMVAR | Selenium log file, MrMax import File Check, QMVAR CSS | 100% | Completed | QMVAR CSS Progress
5 | 2020-10-08 | Selenium log file, EMP_RegLogin | Selenium log file, Employee RegLogin Application | 100% | Completed | Salary tab Page (Modification) Add Column
6 | 2020-10-09 | Selenium log file, EMP_RegLogin | Selenium log file, Employee RegLogin Application | 100% | Completed | Employee RegLogin Application All Pages design Changes(Personal Info, Education & experience , Bank Details Completed) tabs Completed
7 | 2020-10-12 | Selenium log file, Sony SID | Selenium log file, SONY SID (export import checking) | 100% | Completed | Sony Daily RepairSetNp, LogFile Selenium
8 | 2020-10-13 | Selenium log file, Sony SID, QMVAR Recovery(CSS) | Selenium log file, CSS QMVAR (Recovery Menu), Sony File Export | 100% | Completed | Sony Export,LogFile Selenium
9 | 2020-10-14 | Selenium log file, Sony SID | Selenium log file, Sony File Export selenium, | 100% | Completed | Sony Export,LogFile Selenium
10 | 2020-10-15 | Selenium log file, Sony SID, QMVAR (CSS) | Selenium log file, QMVAR migration, Sony File Export Selenium | 100% | Completed | Sony Export,LogFile Selenium
11 | 2020-10-16 | Selenium log file, Sony SID | Selenium log file, Sony Selenium File Export | 100% | Completed | Sony Export,LogFile Selenium
12 | 2020-10-19 | Selenium log file, Sony SID, QMVAR(CSS 2.0) | Selenium log file, Sony Selenium File , RPA Menu | 100% | Completed | Sony Export,LogFile Selenium, Rpa Menu, Analysis Refer menu
13 | 2020-10-20 | Selenium log file, Sony SID, Soniya | Selenium log file, Sony Selenium File Export, best_search_all8 Migration | 100% | Completed | Sony Export,LogFile Selenium
14 | 2020-10-21 | Selenium log file, Sony SID, Soniya | Selenium log file, Sony Selenium File Export, Kuroganeya Migration | 100% | Completed | Sony Export,LogFile Selenium
15 | 2020-10-22 | Selenium log file, Sony SID,QMVAR | Selenium log file, Sony Selenium File Export, QMVAR(CSS) | 100% | Completed | QMVAR CSS Progress
16 | 2020-10-23 | Selenium log file, Sony SID,QMVAR | Selenium log file, Sony Selenium File Export, QMVAR(CSS Menus active page) | 100% | Completed | QMVAR CSS(Menus Active page completed)
17 | 2020-10-26 | Selenium log file, Sony SID, | Selenium log file, Sony Selenium File Export | 100% | Completed | Sony Daily_RepairsetSet_NP import issue Find
18 | 2020-10-27 | Selenium log file, Sony SID | Selenium log file, Sony Selenium File Export | 100% | Completed | Samsung Warranty import issue Find
19 | 2020-10-28 | Selenium log file, Sony SID, QMVAR | Selenium log file, Sony Selenium File Export, QMVAR(CSS) | 100% | Completed | Sony Export,LogFile Selenium
20 | 2020-10-29 | Selenium log file, Sony SID, QMVAR | Selenium log file, Sony Selenium File Export, QMVAR(CSS) | 100% | Completed | QMVAR CSS(Date Picker)
21 | 2020-10-30 | Selenium log file, Sony SID | Selenium log file, Sony Selenium File Export | 100% | Completed | Sony Export,LogFile Selenium
Status
WIP
Pending
Completed
Hold

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | Selenium log file, Soniya nMVAR | Selenium log file count , and Saw discount(uploading issue in QMVAR) | 100% | Completed | Nmvar Processing
2 | 2020-11-03 | SONIYA Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Search | 100% | Completed | Soniya nMVAR_Search Completed
3 | 2020-11-04 | SONIYA Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Mtr | 30% | Wip | Soniya nMVAR_Mtr Completed
4 | 2020-11-05 | SONIYA Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Mtr | 65% | Wip | Soniya nMVAR_Mtr Completed
5 | 2020-11-06 | SONIYA Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Mtr | 100% | Completed | Selenium log file count , and Saw discount(uploading issue in QMVAR) . Soniya nMVAR_Mtr
6 | 2020-11-09 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Report | 100% | Completed | Selenium log file count , QMVAR) . Soniya nMVAR_Report(Activity report working)
7 | 2020-11-10 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Report, Nmvar_mtr | 100% | Completed | nMVAR_Report(Activity report working)
8 | 2020-11-11 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya nMVAR_Report | 100% | Completed
9 | 2020-11-12 | nMVAR Migration, selenium log Files(Sony, Samsung) | Setup Create exe, japanease languaeg | 100% | Completed | Setup Create exe, japanease languaeg not convert
10 | 2020-11-13 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya Bic_Report_soukatsu | 100% | Completed | Bic_Report_soukatsu Tessting
11 | 2020-11-16 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya Nmvar_TSS | 100% | Completed | Fuctionality Testing completed
12 | 2020-11-17 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya, Nmvar_TSS | 75% | Wip | Processing(Activity Report)
13 | 2020-11-18 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya, Nmvar_TSS | 100% | Completed
14 | 2020-11-19 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya Nmvar_Report | 30% | Wip | Processing(Activity Report)
15 | 2020-11-20 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya Nmvar_Report | 60% | Wip | Processing(Activity Report), sony daily deleverd uplading issue find
16 | 2020-11-23 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya Nmvar_Report | 100% | Completed
17 | 2020-11-24 | nMVAR Migration, selenium log Files(Sony, Samsung) | Soniya Nmvar_Mtr, Nmvar_Search, Nmvar_Ai | 100% | Completed | Setup_Create and testing
18 | 2020-11-25 | nMVAR Migration | Soniya Nmvar | 10% | Wip | Nmvar Report Working
19 | 2020-11-26 | Nil | Nil | Nil |  | Due to rain(Power cut)
20 | 2020-11-27 | Soniya | Best_search_all8, Best_Report | 100% | Completed | Issue Fixed, Setup Create all Modules(Soniya)
21 | 2020-11-30 | Soniya | Setup Create exe's(Over all Soniya Projects) |  | Wip | Progress
Status
Wip
Pending
Completed
Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | Soniya | Setup Create exe's(Over all Soniya Projects) | 100% | Completed | Besk Denki, Best Denki(oversease)
2 | 2020-12-02 | Soniya | Setup Create exe's(Over all Soniya Projects) | 100% | Completed | Stream, Koroganeya, MrMax
3 | 2020-12-03 | Soniya | Soniya nMVAR, Nmvar_Report | 100% | Completed | Activity Report PDF Formating Check and Chenage
4 | 2020-12-04 | Soniya | Nmvar_QA, Nmvar_TSS | 100% | Completed | Activity Report PDF Formating Check and Chenage
5 | 2020-12-07 | Nmvar | Nmvar(TSS, QA) | 100% | Completed | Retest Issues Fixing
6 | 2020-12-08 | Nmvar | Nmvar(mtr, Report) | 100% | Completed | Retest Issues Fixing
7 | 2020-12-09 | Nmvar | Nmvar(Search, AI) | 100% | Completed | Retest Issues Fixing
8 | 2020-12-10 | Nmvar | Nmvar | 100% | Completed | Nmvar Overall setup create
9 | 2020-12-11 | nMVAR Migration, selenium log Files(Sony, Samsung) | Nmvar | 100% | Completed | Nmvar overall setup testing,
10 | 2020-12-11 | nMVAR Migration, selenium log Files(Sony, Samsung) | Nmvar | 100% | Completed | Nmvar overall setup testing,
11 | 2020-12-14 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | November monthly Files also testing
12 | 2020-12-15 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
13 | 2020-12-16 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Soniya STRM | 100% | Completed | Soniya STRM File Export testing
14 | 2020-12-17 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
15 | 2020-12-18 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Bic_Report_Soukastu | 100% | Completed | Bic_Report_Soukastu Setup Create
16 | 2020-12-21 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Soniya | 100% | Completed | Soniya Over all Setup Modification(2021 Change)
17 | 2020-12-22 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Soniya | 100% | Completed | Soniya Over all Setup Modification(2021 remove program name)
18 | 2020-12-23 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Soniya | 100% | Completed | Soniya 2021 Change STRM in single Folder
19 | 2020-12-24 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | SONY Site records downloaded and testing
20 | 2020-12-28 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Soniya | 100% | Completed | MrMax_REP design changes, best_ivc_close (Best Denki over all) setup create
21 | 2020-12-29 | Selenium log files(SONY, SAMSUNG), Soniya | Selenium log file Testing (QMVAR TO GSPN), Soniya | 100% | Completed | STRM_import(Client Changes modification) and Setup Create, best_ivc_Close_rerturn(Modification design) and Setup create, best_ivc_close(Modification design) and Setup create
21 | 2020-12-30 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | SONY Site records downloaded and testing
22 | 2020-12-31 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | SONY Site records downloaded and testing
Status
WIP
Pending
Completed
Hold

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-04 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | SONY Site records downloaded and testing
2 | 2021-01-05 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | AscTax, AscGstTax New Samsung, Sony tasks testing also
3 | 2021-01-06 | Selenium log files(SONY, SAMSUNG) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | SONY Site records downloaded and testing
4 | 2021-01-07 | nMVAR Migration | Nmvar Changes request | 100% | Completed | Nmvar Chages and exe create(All modules)
5 | 2021-01-08 | nMVAR Migration, selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Nmvar exe Testing, Sony Testing(QMVAR TO GSPN)
6 | 2021-01-11 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Unable to import, Issue Find(Sony Daily Claim)
7 | 2021-01-12 | Selenium log Files(Sony, Samsung), GitHub | Selenium log file Testing (QMVAR TO GSPN), Git Hub | 100% | Completed | GitHub Pull and Push
8 | 2021-01-13 | Selenium log Files(Sony, Samsung), Git Hub | Selenium log file Testing (QMVAR TO GSPN), Git Hub | 100% | Completed | Git Hub Admin Testing(User Privilage)
9 | 2021-01-18 | Selenium log Files(Sony, Samsung), Soniya | Selenium log file Testing (QMVAR TO GSPN | 100% | Completed | Soniya setup Create(Modification)
10 | 2021-01-19 | Selenium log Files(Sony, Samsung), Git Hub | Selenium log file Testing (QMVAR TO GSPN), Git Hub | 100% | Completed | Git Hub Upload Soniya Project Modules
11 | 2021-01-20 | QMVAR 2.0 | SETUP ADD USER | 30% | Completed | Module, logic Create
12 | 2021-01-21 | Selenium log Files(Sony, Samsung), QMVAR 2.0 | SETUP ADD USER | 100% | Completed | GridView Completed
13 | 2021-01-22 | Selenium log Files(Sony, Samsung), QMVAR 2.0 | SETUP ADD USER | 100% | Completed | Create setup user completed
14 | 2021-01-25 | Laptop SSD changing | Laptop SSD changing |  |  | Laptop Service
15 | 2021-01-27 | Laptop Software installed | Laptop Software installed |  |  | Laptop Software installed
16 | 2021-01-29 | QMVAR 2.0, Sony samsung testing, Setup create | Setup User View part | 80% | Completed | Working View patr setup users

## FEB-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-02-01 | Selenium log Files(Sony, Samsung), QMVAR 2.0 | SETUP ADD USER | 90% | Completed | Create, Grid, Update setup user completed
2 | 2021-02-02 | Selenium log Files(Sony, Samsung), QMVAR 2.0 | Selenium log file Testing (QMVAR TO GSPN), SETUP USER | 100% | Completed | View Completed
3 | 2021-02-03 | Selenium log Files(Sony, Samsung), QMVAR 2.0 | Selenium log file Testing (QMVAR TO GSPN), SETUP USER | 100% | Completed | Setup User Modification
4 | 2021-02-04 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
5 | 2021-02-05 | nMVAR, Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Nmvar Change Request
6 | 2021-02-08 | nMVAR, Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Nmvar Change Request
7 | 2021-02-09 | nMVAR, Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Nmvar Change Request
8 | 2021-02-10 | Selenium log Files(Sony, Samsung), QMVAR 2.0 | Selenium log file Testing (QMVAR TO GSPN), SETUP USER | 100% | Completed
9 | 2021-02-11 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
10 | 2021-02-12 | nil | nil | nil |  | Laptop not started(OS Installing)
11 | 2021-02-15 | nMVAR, Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
12 | 2021-02-16 | nMVAR | Nmvar Change Request | 70% | Completed | Form Design Changes
13 | 2021-02-17 | nMVAR | Nmvar Change Request | 100% | Completed | Form Design Changes
14 | 2021-02-18 | nMVAR | Nmvar Change Request | 30% | Hold | Active Report's to Section Report(Change request) Processing
15 | 2021-02-19 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100%
16 | 2021-02-22 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Token System, Goods Deleverd and others(samsung sony)
17 | 2021-02-23 | nMVAR | Nmvar Change Request | 100% | Completed | Active Report's Alignment Changes
18 | 2021-02-24 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Token System, Goods Deleverd and others(samsung sony)
19 | 2021-02-25 | nMVAR | Nmvar Change Request | 100% | Completed | Active Report's Alignment Changes
20 | 2021-02-26 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% |  | Token System, Goods Deleverd and others(samsung sony)

## MAR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-03-01 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
2 | 2021-03-02 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
3 | 2021-03-03 | Selenium log Files(Sony, Samsung), Muji | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Muji Store chages(Video Search ASC,DESC Not working)
4 | 2021-03-04 | Selenium log Files(Sony, Samsung), Muji | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Muji Store chages(Japanease)
5 | 2021-03-05 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Other Sales Monthly Manually Upload to QMAVR
6 | 2021-03-08 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
7 | 2021-03-09 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed
8 | 2021-03-10 | nMVAR | Nmvar Report Changes | 100% | Completed | Active Report's to Section Report(20 reports Design completed)
9 | 2021-03-11 | nMVAR | Nmvar Report Changes | 100% | Completed | Section Report Export(Testing 10 reports completd)
10 | 2021-03-12 | nMVAR | Nmvar Report Changes | 100% | Completed | Section Report Export(Testing 15 reports completed)
11 | 2021-03-15 | nMVAR | Nmvar Report Changes | 100% | Completed | Active Report's to Section Report(32 reports Design completed)
12 | 2021-03-16 | nMVAR | Nmvar Report Changes | 100% | Completed | Section Report Export(Testing 15 reports completed)
13 | 2021-03-17 | nMVAR | Nmvar Report Changes | 100% | Completed | Section Report Export(Testing 32 reports completed)
14 | 2021-03-18 | Nmvar, Selenium log Files(Sony, Samsung) | Nmvar Report Changes | 100% | Completed | Nmvar report design changes
15 | 2021-03-19 | Selenium log Files(Sony, Samsung) | Nmvar Report Changes | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
16 | 2021-03-22 | Selenium log Files(Sony, Samsung) | Selenium log file Data Verification (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
17 | 2021-03-23 | Selenium log Files(Sony, Samsung) | Selenium log file Data Verification (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
18 | 2021-03-24 | Selenium log Files(Sony, Samsung) | Selenium log file Data Verification (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
19 | 2021-03-25 | nMVAR | Nmvar Changes | 100% | Completed | Nmvar change Request
20 | 2021-03-26 | Selenium log Files(Sony, Samsung) | Selenium log file Data Verification (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
21 | 2021-03-29 | Selenium log Files(Sony, Samsung), Muji | Selenium log file Data Verification (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0), Muji Design Changes(Video Cheange request, Video Change aprovel)
22 | 2021-03-30 | nMVAR | Nmvar change Request | 100% | Completed
23 | 2021-03-31 | Selenium log Files(Sony, Samsung) | Selenium log file Data Verification (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)

## APRIL-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-04-01 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Samsung Monthly task also Checking(Progressing)
2 | 2021-04-05 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
3 | 2021-04-06 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
4 | 2021-04-07 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
5 | 2021-04-08 | nMVAR | Nmvar change Request | 50% | WIP
6 | 2021-04-09 | nMVAR | Nmvar change Request | 100% | Completed
7 | 2021-04-12 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
8 | 2021-04-13 | LEAVE
9 | 2021-04-14 | LEAVE
10 | 2021-04-15 | Selenium log Files(Sony, Samsung), Nmvar | Selenium log file Testing, Nmvar change Request | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
11 | 2021-04-16 | nMVAR | Nmvar change Request | 100% | Completed | point no 25th
12 | 2021-04-19 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
13 | 2021-04-20 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
14 | 2021-04-21 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
15 | 2021-04-22 | Selenium log Files(Sony, Samsung) | Selenium log file Testing, Nmvar change Request | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
16 | 2021-04-23 | Selenium log Files(Sony, Samsung), Muji | Muji Testing | 100% | Completed | Muji Testing (All browsers)
17 | 2021-04-26 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
18 | 2021-04-27 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
19 | 2021-04-28 | Leave | Leave |  |  | Personal Leave
20 | 2021-04-29 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)
21 | 2021-04-30 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (GSPN TO QMVAR)AND (GSPN TO QMVAR2.0)

## MAY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-05-03 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 70% | WIP | April (Monthly Tasks Data Verfication),
2 | 2021-05-04 | Selenium log Files(Sony, Samsung) | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | April (Monthly Tasks Data Verfication), Daily Task(GSPN TO QMVAR and GSPN to QMVAR 2.0)
3 | 2021-05-05 | Muji Store | Stream Srevers | 100% | Completed | 5. Taking logs in results and report screen and design work.
4 | 2021-05-06 | Muji Store | Video Change Request | 100% | Completed | Approval status sorting not working, japanease Language Changing (Resource in Code)
5 | 2021-05-07 | Muji Store, Selenium Log File | Video Change Request | 100% | Completed | GRS, GRD Records duplication Verification , Alignment Issues Fixing
6 | 2021-05-10 | Muji Store | Muji Store | 100% | Completed | Regression(Design Issues Fixing)
7 | 2021-05-11 | Muji Store | Muji Store | 100% | Completed | Regression(Design Issues Fixing)
8 | 2021-05-12 | Muji Store, Samsung(Log files) | Muji Store | 100% | Completed | Good Receiving Details(QMVAR Uploading Issue check CSV(Solved)) , Search not working Stream Server Subnet Management
9 | 2021-05-13 | Muji Store, Samsung(Log files) | Muji Store | 100% | Completed | GRS, GRD Records duplication Verification QMVAR, QMVAR 2.0, Store Group folder management - Dropdown overlaps on footer section
10 | 2021-05-17 | Muji Store, | Muji Store | 100% | Completed | date format changing 24 hourse (hole application)
11 | 2021-05-18 | Muji Store, Samsung(Log files) | Muji Store | 100% | Completed | 5.Create/Edit - Store Management - Delete store group listed in the dropdown, 4.Store Group folder management - Dropdown overlaps on footer section
12 | 2021-05-19 | QMVAR | QMVAR | 100% | Completed | Regression issues (File Export, File upload)
13 | 2021-05-20 | Soniya, QMVAR | Soniya, QMVAR | 100% | Completed | SONIYA Source Code Consolidated and Verification, Menu(Activity Report)
14 | 2021-05-21 | QMVAR, Samsung(Log files) | QMVAR, Samsung | 100% | Completed | Recovery Menu, PR_Summary10 days, PR_Detail10 days data duplication verified
15 | 2021-05-24 | QMVAR 2.0 | QMVAR 2.0 (Analysis,Export) | 100% | Completed | Change Edit page title --> Edit - Service Center Change View Page title --> View - Service Center Close button not aligned properly in View Service Center Provide Space between Branch Name: and search box and Clear icon and Search button missing
16 | 2021-05-25 | QMVAR 2.0 | QMVAR 2.0 (Store mgt,Login) | 100% | Completed | "Change Ship name to branch name wherever appears Change the Validation message Please specify the Target data to be deleted" Credit Info Management - Data not updated for SID1 Logout, SSC1 and User name should be in same line
17 | 2021-05-26 | QMVAR 2.0 | QMVAR 2.0 (User Mgt, Service center) | 100% | Completed | Validation message not showing when saving it and Date picker not showing in Opening Date and Closing Date Validation message not showing when Editing and saving it Change the Update Successfully to Updated Successfully Branch Code 1 field list box in Create New user page Close button not aligned properly in View User
18 | 2021-05-27 | QMVAR 2.0 | QMVAR 2.0(RPA Scheduler) | 100% | Completed | Rpa Scheduler Date Picker format not working (Completed)
19 | 2021-05-28 | QMVAR 2.0 | QMVAR 2.0 | 50% | Completed | Ui Developing Holiday list (CREATE, GRID), Completed
20 | 2021-05-31 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Developing Holiday list Completed
Status
WIP
Pending
Completed
Hold

## JUNE-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-06-01 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Change Request Holiday list (Completed)
2 | 2021-06-02 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | May (Monthly Tasks Data Verfication),
3 | 2021-06-03 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0 | 100% | Completed | Image Icons locally called in Application, Daily task data verification
4 | 2021-06-04 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0 | 30% | WIP | Google Api links called locally, Daily task data verification
5 | 2021-06-07 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Activity report manually update(QMVAR and QMVAR 2.0), Daily tasks data verification(Sony Samsung)
6 | 2021-06-08 | Selenium log Files(Sony, Samsung), | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Daily tasks data verification(Sony Samsung)
7 | 2021-06-09 | QMVAR 2.0 | QMVAR 2.0 | 50% | WIP | live source code, modification (links and icons) entire project's
8 | 2021-06-10 | Nmvar | Nmvar | 100% | Completed | Change Request
9 | 2021-06-11 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | live source code, modification (links and icons) entire project's
10 | 2021-06-14 | QMVAR 2.0, Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Activity Report Manually Update QMVAR and QMVAR 2.0 all SSC'S
11 | 2021-06-15 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Design Chages(Icons alignment, design issue alignment)
12 | 2021-06-16 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Design Chages(Button Alignment Hole Projects)
13 | 2021-06-17 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Mobile View Design Check
14 | 2021-06-18 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Design Chages and deploye
15 | 2021-06-21 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Activity Report Manually Update QMVAR and QMVAR 2.0 all SSC'S, Sony Files Manually download and upload QMVAR and QMVAR 2.0(Saturday Sunday Files)
16 | 2021-06-22 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Mobile View Design Change (Live Source Code)
17 | 2021-06-23 | nMVAR,QMVAR 2.0, Sony Samsung | nMVAR, QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Change Request
18 | 2021-06-24 | QMVAR 2.0, Sony Samsung | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 alignment issues fixing (Live Source Code)
19 | 2021-06-25 | QMVAR 2.0, Sony Samsung | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Mobile View Grid Horizontal Scrollbar View Style Changes (Live Source Code Entire Application)
20 | 2021-06-28 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Sony Files Manually download and upload QMVAR and QMVAR 2.0 (Saturday Sunday Files)
21 | 2021-06-29 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Daily tasks data verification (Sony Samsung)
22 | 2021-06-30 | QMVAR 2.0, Sony Samsung | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR 2.0 Mobile View Sidebar Toggle Design Changes
Status
WIP
Pending
Completed
Hold

## JULY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-07-01 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 50% | WIP | Monthly tasks data verification (Sony Samsung), SAW Discount SSC11 uploading issue to mvs, to check the data (Issue fixing)
2 | 2021-07-02 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Monthly tasks data verification (Sony Samsung), Daily Task data Verification
3 | 2021-07-05 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Holiday List Manually Update in UI All SSC'S (QMVAR 2.0)
4 | 2021-07-06 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Sony (PL_Tracking_Sheet) not Uploading Issue checking (Fixed), Sony Files Manually Download and upload QMVAR and QMVAR 2.0
5 | 2021-07-07 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0 | 100% | Completed | UI Page Designing (QMVAR 2.0)
6 | 2021-07-08 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Daily tasks data verification (Sony Samsung)
7 | 2021-07-09 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Daily tasks data verification (Sony Samsung), QMVAR 2.0 (Apple Page UI Design)
8 | 2021-07-12 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Samsung, Sony | 100% | Completed | Selenium log file Warranty SSC11 Uploading Issue QMVAR (find and fix), QMVAR Apple (Page design HTML, CSS)
9 | 2021-07-13 | QMVAR 2.0, Samsung, Sony | QMVAR 2.0, Samsung, Sony | 100% | Completed | Daily tasks data verification (Sony Samsung), QMVAR 2.0 (Apple Page UI Design)
10 | 2021-07-14 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | RPA Daily tasks data verification (Sony, Samsung)
11 | 2021-07-15 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | RPA Daily tasks data verification (Sony, Samsung)
12 | 2021-07-16 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | RPA Daily tasks data verification (Sony, Samsung)
13 | 2021-07-19 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | RPA Daily tasks data verification (Sony, Samsung)
14 | 2021-07-20 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | RPA Daily tasks data verification (Sony, Samsung)
15 | 2021-07-21 | Leave
16 | 2021-07-22 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (2021-07-21 )th date RPA Daily tasks data verification (Sony, Samsung)
17 | 2021-07-23 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | DRS uploading issue QMVAR fixed, (2021-07-22 and 2021-07-23)th date RPA Daily tasks data verification (Sony, Samsung)
18 | 2021-07-26 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (SSC11 ) RPA GRD Data duplication find, RPA Daily tasks data verification (Sony, Samsung)
19 | 2021-07-27 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | RPA Daily tasks data verification (Sony, Samsung)
20 | 2021-07-28 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (2021-07-27)th date RPA Daily tasks data verification (Sony, Samsung)
21 | 2021-07-29 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (2021-07-28)th date RPA Daily tasks data verification (Sony, Samsung)
22 | 2021-07-30 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | (2021-07-29)th date RPA Daily tasks data verification (Sony, Samsung)
Status
WIP
Pending
Completed
Hold

## AUG-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-08-02 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | July Monthly tasks data verification (Sony Samsung),
2 | 2021-08-03 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | Sony Deleverd Set export Record count miss matching (Modification Source code), RPA Daily tasks data verification (Sony, Samsung)
3 | 2021-08-04 | Samsung, Sony, QMVAR | Selenium log file Testing (QMVAR TO GSPN), QMVAR | 100% | Completed | RPA Daily Tasks, QMVAR Weekly Revenue (Verification January Month)
4 | 2021-08-05 | QMAVR | QMVAR Weekly Revenue | 100% | Completed | QMVAR Weekly Revenue (Verification Febuary,March Month data's),
5 | 2021-08-06 | QMAVR | QMVAR Weekly Revenue | 100% | Completed | QMVAR Weekly Revenue (Verification Jult Month data's),
6 | 2021-08-09 | QMAVR | QMVAR Weekly Revenue | 100% | Completed | QMVAR Weekly Revenue (Verification Aprin, May Month data's),
7 | 2021-08-10 | QMAVR | QMVAR Weekly Revenue | 100% | Completed | QMVAR Weekly Revenue (Verification June,July Month data's),
8 | 2021-08-11 | QMVAR | QMVAR Weekly Revenue | 100% | Completed | PL_Tracking_Sheet Compare to Weekly Revenue (JAN,Feb)
9 | 2021-08-12 | QMAVR | QMVAR Weekly Revenue | 100% | Completed | PL_Tracking_Sheet Compare to Weekly Revenue (March,April)
10 | 2021-08-13 | QMAVR | QMVAR Weekly Revenue | 100% | Completed | PL_Tracking_Sheet Compare to Weekly Revenue (May,June)
11 | 2021-08-16 | QMVAR | QMVAR Count Drs | 100% | Completed | Actually Count DRS get the values for SC_DSR_Info table, now alter the query to change directly to get the Values SC_DSR table
12 | 2021-08-17 | QMVAR | QMVAR Count Drs | 30% | Progress | To Verify the Values to Ui, Screen (Delevoped)
13 | 2021-08-18 | QMVAR | QMVAR Count Drs | 100% | Completed | To Verify the Data in Ui, Screen
14 | 2021-08-19 | QMAVR, Muji | QMVAR Count Drs, Muji | 100% | Completed | Muji Browser Complatability (Edge), Query Checking With data's
15 | 2021-08-20 | QMAVR | QMVAR PL_Tracking_Sheet | 100% | Completed | QMVAR PL_Tracking_Sheet
16 | 2021-08-23 | QMAVR | QMVAR Count Drs | 50% | Progress | To verifying the data's Count Drs to Pl_Tracking Sheet(Qmvar_Live)
17 | 2021-08-24 | Muji | Muji Store | 100% | Completed | Edge To Check Video Playing all formats
18 | 2021-08-25 | QMAVR | QMVAR Call Load | 100% | Completed | Changes Call Load and PL_Tracking_Sheet Chaecking
19 | 2021-08-26 | QMAVR | QMVAR PL_Tracking_Sheet | 100% | Completed | To verifying the data's Count Drs to Pl_Tracking Sheet(Qmvar_Live)
20 | 2021-08-27 | QMAVR | QMVAR Weekly Graph | 100% | Completed | QMVAR Weekly Graph Template Changes and verify Data
21 | 2021-08-30 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Mobile View (Issues Fixing)
22 | 2021-08-31 | QMVAR 2.0 | QMVAR 2.0 Weekly Graph | 100% | Completed | Weekly Graph ( 4 template completed )
Status
WIP
Pending
Completed
Hold

## SEP-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-09-01 | QMVAR 2.0 | QMVAR 2.0 Weekly Graph | 100% | Completed | Call Load (4 template completed)
2 | 2021-09-02 | QMVAR 2.0, PENNA | QMVAR 2.0 Weekly Graph | 100% | Completed | Deploye and Verifying to (Live Server), Penna DB connect and testing
3 | 2021-09-03 | QMVAR 2.0 | QMVAR 2.0 (Logs Report) | 70% | WIP | Date Picker not working to Server
4 | 2021-09-06 | Muji | Muji | 100% | Completed | Muji Edge browser Video Downloaded (MP4, VOB,MPG,MPEG) all Formats
5 | 2021-09-07 | QMVAR 2.0, PENNA | QMVAR 2.0 (Logs Report) | 100% | Completed | Rpa Logs (Date Picker not working to Server), PENNA Demo To freshers
6 | 2021-09-08 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Weekly Graph template color Formaing chaging dynamically (wk28,wk30,wk31,wk29)
7 | 2021-09-09 | QMVAR 2.0, PENNA | QMVAR 2.0, PENNA | 100% | Completed | Qmvar 2.0 check live verified all month data's export(Weekly Graph ), Penna server login and source code access
8 | 2021-09-10 | Office Leave
9 | 2021-09-13 | QMVAR 2.0 | QMVAR 2.0 Weekly Grsaph | 100% | Completed | Sony Friday Files manually download and upload to qmvar2.0 , Weekly Graph template wk30 SID color chaging issue fixed
10 | 2021-09-14 | QMVAR 2.0 | QMVAR 2.0 | 70% | WIP | Mobile View Implementation QMVAR 2.0 Live source code
11 | 2021-09-15 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Mobile View Implementation QMVAR 2.0 Live source code
12 | 2021-09-16 | Personal Leave
13 | 2021-09-17 | PENNA | PENNA | 100% | Completed | PENNA CR
14 | 2021-09-20 | QMVAR 2.0 | QMVAR 2.0 | 50% | WIP | Mobile View Issues Fixing QMVAR 2.0
15 | 2021-09-21 | PENNA | PENNA | 100% | Completed | PENNA CR
16 | 2021-09-22 | QMVAR 2.0 , PENNA | QMVAR 2.0 , PENNA | 70% | WIP | Mobile View Issues Fixing QMVAR 2.0, PENNA CR
17 | 2021-09-23 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Mobile View Issues Fixing QMVAR 2.0
18 | 2021-09-24 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Mobile View Design Changes verification QMVAR 2.0 Live source code
19 | 2021-09-27 | QMVAR 2.0 | QMVAR 2.0 | 70% | WIP | Assign User Role qmvar 2.0
20 | 2021-09-28 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | Assign User Role qmvar 2.0
21 | 2021-09-29 | PENNA | PENNA | 100% | Completed | working javascript Issue and find error log report
22 | 2021-09-30 | PENNA, QMVAR | PENNA, QMVAR | 100% | Completed | qmvar drs file upload issue CHECKING
Status
WIP
Pending
Completed
Hold

## OCT-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-10-01 | MJA,PENNA, QMVAR | MJA,PENNA, QMVAR | 100% | Completed | qmvar saw discount rpa upload issues, jobseeker page design(30% completed)
2 | 2021-10-04 | PENNA, QMVAR | PENNA, QMVAR | 100% | Completed | Penna cr(test certificate)
3 | 2021-10-05 | PENNA, QMVAR | PENNA, QMVAR | 100% | Completed | Penna cr(test certificate)
4 | 2021-10-06 | PENNA, QMVAR | PENNA, QMVAR | 100% | Completed | Penna cr(test certificate), PR_SUMMARY, PR_DETAILS data missmatching locally testing
5 | 2021-10-07 | PENNA,MUJI | PENNA, MUJI | 100% | Completed | Penna cr(test certificate) Modification (CR)
6 | 2021-10-08 | PENNA, Nmvar | PENNA, Nmvar | 100% | Completed | Nmavr CR
7 | 2021-10-11 | nMVAR, QMVAR | nMVAR, QMVAR | 100% | Completed | Nmvar (CR), PR_SUMMARY, Details count checking manually(all centers)
8 | 2021-10-12 | PENNA, QMVAR | PENNA, QMVAR | 100% | Completed | Penna database and code checking, invoice update PDF checking
9 | 2021-10-13 | Muji, QMVAR | Muji, QMVAR | 100% | Completed | Muji Store Cocument Modification, Goods receicing Summary, Details qmvar Unable to export checking
10 | 2021-10-18 | PENNA | PENNA | 100% | Completed | penna clinker test certificate html design Working
11 | 2021-10-19 | PENNA | PENNA | 100% | Completed | penna clinker test certificate html design Working
12 | 2021-10-20 | PENNA | PENNA | 100% | Completed | penna clinker test certificate (Submit View) completed
13 | 2021-10-21 | Muji | Muji | 50% | WIP | Muji Document create(Foler, Store Group, User Edit)
14 | 2021-10-22 | Muji | Muji | 100% | Completed | Muji Document create (Administrator, Change password)
15 | 2021-10-25 | PENNA | PENNA | 100% | Completed | Admin role checking
16 | 2021-10-26 | PENNA | PENNA | 100% | Completed | Clinker Testing test Cirtificate
17 | 2021-10-27 | PENNA | PENNA | 100% | Completed | Monitering
18 | 2021-10-28 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | QMVAR (sony file upload issue 124 unrepair set & 119 Received Set),
19 | 2021-10-29 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | QMVAR2.0 (Data verification Sony, Samsung),
Status
WIP
Pending
Completed
Hold

## NOV-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-11-01 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | October Monthly tasks data verification (Sony Samsung),
2 | 2021-11-02 | QMVAR 2.0 | QMVAR 2.0 | 100% | Completed | SAW discount SSC11 upload failed to QMVAR (check and Clear)
3 | 2021-11-03 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | QMVAR2.0 (Data verification Sony, Samsung),
4 | 2021-11-08 | Samsung, Sony | Selenium log file Testing (QMVAR TO GSPN) | 100% | Completed | data verification (Sony Samsung),
5 | 2021-11-09 | QMVAR 2.0, Penna | QMVAR 2.0, Penna | 100% | Completed | data verification (Sony Samsung),
6 | 2021-11-10 | penna,QMVAR2.0 | penna,QMVAR2.0 | 100% | Completed | Penna ApI, QMVAR2.0 (Data verification Sony, Samsung),
7 | 2021-11-11 | penna,QMVAR2.0 | penna,QMVAR2.0 | 100% | Completed | Penna ApI, QMVAR2.0 (Data verification Sony, Samsung),
8 | 2021-11-12 | penna,QMVAR2.0,Nmvar | penna,QMVAR2.0,Nmvar | 100% | Completed | QMVAR2.0 (Data verification Sony, Samsung), Nmvar cr
WIP
Pending
Completed
Hold