## November-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-02-11 | QMVAR-RPA | Debitnoteregister Monthly failure | 100% | Completed | While file was moved to backup failed.Root cause of the issue was file was not closed properly,handled it.Also wild card characters for removing the files in download directory is handled separatley for the service centers.
|  | HAYAAI-B2B | Jobs display for services login | 70% | WIP | For Services
2 | 2020-03-11 | HAYAAi-B2B | Jobs display for services login | 80% | WIP | Service
3 | 2020-04-11 |  | Leave
4 | 2020-05-11 |  | Leave
5 | 2020-06-11 |  | Leave
6 | 2020-09-11 |  | Leave
7 | 2020-10-11 |  | Leave
8 | 2020-11-11 |  | Leave
9 | 2020-12-11 |  | Leave
10 | 13/11/2020 |  | Leave
11 | 16/11/2020 | Rlogic - GL | Started with Rlogic general ledger task | 40% | WIP
12 | 17/11/2020 | Rlogic - GL | Rlogic general ledger task | 70% | WIP
13 | 18/11/2020 | Rlogic - GL | Rlogic general ledger task,completed | 100% | Completed
14 | 19/11/2020 | Rlogic-GL | Rlogic general ledger task,corrections from Rahman san,done those | 30% | WIP
15 | 20/11/2020 | Rlogic-PL | P&L,Parts IO donwload done | 30% | WIP
16 | 23/11/2020 | Rlogic-PL | Formula cauclations from Rahman San as P&L formula changed | 30% | WIP
17 | 24/11/2020 | Rlogic-PL | Call wise merging with VLOOKUP | 50% | WIP
18 | 25/11/2020 | Rlogic-PL | Call wise merging with VLOOKUP | 100% | Completed
19 | 26/11/2020 | Rlogic-PL | Call wise data calculations | 30% | WIP
20 | 27/11/2020 | Rlogic-PL | Call wise data calculations | 80% | WIP
21 | 30/11/2020 | Rlogic-PL | Since Callwise data sheet changed,had to modify the code | 80% | WIP

## December-2020
No | Date | Application | Task | % of completion | Status
1 | 2020-12-01 | RLOGIC RPA | RLOGIC P&L | 90% | WIP
2 | 2020-12-02 | RLOGIC RPA | RLOGIC P&L | 100% | Completed
3 | 2020-12-03 | RPA SONY | RPA SONY to enable IE 8 code to work on ie11 | 30% | WIP
4 | 2020-12-03 | RPA SONY | RPA SONY to enable IE 8 code to work on ie11 | 70% | WIP
5 | 2020-12-04 | HAYAAI API | Worked on issues on B2C API | 100% | Completed
7 | 2020-12-07 | HAYAAI API | Worked on issues on B2C API | 100% | Completed
8 | 2020-12-08 | HAYAAI API | Worked on B2B API issue | 100% | Completed
9 | 2020-12-09 | RPA GSPN | Correction received for Purchase Summary,service repair | 100% | Completed
11 | 2020-12-10 | RPA Sony | Tried for windows registry key for avoiding save popup but was not working | 20% | WIP
12 | 2020-12-11 |  | Leave
13 | 2020-12-14 | HAYAAI API | Jobs not created in B2B,hence working on the root cause of the issue | 40% | WIP
14 | 2020-12-15 | HAYAAI API | Corrected the APIs in B2B and B2C to display data in JobSheet and for jobs creation | 80% | WIP
15 | 2020-12-16 | HAYAAI API | Jobs display | 80% | WIP
16 | 2020-12-17 | HAYAAI API | Warranty_type,email,address information added | 80% | WIP
17 | 2020-12-18 | Rlogic GL | GL creation for Rlogic | 80% | WIP
18 | 2020-12-21 | Rlogic GL | GL completion and PL started | 100% | WIP
19 | 2020-12-22 | Rlogic PL | PL creation | 100% | WIP
20 | 2020-12-23 | Sony Asctax | Sony Asctax creation | 60% | WIP
21 | 2020-12-24 | Sony Asctax | Sony Asctax creation and integration | 60% | WIP
22 | 2020-12-28 | Sony Asctax and gsttax | Sony Asctax and gsttax integration | 60% | WIP
23 | 2020-12-29 | Sony Asctax and gsttax | Sony Asctax and gsttax integration | 80% | WIP
24 | 2020-12-30 | Sony Asctax and gsttax | Sony Asctax and gsttax integration,corrections | 90% | WIP
25 | 2020-12-31 | Sony Asctax and gsttax | Leave

## Januray-2021
No | Date | Application | Task | % of completion | Status
1 | 2021-04-01 | Samsung RPA | DebitNite Register error correction,Invoice update correction | 100% | Completed
2 | 2021-05-01 | RPA SONY | ApNewsis Report no data error,correction | 60% | Completed
3 | 2021-06-01 | Samsung RPA | Invoice update correction for loading file | 100% | Completed
4 | 2021-07-01 | RPA SONY | ApNewsis Report error,correction | 70% | WIP
5 | 2021-08-01 | HAYAAI API | updateimei error not updating imei no,corrected | 100% | Completed
7 | 2021-11-01 | HAYAAI API | Add partner error correction in B2B | 60% | Completed
8 | 2021-12-01 | HAYAAI API | Add partner error correction in B2B | 70% | Completed
9 | 13/01/2021 | HAYAAI API | Add partner error correction in B2B | 100% | Completed
11 | 18/01/2021 | HAYAAI API | Product information for Service Request in B2B | 60% | WIP
12 | 19/01/2021 | HAYAAI API | Manually created jobs doesn't show in the list - | 100% | Completed
13 | 20/01/2021 | HAYAAI API | view job in SR throwing error | 100% | Completed
14 | 21/01/2021 | HAYAAI API | Failure description in SR and JOB shows wrongly | 100% | Completed
15 | 22/01/2021 | Rlogic GL | Warranty Status not get displayed in Jobs page | 100% | Completed
16 | 25/01/2021 | Rlogic PL | PL Generated | 100% | Completed
17 | 27/01/2021 | HAYAAI API | B2B Report correction | 30% | WIP
18 | 29/01/2021 | HAYAAI API | B2B Report correction | 70% | WIP

## February-2021
1 | 2021-02-01 | Hayaai | In B2B,corrected code manual SR creation error | 100% | Completed
2 | 2021-02-02 | RPA-SAMSUNG | credit information error as SSC4 is removed | 60% | WIP
3 | 2021-02-03 | RPA-SAMSUNG | credit information error as SSC4 is removed | 100% | Completed
4 | 2021-02-04 | Hayyai - B2B | Creation of new branch and new db | 40% | WIP
5 | 2021-02-05 | Hayyai - B2B | Checking user creation for new db | 30% | WIP
6 | 2021-02-06 |  | Week Off
7 | 2021-02-07
8 | 2021-02-08 | Hayyai - B2B | Working on data for new user | 40% | WIP
9 | 2021-02-09 | Hayyai - B2B | Working on data for new user | 100% | Completed
10 | 2021-02-10 | Hayyai - B2B | New user's menu privileges | 70% | WIP
11 | 2021-02-11 | Hayyai - B2B | Product registration view all records and datewise search | 100% | Completed
12 | 2021-02-12 | Hayyai - B2B | Parts add API,update | 50% | WIP
13 | 2021-02-13 |  | Week Off
14 | 2021-02-14
15 | 2021-02-15 | Hayyai - B2B | Parts Excel download | 80% | WIP
16 | 2021-02-16 | Hayyai - B2B | Product registration view based on imei and serial no | 80% | WIP
17 | 2021-02-17 | Hayyai - B2B | Product registration excel download based on search | 40% | WIP
18 | 2021-02-18 | Hayyai - B2B | Product registration excel download based on search | 80% | WIP
19 | 2021-02-19 | Hayyai - B2B | Product registration add with few new fields | 30% | WIP
20 | 2021-02-20 |  | Week Off
21 | 2021-02-21
22 | 2021-02-22 | Hayyai - B2B | Product registration add with few new fields | 80% | WIP
16 | 2021-02-23 | Hayyai - B2B | search products | 80% | WIP
17 | 2021-02-24 | Hayyai - B2B | Create new job | 40% | WIP
18 | 2021-02-25 | Hayyai - B2B | Create new job | 80% | WIP
19 | 2021-02-26 | B2B | B2B for error correction | 60% | WIP

## March-2021
1 | 2021-03-01 | Hayaai B2B | Parts Information pending | 80% | WIP
2 | 2021-03-02 | Hayaai B2B | B2B new layout Document and Design Modifications | 20% | WIP
3 | 2021-03-03 | Hayaai B2B | Service Job management Screen modification | 100% | Completed
4 | 2021-03-04 | Hayaai B2B | Warranty Extention - View & download screen | 100% | Completed
5 | 2021-03-05 | Hayaai B2B | Warranty Extention - EW invoice Details, Create new Job screen | 100% | Completed
6 | 2021-03-06 |  | Week Off
7 | 2021-03-07
8 | 2021-03-08 | Hayaai B2B | Warranty APIs development | 30% | WIP
9 | 2021-03-09 | Hayaai B2B | Warranty APIs development | 70% | WIP
10 | 2021-03-10 | Hayaai B2B | Warranty APIs development | 90% | WIP
11 | 2021-03-11 | Samsung RPA | New qmvar integration for PR Summary daily | 100%
12 | 2021-03-12 | Hayaai B2B | Warranty excel download | 80% | WIP
13 | 2021-03-13
14 | 2021-03-14
15 | 2021-03-15 | Samsung RPA | New qmvar for sony daily task | 50% | WIP
16 | 2021-03-16 | Samsung RPA | New qmvar for sony daily task | 90% | WIP
17 | 2021-03-17 | Samsung RPA | New qmvar integration for InvoiceupdateOOW weekly | 100% | Completed
18 | 2021-03-18 | Samsung RPA | New qmvar integration for PR Summary 10 days and Prdaily 10days | 100% | Completed
19 | 2021-03-19 |  | Leave
20 | 2021-03-20
21 | 2021-03-21
22 | 2021-03-22 | Hayaai B2B | New qmvar integration for InvoiceupdateOOW montly and service parts return | 100% | Completed
23 | 2021-03-23 | Hayaai B2B | New qmvar integration for InvoiceupdateEXC and invoiceupdateIW montly and service parts return | 100% | Completed
24 | 2021-03-24 | Hayaai B2B | Debitnoteregistermonthly and partsio qmvar integration | 100% | Completed
25 | 2021-03-25 | Hayaai B2B | Issues and development of B2B | 70% | WIP
26 | 2021-03-26 | Hayaai B2B | Issues and development of B2B | 70% | WIP
27 | 2021-03-27
28 | 2021-03-28
29 | 2021-03-30 | Hayaai B2B | Issues and development of B2B | 70% | WIP
30 | 2021-03-31 | Hayaai B2B | Issues and development of B2B | 70% | WIP

## April-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-04-01 | Hayaai | PArts information not loding in update jobs | 100% | Completed
2 | 2021-04-02 |  | Holiday
3 | 2021-04-03 |  | Week Off
4 | 2021-04-04
5 | 2021-04-05 | Hayaai | display parts for job | 100% | Completed
6 | 2021-04-06 |  | Holiday
7 | 2021-04-07 | Hayaai | Able to add same parts again and again duplication occurs | 70% | Completed
8 | 2021-04-08 | Hayaai | Duplication occurs by default add all parts then save and check | 80% | Completed
9 | 2021-04-09 | Hayaai | Update Jobs "App crash on clicking Update and Close button | 100% | Completed
10 | 2021-04-10 |  | Week Off
11 | 2021-04-11
12 | 2021-04-12 | Hayaai | App crash while dleting last parts in update jobs | 100% | Completed
13 | 2021-04-13 |  | Holiday
14 | 2021-04-14
15 | 2021-04-15 | Hayaai | Display error correction in reports
16 | 2021-04-16 | Hayaai | ADvance flow | 100% | Completed
17 | 2021-04-17 |  | Week Off
18 | 2021-04-18
19 | 2021-04-19 | Hayaai | billing flow | 70% | WIP
20 | 2021-04-20 | Hayaai | billing flow | 80% | WIP
21 | 2021-04-21 | Hayaai | dashbaord | 100% | Completed
22 | 2021-04-22 | Hayaai | cancel billing and some updated getbilling API | 100% | Completed
23 | 2021-04-23 | RPA-Samsung | PurchaseRegister date correction to Calendat | 100% | Completed
24 | 2021-04-24 |  | Week Off
25 | 2021-04-25
26 | 2021-04-26 | Hayyai | In job sheet report data error in report | 80% | WIP
27 | 2021-04-27 | Hayaai | QC implementation | 50% | WIP
28 | 2021-04-28 | Hayaai | saveBilling corrections | 30% | WIP
29 | 2021-04-29 |  | Leave
30 | 2021-04-30 | Hayaai | QC testing and getBilling correction | 80% | WIP

## May-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-05-01 |  | Week Off
2 | 2021-05-02
3 | 2021-05-03 | B2B | Qccheck implementation | 100% | Completed
4 | 2021-05-04 | B2B | Advance billing | 70% | WIP
5 | 2021-05-05 | B2B | Advance billing | 50% | WIP
6 | 2021-05-06 | B2B | Parts request change if not available | 65% | WIP
7 | 2021-05-07 | B2B | parts update change | 85% | WIP
8 | 2021-05-08 |  | Week Off
9 | 2021-05-09
10 | 2021-05-10 | B2B | Sales invoice | 40% | WIP
11 | 2021-05-11 | B2B | Sales invoice | 60% | WIP
12 | 2021-05-12 | B2B | Sales invoice | 75%
13 | 2021-05-13 | B2B | Sales invoice | 8500%
14 | 2021-05-14 |  | Week Off
15 | 2021-05-15
16 | 2021-05-16 |  | Weekoff
18 | 2021-05-17 | B2B | Sales invoice report
19 | 2021-05-18 | RPA | credit detail
20 | 2021-05-19 | RPA | credit detail
21 | 2021-05-20 | B2B | Extended warranty-sales invoice
22 | 2021-05-21
23 | 2021-05-22
23 | 2021-05-23
24 | 2021-05-24
25 | 2021-05-25
26 | 2021-05-26
27 | 2021-05-27
28 | 2021-05-28
29 | 2021-05-29
30 | 2021-05-30
Status
WIP
Pending
Completed
Hold

## August-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-08-01 |  | Week Off
2 | 2021-08-02 | Samsung-RPA | Five tasks completed for new popup window | 100% | Completed
3 | 2021-08-03 | Samsung-RPA | Three tasks completed for new popup window | 100% | Completed
4 | 2021-08-04 | GL-framework | Started with PRSummary | 50% | WIP
5 | 2021-08-05 | GL-framework | completed PR summary | 100% | Completed
6 | 2021-08-06 | GL-framework | Return credit completed | 100% | Completed
7 | 2021-08-07 | Holiday
8 | 2021-08-08 | Holiday
9 | 2021-08-09 | GL framework | RMA reject | 100% | Completed
10 | 2021-08-10 | GL framework | GL calculation | 30% | WIP
11 | 2021-08-11 | GL framework | GL calculation | 100% | Completed
12 | 2021-08-12 | GL framework | Integration | 30% | WIP
13 | 2021-08-13 | GL framework | Integration | 80% | WIP
14 | 2021-08-14 | Holiday
15 | 2021-08-15 | Holiday
16 | 2021-08-16 | PL framework | PartsIO | 100% | Completed
17 | 2021-08-17 | PL framework | Invoice uodateOW | 100% | Completed
18 | 2021-08-18 | PL framework | filreread | 100% | Completed
19 | 2021-08-19 | PL framework | search | 100% | Completed
20 | 2021-08-20 | PL framework | PL Calcualtion | 100% | Completed
21 | 2021-08-21 | Holiday
22 | 2021-08-22 | Holiday
23 | 2021-08-23 | PL framework | Integration
24 | 2021-08-24
25 | 2021-08-25
26 | 2021-08-26
27 | 2021-08-27
28 | 2021-08-28
29 | 2021-08-29
30 | 2021-08-30
31 | 2021-08-31