## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-04-29 | RPA Dotnet | [Backend] CRM | 30% | WIP | Tables are created at RPA Sale database, whereas relationship is penidng, after discussing with Mr Bharathi san, it will be over, if any changes or modification can be done.
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | MujiStore | MujiStore - Authorization for Stores video | 30% | WIP
2 | 2020-04-30 | MujiStore | MujiStore - Authorization for Stores video | 50% | WIP
Status
WIP
Pending
Completed
Hold

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
|  | QMVAR-RPA | Debitnote Register | 100%
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
2 | 2020-05-04 | Hayaai | Website design- Business page | 100% | Completed
2 | 2020-05-05 | Hayaai | Website design- Contact page & Business page popup | 60% | WIP
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-30 | DOTNET APP | Video | 70% | WIP | Retrive table Values for DB and Ui Design
2 | 2020-05-04 | DOTNET APP | Video | 100% | Completed
2 | 2020-05-04 | DOTNET APP | Presentation | 40% | WIP | Retrive table Values for DB and Ui Design
3 | 2020-05-05 | DOTNET APP | Presentation | 100% | Completed
4 | 2020-05-06 | DOTNET APP | Muji Multi Language(Resource Changing) | 50% | WIP | tblDeploySchedule, tblDeployStatu, SubnetController, DeploySchedulesController, FoldersController, FormatsController, HomeController, StoreGroupFoldersController, StoreGroupsController, StreamServersController, StreamServerSubnetsController, VideoFilesController, StreamServerFormats
5 | 2020-05-07 | DOTNET APP | Muji Multi Language(Resource Changing) | 100% | Completed | tblFolder, tblFolder, tblStreamServer, tblStreamServerSubnet, DeployLogs, DeploySchedules, DeployStatus, Formats, Shared, StoreMst, StoreSubnets, StreamServers, StreamServerSubnets, Subnets, VideoFiles
6 | 2020-05-08 | DOTNET APP | Hit Counter | 30% | WIP | Retrive Values for DB and Ui Design
7 | 2020-05-11 | DOTNET APP | Hit Counter, UserPresentation | 30% | WIP | UserPresentation Chages Completed and design Chages
8 | 2020-05-12 | DOTNET APP | Hit Counter | 100% | Completed
9 | 2020-05-13 | DOTNET APP | Hit Counter, SocialMedia | 60% | WIP | Hit Counter Design Changes Completed, SocialMedia Working
10 | 2020-05-14 | QMVQR, | CountDrs Testing | 100% | Completed | Matching Values for all centers ssc1-ssc8
11 | 2020-05-15 | DOTNET APP | Mobile Srevice Centers , SocialMedia | 30% | WIP | retrive db and css design
12 | 2020-05-18 | DOTNET APP | Social Media | 30% | WIP | Insert table values
13 | 2020-05-19 | DOTNET APP | Social Media | 30% | WIP | GridView Show the table, Delete
14 | 2020-05-20 | DOTNET APP | Social Media, Count Drs Verified | 100% | Completed | Count Drs data check complted
15 | 2020-05-21 | DOTNET APP | PowerPoint Presentation design and dynamic download | 100% | Completed
16 | 2020-05-22 | DOTNET APP | Testing RPA_Sales Application | 50% | WIP | Login Page, User Management, Video Management, PPT Management
17 | 2020-05-26 | DOTNET APP | RPA_Sales Application (Language Changing), GSPN Password Changing | 100% | Completed | Login Page, User Management, CRM, SocialMedia, Task Management, Video Management, PPT Management, Dashboard, RPA Sample Reports
18 | 2020-05-27 | QMVQR, DOTNET APP | QMVAR PO_Confirmaion, RPA_Sales(Hold) | 30% | WIP | PO_Confirmaion data check to verification Completed, RPA_Sales language Resource changing
19 | 2020-05-28 | DOTNET APP | RPA_Sales(CRUD Operations) | 50% | WIP | GridView Show the table, Insert the values
20 | 2020-05-29 | DOTNET APP | RPA_Sales(CRUD Operations) | 100% | Completed | Edit, Delete the Records Completed
June
21 | 2020-06-01 | DOTNET APP | RPASales LAnguage (Resource Changing) | 50% | WIP | Admin Menu Changes Completed
22 | 2020-06-02 | DOTNET APP | RPASales LAnguage (Resource Changing) | 100% | Completed | Client Menu Changes Completed
23 | 2020-06-03 | DOTNET APP | RPASales Language (Testing and Designing) | 50% | WIP
24 | 2020-06-04 | DOTNET APP | RPASales Language (Testing and Designing) | 100% | Completed
25 | 2020-06-05 | RPA Application | SSC10 Adding RPA tasks | 50% | WIP | DRS, Warranty, Purches Order (Summary, Details), Good Receiving (Summary, Details)
26 | 2020-06-08 | RPA Application | SSC10 Adding RPA tasks | 90% | WIP | Monthly Tasks, 10 days Completed
27 | 2020-06-09 | DOTNET APP, RPA Applicatoin | SSC10 Adding RPA tasks, RPA_Sales integration japanease code | 100% | Completed
28 | 2020-06-10 | RPA Application | SSC10 Adding Scneduler | 100% | Completed | Adding Scheduler ssc10
29 | 2020-06-11 | GSS Website design | GSS Website design(Hold) | 10% | Completed | Div Images align and Text design(Store Menu)
30 | 2020-06-12 | GSS Website design | GSS Website design(Hold) | 10% | Completed | Div Images align and Text design(Our team Menu)
31 | 2020-06-15 | Muji Store | Muji Multi Language(Resource Changing), Design Changes | 90% | WIP | Robo Copy Exist Code, Layout page, RoboCopyExistController
32 | 2020-06-16 | GSS Website design | GSS Website design | 50% | WIP | Rpa Solution
33 | 2020-06-17 | GSS Website design | GSS Website design, Muji Design Changes | 100% | Completed
34 | 2020-06-18 | Muji Store | Muji Multi Language(Resource Changing Checking), | 50% | WIP
35 | 2020-06-21 | Muji Store | Muji Multi Language(Resource Changing Checking), | 100% | Completed
36 | 2020-06-22 | Muji Store | Muji Multi Language(Design Changes), | 50% | WIP | VideoChange Aproval,
37 | 2020-06-23 | Muji Store | Muji Multi Language(Design Changes), | 100% | Completed | \Video Management
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
1 | 29/04/2020 | Rever B2C | IF full flow with technician tracking integration | 100% | Completed | APK sent.
Status
WIP
Pending
Completed
Hold