## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | QMVAR | DRS Count Design | 100% | Completed
2 | 2020-10-01 | RPA | Testing Data | 100% | Completed
2 | 2020-10-02 |  | Holiday
3 | 2020-10-03 |  | Week off
4 | 2020-10-04 |  | Week off
5 | 2020-10-05 | Soniya | Creating Setup file | 50% | WIP
6 | 2020-10-06 | Soniya | creating Setup file | 100% | Completed
7 | 2020-10-07 | QMVAR | Layout Designing |  | WIP
8 | 2020-10-08 | Emplogin | Adding assests Detatils | 50% | WIP
9 | 2020-10-09 | Emplogin | Adding assests Detatils | 100% | Completed
10 | 2020-10-10 |  | Week off
11 | 2020-10-11 |  | Week off
12 | 2020-10-12 | Emplogin | Adding assests Detatils and responisble view | 100% | Completed
13 | 2020-10-13 | QMVAR | Adding assests Detatils | 100% | WIP
14 | 2020-10-14 | QMVAR | stored management added in Monthly target | 100% | Completed
15 | 2020-10-15 | QMVAR | adding layout in analysis file upload | 70% | WIP
16 | 2020-10-16 | QMVAR | adding layout in analysis file Export | 50% | WIP
17 | 2020-10-17 |  | Week off
18 | 2020-10-18 |  | Week off
19 | 2020-10-19 | QMVAR | adding layout in analysis report and stored managemant | 50% | WIP
20 | 2020-10-20 | soniya | migration testing issue | 100% | Completed
21 | 2020-10-21 | QMVAR | fixing alignment | 30% | WIP
22 | 2020-10-22 | QMVAR | fixing alignment | 50% | WIP
23 | 2020-10-23 | QMVAR | fixing alignment | 60% | WIP
24 | 2020-10-24 |  | Week off
25 | 2020-10-25 |  | Week off
26 | 2020-10-26 |  | Week off
27 | 2020-10-27 | QMVAR | issue fixing |  | WIP
28 | 2020-10-28 | QMVAR | issue fixing |  | WIP
29 | 2020-10-29 | QMVAR | issue fixing |  | WIP
30 | 2020-10-30 | QMVAR | issue fixing |  | WIP

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | QMVAR | QMVAR Fixing |  | Completed
2 | 2020-11-03 | Nmvar | Nmvar Migration |  | WIP
3 | 2020-11-04 | Nmvar | Nmvar Migration |  | WIP
4 | 2020-11-05 | Nmvar | Nmvar Migration |  | WIP
5 | 2020-11-06 | Nmvar | Nmvar Migration |  | WIP
6 | 2020-11-07 | SAT & SUN DAY
7 | 2020-11-08
8 | 2020-11-09 | Nmvar | Nmvar Migration |  | WIP
9 | 2020-11-10 | Nmvar | Nmvar Migration |  | WIP
10 | 2020-11-11 | Nmvar & soniya | Nmvar Migration |  | WIP
11 | 2020-11-12 | soniya | issue fixing |  | WIP
12 | 2020-11-13 | soniya | issue fixing |  | Completed
13 | 2020-11-14 | SAT & SUN DAY
14 | 2020-11-15
15 | 2020-11-16 | soniya | issue fixing |  | Completed
16 | 2020-11-17 | Nmvar | Nmvar Migration |  | Completed
17 | 2020-11-18 | soniya | issue fixing |  | WIP
18 | 2020-11-19 | soniya | issue fixing |  | Completed
19 | 2020-11-20 | personal leave
20 | 2020-11-21 | SAT & SUN DAY
21 | 2020-11-22
22 | 2020-11-23 | soniya | issue fixing |  | Completed
23 | 2020-11-24 | soniya | issue fixing |  | WIP
24 | 2020-11-25 | soniya | issue fixing |  | Completed
25 | 2020-11-26 | nMVAR | Migration |  | WIP
26 | 2020-11-27 | nMVAR | Migration |  | WIP
28 | 2020-11-28 | SAT & SUN DAY
29 | 2020-11-29
30 | 2020-11-30 | nMVAR | nMVAR Migration Activuty report | 70% | WIP
Status
| WIP | WIP
| Pending | Pending
| Completed | Completed
| Hold | Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold