## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-04-29 | RPA Dotnet | [Backend] CRM | 30% | WIP | Tables are created at RPA Sale database, whereas relationship is penidng, after discussing with Mr Bharathi san, it will be over, if any changes or modification can be done.
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | MujiStore | MujiStore - Authorization for Stores video | 30% | WIP |  | Status
2 | 2020-04-30 | MujiStore | MujiStore - Authorization for Stores video | 50% | WIP |  | WIP
3 | 2020-05-05 | MujiStore | MujiStore - Authorization for Stores video | 100% | Completed |  | Pending
4 | 2020-05-06 | MujiStore | Subnet Integration for Troubleshooting | 10% | WIP |  | Completed
5 | 2020-05-07 | MujiStore | Subnet Integration for Troubleshooting | 20% | WIP |  | Hold
6 | 2020-05-08 | MujiStore | Subnet Integration for Troubleshooting | 30% | WIP
7 | 2020-05-11 | MujiStore | Subnet Integration for Troubleshooting | 40% | WIP
8 | 2020-05-11 |  | Code Merging |  |  | Multi language integration get from Prabhu, Menu Integration from Ram
9 | 2020-05-11 | QMVAR | SV1 issue |  |  | Find and fix the issue
10 | 2020-05-12 | MujiStore | Subnet Integration for Troubleshooting | 50% | WIP
11 | 2020-05-12 | RPA Dotnet | Check and upload DB objects
12 | 2020-05-13 | MujiStore | Subnet Integration for Troubleshooting | 60% | WIP
13 | 2020-05-14 | MujiStore | Subnet Integration for Troubleshooting | 70% | WIP
14 | 2020-05-14 | QMVAR | Account Report |  |  | Gone through document
15 | 2020-05-15 | MujiStore | Subnet Integration for Troubleshooting | 80% | WIP
16 | 2020-05-15 | RPA Dotnet | Check and upload DB objects and Application
17 | 2020-05-18 | MujiStore | Subnet Integration for Troubleshooting | 100% | Completed
18 | 2020-05-18 | MujiStore | Code meging from Ram source code
19 | 2020-05-18 | MujiStore | Muji Store Deployment
20 | 2020-05-19 | MujiStore | Subnet Integration for Troubleshooting | 100% | Completed | Bug fixing completed
21 | 2020-05-19 | MujiStore | KT Given to Team for How to deploy in server (both App and DB)
22 | 2020-05-19 | MujiStore | Analysis Media file Approval
23 | 2020-05-20 | QMVAR | Account Report | 5 | WIP
24 | 2020-05-20 | MujiStore | KT Given to Ram
25 | 2020-05-20 | QMVAR | DRS Count issue
26 | 2020-05-21 | QMVAR | Account Report | 5 | WIP | Discuss with Elaya, Rahman and Mamatha. This task put on hold. We need to discuss to client on tomorrow
27 | 2020-05-21 | QMVAR | Count DRS |  |  | Total value issue fixed, Need to check Count DRS with data
28 | 2020-05-22 | QMVAR | Account Report | 5 | WIP | Discuss with Elaya, Rahman and Mamatha, Mohan Shimada San.
29 | 2020-05-22 | QMVAR | Count DRS |  |  | Issue fixed.
30 | 2020-05-26 | QMVAR | Account Report | 25 | WIP
31 | 2020-05-27 | QMVAR | Account Report | 40% | WIP
32 | 2020-05-27 | MujiStore | Multi language integrated from Ram |  | Completed
33 | 2020-05-27 | MujiStore | Default load Japanes language |  | Completed
31 | 2020-05-28 | QMVAR | Account Report | 65% | WIP
32 | 2020-05-29 | QMVAR | Account Report | 100% | Completed
32 | 2020-06-01 | QMVAR | Account Report |  |  | format changed fom csv to htmltable then excel completed. Currency fromat changed
33 | 2020-06-01 | QMVAR | Account Report |  |  | KT given to Ram for design html template
34 | 2020-06-02 | QMVAR | Account Report |  |  | Html table design implemented Account report table
35 | 2020-06-02 | MujiStore | Log table |  |  | Log table not used in existing application. It may be use other application (Video file process)
36 | 2020-06-02 | QMVAR | Code merge and deployment
37 | 2020-06-03 | QMVAR | PO Confirmation issue
38 | 2020-06-04 | QMVAR | PO Confirmation issue |  | completed
39 | 2020-06-04 | MujiStore | Media file approval | 15% | WIP
40 | 2020-06-05 | MujiStore | Media file approval | 20% | WIP
41 | 2020-06-08 | MujiStore | Media file approval | 40% | WIP
42 | 2020-06-09 | MujiStore | Media file approval | 60% | WIP
43 | 2020-06-10 | MujiStore | Media file approval | 75% | WIP
44 | 2020-06-11 | MujiStore | Media file approval | 85% | WIP
45 | 2020-06-12 | MujiStore | Media file approval | 100% | completed
46 | 2020-06-15 | MujiStore | Media file approval document modification
47 | 2020-06-15 | QMVAR | Looking Issue in DSR with Mohan San
48 | 2020-06-15 | MujiStore | KT Given to Prabhu
49 | 2020-06-16 | QMVAR | Looking Issue in DSR with Mohan San and Find the issue By Mohan San
50 | 2020-06-16 | Sonia | Go through Soica Project and create DB
51 | 2020-06-16 | MujiStore | Deployment
52 | 2020-06-17 | Sonia | Working Sonia Project
53 | 2020-06-17 | MujiStore | Deployment
54 | 2020-06-17 |  | System Windows Update
55 | 2020-06-18 | Sonia | Working Sonia Project
56 | 2020-06-18 | MujiStore | Deployment
57 | 2020-06-18 |  | System Windows Update
58 | 2020-06-18 | MujiStore | Prepare Language Information
60 | 2020-06-19 | SONIA | Modules - Best Denki, All Denka, Stream | 30 | WIP
61 | 2020-06-22 | SONIA | Module - Best Denki - web data creation(best_web_data_bat.exe,best_web_data_sub1.exe,best_web_data_sub2.exe,best_web_data_sub3.exe,best_web_data_sub4.exe) | 100 | Completed
62 | 2020-06-22 | MujiStore | Deployment
63 | 2020-06-23 | MujiStore | Deployment
64 | 2020-06-23 | SONIA | Modules - Best Denki, All Denka, Stream | 20%
65 | 2020-06-24 | SONIA | Modules - Best Denki, All Denka, Stream | 50%
66 | 2020-06-25 | SONIA | Modules - Best Denki, All Denka, Stream | 70%
67 | 2020-06-25 | QMVAR | Daily Summary
68 | 2020-06-26 | SONIA | Modules - Best Denki, All Denka, Stream | 80%
69 | 2020-06-29 | SONIA | Modules - Best Denki, All Denka, Stream | 100%
70 | 2020-06-30 | SONIA | Modules - Best Denki, All Denka, Stream | 100%
71 | 2020-07-01 | SONIA | Modules - Best Denki, All Denka, Stream
72 | 2020-07-01 |  | Email Merge from Google spread sheet
73 | 2020-07-02 |  | Email Merge from Google spread sheet | 100% | Completed
74 | 2020-07-03 | SONIA | Modules - Best Denki, All Denka, Stream | 20% | WIP
75 | 2020-07-06 | SONIA | Modules - Best Denki, All Denka, Stream | 30% | WIP
76 | 2020-07-06 | QMVAR | Working DSR issue
77 | 2020-07-07 | SONIA | Modules - Best Denki, All Denka, Stream | 50% | WIP
78 | 2020-07-08 | SONIA | Missing DB objects documented | 100% | Completed
79 | 2020-07-09 | SONIA | Modules - Best Denki, All Denka, Stream | 100% | WIP
80 | 2020-07-09 |  | Email from Google forms
79 | 2020-07-10 | SONIA | Modules - Best Denki, All Denka, Stream
80 | 2020-07-13 | QMVAR | Upload summary issue
81 | 2020-07-13 | SONIA | DB Creation
82 | 2020-07-13 |  | Email Merge from Google spread sheet
83 | 2020-07-14 | SONIA | DB Creation
84 | 2020-07-14 |  | Email Merge from Google form
85 | 2020-07-15 |  | Email Merge from Google form
86 | 2020-07-16 |  | Email Merge from Google form
87 | 2020-07-17 |  | Email Merge from Google form
88 | 2020-07-17 | QMVAR | Working Count DSR issue
88 | 2020-07-20 | VASTU | Vastu Project set up
89 | 2020-07-21 | CODE | Email Merge from Google spread sheet
90 | 2020-07-21 | SOINA | Active Report issue
91 | 2020-07-21 | VASTU | Added Additional table and support team
92 | 2020-07-22 | SOINA | Download Active report setup and used in Application
93 | 2020-07-22 | CODE | Email Merge from Google spread sheet
94 | 2020-07-22 | VASTU | BackEnd Vastu Master Module
95 | 2020-07-23 | SONIA | Input Man Dll checking
96 | 2020-07-23 | SONIA | Active Report issue
97 | 2020-07-24 | SONIA | Active Report issue
98 | 2020-07-27 | SONIA | Active Report issue
99 | 2020-07-28 | SONIA | Input Man Dll checking
100 | 2020-07-29 | SONIA | Vastu Report PDF Issue
101 | 2020-07-29 | SONIA | Vastu Project Master Page
102 | 2020-07-30 | SONIA | Input Man DLL Issue License Issue fixed and two Project Build
103 | 2020-07-31 | SONIA | Conversion completed . DB need to merge from other developer
104 | 2020-08-03 | SONIA | Implement Product key in Sonia Application
105 | 2020-08-03 | VASTU | Master Page start working
106 | 2020-08-04 | SONIA | Issue "ImeHandler" working in Soina Project
107 | 2020-08-04 | VASTU | Master Page
108 | 2020-08-05 | SONIA | Issue "ImeHandler" fixed in Soina Project
109 | 2020-08-05 | VASTU | Master Page
110 | 2020-08-06 | VASTU | Master Page
111 | 2020-08-07 | VASTU | Master Page
112 | 2020-08-10 | VASTU | Master Page
113 | 2020-08-11 | VASTU | Master Page
114 | 2020-08-12 | VASTU | Master Page
115 | 2020-08-13 | VASTU | Authorization,Session and Role
116 | 2020-08-13 | VASTU | Source Code Merge and Deployment
117 | 2020-08-14 | VASTU | Source Code Merge, Deployment and Bug fixing
118 | 2020-08-17 | VASTU | Testing Issues Fix
119 | 2020-08-18 | VASTU | Testing Issues Fix
120 | 2020-08-19 | VASTU | Testing Issues Fix
121 | 2020-08-20 | VASTU | Testing Issues Fix
122 | 2020-08-21 | VASTU | Testing Issues Fix
123 | 2020-08-24 | VASTU | Testing Issues Fix, Vastu Master Log
124 | 2020-08-25 | VASTU | Testing Issues Fix, Vastu Master Log
126 | 2020-08-26 | VASTU | Testing Issues Fix, Vastu Master Log
127 | 2020-08-27 | VASTU | Testing Issues Fix
128 | 2020-08-28 | VASTU | Testing Issues Fix
129 | 2020-08-31 | VASTU | Testing Issues Fix
130 | 2020-09-01 | VASTU | Testing Issues Fix
131 | 2020-09-02 | VASTU | Testing Issues Fix and New enhancement
132 | 2020-09-03 | VASTU | Testing Issues Fix and New enhancement
133 | 2020-09-04 | VASTU | Testing Issues Fix and New enhancement
134 | 2020-09-07 | VASTU | Testing Issues Fix and New enhancement
135 | 2020-09-08 | VASTU | Testing Issues Fix
136 | 2020-09-08 | SONIA | MrMax Testing and fixing Issue
137 | 2020-09-08 | QMVAR | SAW Discount issue looking
138 | 2020-09-09 | VASTU | Testing Issues Fix and New enhancement
139 | 2020-09-10 | VASTU | Testing Issues Fix and New enhancement
140 | 2020-09-14 | SONIA | Homax Testing and fixing Issue
141 | 2020-09-14 | QMVAR | Sony upload and Export KT from Mohan San
142 | 2020-09-15 | SONIA | Testing and fixing Issue
143 | 2020-09-16 | SONIA | Testing and fixing Issue
144 | 2020-09-17 | SONIA | Testing and fixing Issue
145 | 2020-09-18 | SONIA | Testing and fixing Issue
146 | 2020-09-21 | VASTU | Testing Issues Fix and New enhancement
147 | 2020-09-22 | VASTU | Testing Issues Fix and New enhancement
148 | 2020-09-23 | QMVAR | DRS Count - Saw Discount with out discount
149 | 2020-09-24 | QMVAR | DRS Count - Saw Discount with out discount
150 | 2020-09-25 | QMVAR | DRS Count - Saw Discount with out discount
151 | 2020-09-26 | SONIA | Testing and fixing Issue
152 | 2020-09-27 | SONIA | Testing and fixing Issue
153 | 2020-09-30 | SONIA | Checking Mr max Import issue
154 | 2020-09-30 | QMVAR | DRS Count - Added New Service Center SSC11
155 | 2020-10-01 | VASTU | Checking date time issue
156 | 2020-10-01 | RPA Dotnet | Project set up
157 | 2020-10-05 | QMVAR | DRS Count - Saw Discount changes and Issue
158 | 2020-10-06 | QMVAR | DRS Count - Saw Discount Summary & Details | 50
159 | 2020-10-07 | QMVAR | DRS - Daily Revenue | 20
160 | 2020-10-08 | QMVAR | DRS - Daily Revenue | 40
161 | 2020-10-09 | QMVAR | DRS - Daily Revenue | 50
162 | 2020-10-12 | QMVAR | DRS - Daily Revenue | 65
163 | 2020-10-13 | QMVAR | DRS - Daily Revenue | 80
164 | 2020-10-14 | QMVAR | DRS - Daily Revenue | 100
165 | 2020-10-15 | SONIA | Go through Soica Project MDB File Application
166 | 2020-10-16 | SONIA | Check Suma Email and Start work application
167 | 2020-10-19 | SONIA | Access DB Migration - BIC CAMERA - 1 | 10
168 | 2020-10-20 | SONIA | Access DB Migration - BIC CAMERA - 1 | 30
169 | 2020-10-21 | SONIA | Access DB Migration - BIC CAMERA - 1 | 50

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
1 | 29/04/2020 | Rever B2C | IF full flow with technician tracking integration | 100% | Completed | APK sent.
Status
WIP
Pending
Completed
Hold