## Balraj
No | Date | Application | Task | % of completion | Status
|  |  | [Backend] CRM |  |  | 1. Datass are fetched from CRM table and displayed the results in dropdownlist dynamically 2. Customer type dropdownlist has been created using using enum and displayed in right order 3. Working on onchange events to select all emailid based on customer types.
|  |  | Hayaai website |  | Completed | 1. Visited customer information from the contact us page of hayaai website has been recorded in the database using PHP and MYQL
|  |  | Hayaai website |  | WIP | Sending email is in progress
|  |  | Hayaai website | 90 | Completed | data insertion and email sending are completed, whereas we have tested email sending using gmail.com for contacts.html. We are waiting for actual email settings for hayaai site.
|  |  | Hayaai website | 95 | Completed | Email validation and contact number validation has been completed before submiting fields values to the database.
|  |  | RPA_Sale/[Front End] Full app keyword search | 10 | WIP | Analysing the all tables to fetch all records and keep it as list and obtaining the keyword by filtering from the list and converting the result with paging and pagelisted concept in MVC
|  | Status | RPA_Sale/[Front End] Full app keyword search | 30 | WIP | Searching string in all tables from the entire database has been completed , whereas UI design and development are pending
WIP
Pending
|  | Completed | RPA_Sale/[Front End] Full app keyword search | 40 | WIP | Searching in all tables and fetching the results and displaying the results at bottom of the master pages, whereas other activities like styling and crossref link or sublink tasks are pending.
Hold
|  |  | RPA_Sale/[Front End] Full app keyword search | 80 | WIP | Searching results are coming in right order along with query text, whereas a small design issue is pending and also no data found to be implemented.
|  |  | RPA_Sale/[Front End] Full app keyword search | 100 | Completed | No data found has been implemented if no records found and etc. Attended in RPASale_dev deployeement task
|  |  | RPA_Sale/[Front End] Full app keyword search |  |  | Today, I was engaged in rpa selenium tasks for DRS, GRS, and GRD DRS was done, GRS, till dowload portion is over and whereas, upload is pending as issue in converting xls to csv.
|  |  | Jiffy_to_selenium |  |  | Conversion from jiffy to selenium for the tasks of Goods Receiving Summary and Goods Receiving details are completed, whereas the conversion of warranty is WIP
Leave on 22-05-2020
|  |  | Jiffy_to_selenium |  |  | Conversion from JIFFY to selenium for the tasks of DRS, GRS and GRD are completed, CSV conversion for warranty is in Pending.
|  |  | RPA Customization |  | WIP | Customization of RPA tasks named as GRS and GRD are completed, no data found for warranty and csv header/contents validations are in progress. Also DRS no data found is also pending.
|  |  | RPA Customization |  | WIP | DRS Daily, DRS Weekly and DRS Monthly are completed with download/upload and no data found. Warranty csv file is having issue and hence it has been shared to Mohan san.
|  |  | RPA Customization |  | WIP | POC confirmation task has been implemented at new bot, and it will work for download and upload success
Warranty CSV file is having uploading issue.
|  |  | RPA Customization |  | WIP | 1. Fine tuning with DRS, GRS and GRD are done. 2. POC task has been implementation done with download/upload/nodata found/failed to download steps are tested and 3. OtherSales(extended warranty ) implementation is going on with PO values/withou PO values to get UnitPrice along with download and upload steps are in Progress. 4. Mr Mohan san has asked to run GRS and GRD for all centers to know the success and issue while running continueously.
|  |  | RPA Customization |  | WIP | Tested for all services dynamically for DRS, GRS and GRD are done, In GRDetails a file moving issue after uploading.
POC Task tested and validated for downloading, uploading and for no data found with email
|  |  | RPA Customization |  |  | 1. POC Tasks for all centers has been developed to download and upload 2. GRS and GRDetails tasks are completed. 3. CommunicationBoard task has been tested for SSC1, as could not find notification, we could not complete the test for all centers
|  |  | RPA Customization |  |  | 1.POC tasks tested for all centeres excluding SSC10 individually at new bot 2. Anchor element not found at JIFFY for DRS and Warranty daily tasks has been solved and it is running smoothly to download and upload.
|  |  | RPA Customization |  |  | POC Tasks are completed and tested till SSC6 and are going smooth for download and uploaded for rpa customization tasks, POC Taks are placed at scheduler Also developed code to convert purchase summary xls to csv file and uploaded successful.
|  |  | RPA Customization |  |  | Invalid data Issue during upload at SSC10 of Warranty task has been solved and updated script file also shared to Mohan san.
Dowload and upload for POC task has been tested from SSC1 to SSC10 exclusing SSC5 and SSC9 and going smooth and placed in scheduler.(newbot)
|  |  | Hayaai-Website |  |  | Learning and reviewing the Hayaai-Website
|  |  | Hayaai-Website |  |  | Learning and reviewing the Hayaai-Website in Laravel
|  |  | RPA Customization |  |  | 1. Supporting to RPA customization for Purchase details task of xls to csv conversion and uploading the same at MVS. 2. Customizing the Monthly OtherSales task is in Progress.
|  |  | RPA Customization |  |  | 1. Supported to laravel installation for web design
2. Customizing the Monthly Otherssales task is in Progress ( upto fetching data from the extended warranty is over, 3. Whereas With PO task and Without PO task are pending and it is connected task of OtherSales
|  |  | RPA Customization |  |  | 1. With PO task and Without PO task are done and it is connected task of OtherSales 2.OtherSales tasks are completed for SSC1, whereas it has to tested for all SSC as data fetching method is varying from center to centers. 3. Learning wordpress and is going.
|  |  | GSS website |  |  | Learning and Supporting GSS website editing in wordpress
|  |  | RPA Customization |  |  | Correction received for taks DRS-Weekly for all SSC and POC tasks for uploading issue at SSC10 and both corrections were rectified. Supporting to GSS website page editing.
|  |  | RPA Customization |  |  | 1.The Othersales extended warranty tasks has been completed and tested for SSCs to fetch data and converting csv and uploading success 2. RPA customization of Saw discounts is work in Progress.
|  |  | RPA Customization |  |  | 1. Saw Discount task has been completed and tested for all SSCs to get a download, csvconversion and upload are success.
2. Correction has been received for the OtherSales task and work in progress.
|  |  | RPA Customization |  |  | 1. StockOverView task has been completed and tested for three SSCs to know about downloading, csv file conversion, and uploading are success, remaining SSCs to be tested.
|  |  | RPA Customization |  |  | 1. StockOverView task has tested for all SSCs to download, CSV file conversion and uploading are success.
|  |  | RPA Customization |  |  | Return Credit Monthly task has been completed and tested in all SSCs to get downloading, CSV file conversion, uploading and file moving to backup folder and are functioning perfectly.
|  |  | RPA Customization |  |  | Storing changed password into Database is in WIP
|  |  | RPA Customization |  |  | 1. Corrections of GRS_Details tasks has been done 2. Analysing the Google forms
3. Working in Progress of Communication board
|  |  | RPA Customization |  |  | 1. Corrections of GRS_Details tasks has been done 2. Analysing the Google forms and sending email on submission done.
|  |  | RPA Customization |  |  | 1. Analysing the google excel sheet, and sending bulk emails at time is done.(50 emails) 2.Correction at GRS_Details of SSC3 has been done.
|  |  | RPA Customization |  |  | 1.Correction at GRS_Details of SSC3 was Work in Progress
|  |  | RPA Customization |  |  | 1.Correction at GRS_Details of SSC3 has been completed and tested for all SSC to get download, csv conversion and upload are success.
|  |  | RPA Customization |  |  | 1. Received errors from DRS-DAILY, Weekly and Monthly had been reviewed due to not uploading at MVS and later on issue fixed at QMVR 2.Communication board clearing task in WIP
|  |  | RPA Customization |  |  | 1. Communication board clearing task has been completed and tested for one SSC only and remaining Center to be tested 2. Correction of SawDiscount_monthly task has been fixed and tested for all SSC and running smoothly from download, csv file conversion, and uploading.
|  |  | RPA Customization |  |  | 1. Communication board clearing task has been completed and waiting communication board pending notice to test all centers
2. Working on Password management to store at Database.
|  |  | RPA Customization |  |  | 1. New issues are raised while running a communication board to pending clear notice. Hence, we may have to look new approach. 2. Checking the email from contact form and login and sigup form in Haiyaai and gss website.
|  |  | RPA Customization |  |  | 1. OtherSales corrections Received and it is work in progress
2. Communication board is work in progress.
|  |  | RPA Customization |  |  | 1. Corrections Received for Warranty and it had been completed, tested success and shared to Mohan san
2. Corrections Received for GRS-Details and it had been completed, tested success and shared to Mohan san
3. Small brief about RPA workflow, creation, execution and uplading,(python/selenium/) has been given to Sabeena san
4. Data validation support for OtherSales task has been to Prabhu with GSPN site.
|  |  | RPA Customization |  |  | Correction of ReturnCredit Task has been completed and tested in all SSCs and running smooth.
|  |  | RPA Customization |  |  | 1. Correction of POC task has been completed and tested in all SSC and running smooth. 2. CommunicationBoard task has been completed and to be tested.
|  |  | RPA Customization |  |  | 1. Communication borad task is work in progress in new approach for all SSCs.
|  |  | RPA Customization |  |  | 1. Communication beard task is completed as fresh one, whereas implementation of logg is pending.
2. Storing pwd at database is work in progress
|  |  | RPA Customization |  |  | The communication board task has been completed, log implemented and tested in all SSCs and working fine, whereas a rerun process is pending now.
|  |  | RPA Customization |  |  | The rerun processes has been implemented at Communication task and tested success.
|  |  | RPA Training |  |  | 1. Python Introduction(Version, Cmd, Idle, Pycharm)
2. Data types with example
3. Rerun process are success for the communication board, whereas yet to fine tuning is pending.
|  |  | RPA Training |  |  | 1. Continuation of Data types, Dictionary, conditional statements, looping statements (if, else, for, break,continue and pass)
|  |  | RPA Training |  |  | 1. Correction of communication task has been done and tested success.
2. Preparations for the Training
RPA Training
|  |  | RPA Training |  |  | 1. Correction of DRSDaily and Communication has been done
2. RPA Training has been handled
|  |  | RPA Training |  |  | 1. Correction of Communication board has been completed, tested in all SSCs and functioning perfect
2. RPA Training has been handled on 4th day.
RPA Training
1. One new update received to store ESG Notice texts in database, implemented, tested in all SSCs and running smoothly.
2. RPA Training has been handled on 5th day.
|  |  | RPA Training |  |  | 1. One update is received for Goods Receiving Details task and completed, tested in all SSCs.
2. RPA Training has been handled on 5th day.

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold