## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | RPA SAMSUNG | Correction Received for DRS-Monthly, SAW Discount Monthly and ReturnCredit Monthly tasks | 100% | Completed |  | Pending
2 | 2020-10-01 | RPA SONY | A 7 files are uploaded with customization in single approach for Scheduling Reports tasks | 70% | WIP |  | Completed
3 | 2020-10-05 | RPA SAMSUNG | 1. DRS-Weekly correction received and completed | 100% | Completed |  | Hold
|  |  | 2. Return Credit Correction received and completed | 100% | Completed
4 | 2020-10-05 | RPA SONY | Daily Task of Scheduling Report has been completed for download and upload (11 files except one is having upload issue which under progress by Mohan san) | 100% | Completed
5 | 2020-10-06 | RPA SAMSUNG | 1. DRS-WeeKly task of SSC8 , Correction has been done | 100% | Completed
|  |  | 2. DRS-DAILY task of SSC11, Correction has been done | 100% | Completed
6 | 2020-10-06 | RPA SONY | 1. SchedulingReport daiky has been completed | 100% | Completed
|  |  | 2. Scheduling Report Monthly task has been completed | 100% | Completed
7 | 2020-10-07 | RPA Sony | For Sony_Daily_SchedulingReport task,
|  |  | 1. method created to delete all specific pattern files before downloading the Sony daily scheduling report | 100% | Completed
2. method created to delete all specific pattern files before creating CSV files to upload from temp folder for the task Sony daily scheduling report
8 | 2020-10-08 | RPA Sony | Correction at Sony_Daily_SchedulingReport task has been done related to unicode error | 100% | Completed
9 | 2020-10-09 | RPA Sony | Customization work is in progress for Sony daily task of scheduling report | 60% | WIP
10 | 2020-10-12 | RPA Sony | 1. Customization of Sony Schedule Report of Daily task has been completed | 100% | Completed | Updated codes has been shared
|  |  | 2. Customization of Sony Schedule Report of Monthly task is work in progress | 60% | WIP
11 | 2020-10-13 | RPA Sony | 1. Customization of Sony Schedule Report of Daily task has been completed (with enhanced corrections) | 100% | Completed
|  |  | 2. Code included for SchedulingReport to give manual captcha | 100% | Completed
12 | 2020-10-13 | RLOGIC DEMO | 3. RPA Demo prepared and tested for the RLOGIC | 100% | Completed
13 | 2020-10-14 | RLOGIC DEMO | 1. Supported/Prepared for Demo Presentation | 100% | Completed
14 | 2020-10-14 | RPA Sony | 2. Correction work supported to Daily task of schedule_report for record count, and upload issue | 80% | WIP
15 | 2020-10-15 | RPA Sony | 1. Correction work supported to Sony task of scheduling report for file movement to backup folder and record count issue are fixed for the daily and monthly tasks | 100% | Completed
16 | 2020-10-15 | RLOGIC | 2. A set up has been established and GL,PL and RPA management files are copied(supported for installation and testing) and tested for the purchase summary from GSPN at RLOGIC system | 100% | Completed
17 | 2020-10-16 | RPA SAMSUNG | 1. Correction supported to the communication board task to clear pending notices | 90% | WIP
18 | 2020-10-16 | RPA SAMSUNG | 2 Correction of Password Management task is pending | 70% | WIP
19 | 2020-10-19 | RLOGIC | 1. Downloading DRS task done | 100% | Completed
|  |  | 2. Downloading InvoicePDF task done (downloading pdf, pdf to csv) | 100% | Completed
20 | 2020-10-19 | RPA SAMSUNG | 1. Correction of Password Management has done. | 100% | Completed
21 | 2020-10-20 | RPA Sony | 1. Went to the office to support the System Admin towards formatting, windows 7 installation and office 365 softwares are installed at Oldbot | 90% | WIP
|  |  | 2. and office365 has been installed at newbot | 100% | Completed
22 | 2020-10-20 | RLOGIC | 3. Warranty task has been done towards download | 100% | Completed
21 | 2020-10-21 | RPA SAMSUNG | 1. Manual date input has been implemented in warranty task | 100% | Completed
22 | 2020-10-21 | RPA SAMSUNG | 2. Corrections work supported for the Password management has been done | 100% | Completed
23 | 2020-10-21 | RPA SONY | 3. Correction work is in Progress for the scheduling reports(11 files task) | 60% | WIP
24 | 2020-10-22 | RPA SONY | 1. Correction has been completed for Sony Daily Scheduling Report (), | 100% | Completed | Code shared
2, failed files are to moved backup folder
3. records count correction and testing)
4. manual input date method implementation
25 | 2020-10-23 |  | Leave | Leave
26 | 2020-10-27 | RPA SONY | The below pointes are fixed at schedulingreport monthly task: 1. records counts are corrected, 2. failed files will be moved to backup, 3. success files also be moved to backup, 4. 100000 passwords are generated and stored as valid and invalid pwd at csv for password management, 5. manual date input logic can not be implemented at monthly task as it contains only previous month folder and others are daily folders(noticed to mohan san) | 100% | Completed
27 | 2020-10-27 | RLOGIC | 1. Created a report of Profit and Loss of Rlogic task | 100% | Completed
28 | 2020-10-27 | RPA SONY | 2. For schedulingreport task, uploading issue at MVS site, and it is in Progress | 90% | WIP
29 | 2020-10-28 | RPA SONY | 1. Uploading issue was at SchedulingReport daily task due to Invalid data presents in the csv file and it has been fixed | 100% | Completed
30 | 2020-10-28 | RPA SAMSUNG | 2. Uploading issue was at Warranty task due to special characters (tick mark symbol) presents and it has been fixed | 100% | Completed
31 | 2020-10-28 | RPA SAMSUNG | 3.Second approach has been implemented at Communicationboard task | 90% | WIP
32 | 2020-10-29 | RLOGIC | 1. Setup, Established and tested to give a RPA Management template demo towards RLOGIC, In addition GL, and PL and executed a predemo with Rahman san | 100% | Completed
33 | 2020-10-30 | RPA SAMSUNG | 1. Second Approach has been implemented at Communicationboard task, notice titles can be stored in database once all notices are cleared, tested in all SSCs and running smoothly | 100% | Completed
34 | 2020-10-30 | RLOGIC | 2. R & D has been done to convert a project files to exec and create a trial version | 50% | WIP

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | RPA SONY | Conversion issue during CSV files creation at Sony Daily SchedulingReport task has been fixed, tested and running smoothly for all 11 files | 100% | Completed
2 | 2020-11-02 | RPA SAMSUNG | Upload issue at RETURNCREDIT MONTHLY task has been fixed, tested and running smoothly | 100% | Completed
3 | 2020-11-02 | RPA SAMSUNG | Conversion issue during CSV files creation at SAWDISCOUNT Monthly task is going on | 80% | WIP
4 | 2020-11-03 | RPA SAMSUNG | Conversion issue has been fixed and tested in all SSCs for the task of SawDiscountMonthly and running smoothly from to download to csv and uploading success | 100% | Completed
5 | 2020-11-03 | RPA RLOGIC | 1. Prepared and supported for RLOGIC client demo GL/PL/RPA Management | 100% | Completed
6 | 2020-11-04 | RPA RLOGIC | 1. Extened warranty task has been established and tested for the given user and running smoothly to download and csv file creation etc | 100% | Completed
7 | 2020-11-04 | RPA SAMSUNG | 2. Correction at Warranty task has been fixed and tested in all SSCs, running smoothly from download to upload | 100% | Completed
8 | 2020-11-04 | RPA SONY | Tested and supported for Sony RPA at Oldbot after installation of sony certificate, still date fields are not working properly for RPSI Enquiry, Inboundlist, Outboundlist etc | 80% | WIP
9 | 2020-11-05 | RPA RLOGIC | 1. Log has been implemented at DRS download | 100% | Completed |  | Status
|  |  | 2. Converted Python script to Exe(Trial Version) for the DRS download and tested and running smoothly | 100% | Completed |  | WIP
|  |  | 3. Converted Python script to Exe (Trial Version) for RPA Management, tested and running smoothly | 100% | Completed |  | Pending
|  |  | 4. Sending email with attachments has been done for RPA Management template | 100% | Completed |  | Completed
10 | 2020-11-06 | RLOGIC | 1. Trial version Exe has been tested and functioning as expected for RPA Management Template | 100% | Completed |  | Hold
|  |  | 2. Log has been implemented to Warranty, InVoicePDF etc | 100% | Completed
|  |  | 3. Communicationboard task is implemented, tested and running smoothly | 100% | Completed
11 | 2020-11-09 | RLOGIC | 1. Log has been implemented at RPA Management template and converted as Exec file and placed at Scheduler to run daily 6:00 AM | 100% | Completed
|  |  | 2. Communication board task has been converted as Executive file and placed in Scheduler to run daily at 18:00 | 100% | Completed
12 | 2020-11-10 | SONY RPA | 1. Correction Received due to conversion issue at Sony Daily of scheduling report task and same had been fixed, tested, running smoothly to download,conversion and uploading | 100% | Completed
|  |  | 2. Supported to fix IE issue to ap-new-sis site at Oldbot with Mr Amit and Mr Oniel and issue fixed, manually site can be accessed, whereas, dynamically IE is not launching this | 60% | WIP
13 | 2020-11-10 | RLOGIC | 3. InvoiceUpdatePDF task are fine tunned to convert EXEC | 100% | Completed
14 | 2020-11-11 | RPA SONY | Supported to SONY task to luanch IE and it has been fixed at Oldbot, whereas we could not run the script to download and convertsion due to internet security and it is work in progress | 60% | WIP
15 | 2020-11-12 | RPA SONY | 1. Sony daily of OutboundList has been to download and CSV conversion at OldBot with IE11 | 100% | Completed
16 | 2020-11-12 | RLOGIC RPA | 2. While opening the Management model report of xlsx file, we have made the Management Sheet to active | 100% | Completed
|  |  | 3.In GL, InvoiceUpdate sheet has been created from the RLOGIC sheet received | 100% | Completed
17 | 2020-11-13 | RPA RLOGIC | 1. Downloaded DRS and Warranty Files from GSPN to generate Calls count report etc for October-2020 | 100% | Completed
|  |  | 2. Downloaded InvoiceUpdatePDF to generate InvoiceUpdate summary report with client provided data | 100% | Completed
|  |  | 3.Extended warranty report generated from the GSPN data | 100% | Completed
|  |  | 4. RPA Management Model report generated | 100% | Completed
|  |  | 5.Tested with Mr Rahaman to verify the data | 100% | Completed
18 | 2020-11-16 | RPA RLOGIC | 1. Downloading Warranty and DRS, generated to Calls count report | 100% | Completed
|  |  | 2. Converted warranty xls to CSV using pure python | 100% | Completed
|  |  | 3. Converted DRS xls to CSV using pure python is work in Progress | 60% | WIP
19 | 2020-11-17 | RPA RLOGIC | 1. Converting DRS to CSV using pure python has been completed | 100% | Completed
|  |  | 2. Creating WRTY_DRS.xlsx of merging (both warranty and DRS based on asc claim no) | 100% | Completed
20 | 2020-11-17 | RPA SONY | 1. Converting xls to CSV for SendRepairedReport1605588144058700.xls (from Mohan san) | 100% | Completed
21 | 2020-11-18 | RPA RLOGIC | 1. Created RPA Management model reports based the P and L reports | 100% | Completed
|  |  | 2. Code has been implemented to convert as Exec for General Ledger | 100% | Completed
22 | 2020-11-19 | RPA RLOGIC | 1. Prepared and Supported to RLOGIC tasks
2. discussion with Rahman san and Mamatha san for Rlogic live
|  |  | 3. Working on new logic gave by Rahman san for DRS, Warranty and Invoice Update etc | 60% | WIP
23 | 2020-11-20 | RPA RLOGIC | Creating DRS_WRNTY_InvoiceUpdate merge task is work in progress to get callwisedata report and callscount reports | 80% | WIP
24 | 2020-11-23 | RPA RLOGIC | Creating DRS_WRTY_INVOICE_SAW and merging based on some conditions (Work in Progress), whereas (Extracted data for the DRS, WRTY, InvoiceUpdate and SAW) | 80% | WIP
25 | 2020-11-24 | RPA RLOGIC | 1. Merging DRS_INV_SAW with WRT based on ClaimNo has been done for P & L | 100% | Completed
|  |  | 2. CallsCount Reports has been generated | 100% | Completed
26 | 2020-11-25 | RPA RLOGIC | Supporting to P and L process till 12:30 and since 12:30 no electric power due to heavy rain with wind | 100% | WIP
27 | 2020-11-26 | RPA RLOGIC | Due to Cyclone, no power supply and it has been restored at 19:30
28 | 2020-11-27 | RPA RLOGIC | Supporting to P and L process (Generating WRTY_DRS_INV_SAW_merging report and CallsCount Report) with updates (correction also corrected in results) | 100% | Completed
29 | 2020-11-29 | RPA RLOGIC | Supporting to P and L process (Generating WRTY_DRS_INV_SAW_merging report and CallsCount Report) with updates (correction also corrected in results) | 90% | WIP | supported on Sunday
30 | 2020-11-30 | RPA RLOGIC | Suppoted to RLOGIC for P&L | 100% | Completed
31 | 2020-11-30 | RPA GSPN | Corrections received for Warranty task and it has been completed from download to upload process | 100% | Completed

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | RLOGIC RPA | RPA Management model reports has been generated for P & L along with Charts, whereas Correcting data label and adding KPI details are pending | 90% | WIP
2 | 2020-12-02 | RLOGIC RPA | RPA Management model report has been generated with all updates (table and charts) and placed it on scheduler to trigger the task and sent email | 100% | Completed
3 | 2020-12-02 | RPA SONY | Tried to run sony task at old bot is in under study | 30% | WIP
4 | 2020-12-03 | RLOGIC RPA | RPA Management model report has been generated based on Final P&L updates (table and charts) and placed it on scheduler to trigger the task and sent email | 100% | Completed
5 | 2020-12-03 | RPA SONY | Research and Development of SQLITE3 database to support SONY | 60% | WIP
6 | 2020-12-04 | RPA SONY | Installation of MySQL, and establishment, testing also done using Python at Oldbot, whereas migration from mssql to mysql is pending | 60% | WIP
7 | 2020-12-07 | RPA SONY | Working on InboundList and OutBoundList task to download | 40% | WIP
and Upload, other tasks are pending like(Part, stock, RPSI)
Status
WIP
Pending
Completed
Hold