## Balraj
No | Date | Application | Task | % of completion | Status
Status
WIP
Pending
Completed
Hold
1 | 2020-09-01 | RPA Sony | SchedulingReport |  |  | 1. Sony RPA task SchedulingReport is in work progress.
|  |  | StockOverView |  |  | 2. Corrections are received for the GSPN tasks named as Stockoverview for data fetching issue and SawDiscount for invalid data
|  |  | SawDiscount |  |  | 3. SawDiscount has been completed and tested in all SSCs, whereas Stockoverview is pending due to GSPN site issue.
2 | 2020-09-02 | RPA Samsung | SawDiscount and GRS-Details |  |  | 1. Corrections are completed, tested and success for the tasks of SawDiscount and GRS-Detatils
|  | RPASony | Scheduling Report |  |  | 2. Downloading the all files for the SchedulingReport task has been completed excluding alert click., whereas Alert click OK is pending.
3 | 2020-09-03 | RPASony | For NEWAPSIS tasks |  |  | 1. Development has been done for Captcha verification error and for Username/password verification error and tested and success
4 | 2020-09-04 | RPASony | For www.sonyb2b.com |  |  | 1. Regarding OK button click, using thread concept for scheduling_report task has been completed success and downloading files
2.Tried to install VPN with windows updates at the oldbot, but it is failed, wrote an email.
5 | 2020-09-07 | RPASony | ClaimInvoice(Pdf&Excel) |  |  | 1. Downloading InvoicePDF and Excel files has been done for the task of InvoicePDF and InvoiceExcel
6 | 2020-09-08 | RPASony | RPASony |  |  | 1. Supporting to system admin to windows update and VPN issue
2. Merging xlsx files based on file name for shedulingreport task is work in progress
7 | 2020-09-09 | RPAGSPN | Warranty |  |  | Date search is fixed at warranty task and tested and it is success
|  | RPAGSPN | Communications Board |  |  | 1. Corrections of communication board task has been completed and tested in all SSCs and running smoothly
|  | RPASONY | Browser Issue |  |  | 2. R and D on IETAB in chrome is going on
8 | 2020-09-10 | RPASony | Scheduling Report |  |  | 1. Merging the IN_Daily_OS_Reservation csv files are done
2. Merging the IN_daily_UnRepaipairset_NP csv files are done
9 | 2020-09-11 | RPASony | Scheduling Report |  |  | 1. Customization work is in progress for the tasks of schedulinReport for the monthly and daily
|  |  | B2B extended warranty |  |  | 2. B2B extended warranty is in progress from the afternoon
10 | 2020-09-14 | RPASony | DatewiseSalesreport |  |  | 1. Task of Datewise sales report has been done to download and it is fine in chrome
|  |  | SockAvailable |  |  | 2. Task of Stock Available report has been done to download and it is fine in chrome
11 | 2020-09-15 | RPASony | DateWiseSalesreport |  |  | 1. Uploading and customisation has been done for the task datewisesalesreport
|  |  | StockAvailable |  |  | 2. Uploading and customisation has been done for the task stockavailablereport
12 | 2020-09-16 | RPASony | InvoicePDF and Excel download |  |  | 1. Partial Customization has been done for the task of InvoicePdf_excel to download Pdf and Excel
13 | 2020-09-17 | RPASony | B2B extended warranty |  |  | 1. Corrections received for the sony b2b extended warranty task to autologin the paloalto global network(firewall) is in progress.
14 | 2020-09-18 | RPA GSPN | Warranty |  |  | 1. Corrections received for the task of warranty, it has been fixed and tested in all SSCs and running smoothly
2. Date Input method is work in progress for SONY and GSPN for backlog date
15 | 2020-09-21 | RPA GSPN | DRS-Daily, DRS-Monthly, Warranty_daily, GRS-Daily, GRS_details_daily and |  |  | 1. Creation of datefile.txt for inputing the date to the DRS-Daily, DRS-Monthly, Warranty_daily, GRS-Daily, GRS_details_daily and POC daily tasks has been completed and tested and running smoothly
POC daily
16 | 2020-09-22 | RPA GSPN | DRS-Weekly and OtherSales |  |  | 1. Creation of datefile.txt for inputing the date to the DRS-Weekly, and OtherSales extended warranty tasks has been completed and tested and running smoothly
17 | 2020-09-23 | RPA GSPN | SawDiscount |  |  | 1. Creation of datefile.txt for inputing the date to the SAWDiscount task has been completed, tested and running smoothly
|  | RPA SONY | RPA SONY |  |  | 2. SONY Upload alone has been done for the below mentioned tasks 113.Daily Abandon 114.Daily Accumulated_KPI_Report 115.Daily_ASCPartsUsed 116.Daily_Claim 117.Daily_Delivered
18 | 2020-09-24 | RPA SONY | RPA SONY |  |  | 2. SONY Upload alone has been done for the below mentioned tasks 112 .ASC Invoice Data 118.Daily_OS_Reservation 119.Daily_Receiveset 137.Monthly_SOMC_Claim
19 | 2020-09-25 | RPA SONY | RPA SONY |  |  | 1. Sony upload alone has been done for the below mentioned tasks 120.Daily_OS_specialtreatment
121.Daily_Acct Stmt
122.Daily_RepairsetSet_NP
123.Daily_UnDeliveredSet # content issue @column size to be increased
124.Daily_UnRepaipairset_NP # content issue @column size to be increased
2. R and D has been done for chrome to select automatically to avoid popup based on Mohan san suggestions
20 | 2020-09-28 | RPA GSPN | CommunicationBoard |  |  | 1.Corrections Received for the Communication Board tasks and it is work in progress
20 | 2020-09-28 | RPA Sony | RPA Sony |  |  | 2. Uploading the monthly tasks are pending for the below mentioned tasks
125.Monthly Reservation
135.Monthly Repairset
136.Monthly Abandon
21 | 2020-09-29 | RPA Samsung | DRS-Daily(SSC11) | 100% | Completed | Correction Received for DRS-Daily of SSC11 due to encoding error during CSV file creation, rectified, tested and running smoothly

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-08-03 | SONIA | Implement Product key in Sonia Application | 100% | Completed
2 | 2020-08-03 | VASTU | Master Page start working | 10 | WIP
3 | 2020-08-04 | SONIA | Issue "ImeHandler" working in Soina Project | 50 | WIP
4 | 2020-08-04 | VASTU | Master Page | 20 | WIP
5 | 2020-08-05 | SONIA | Issue "ImeHandler" fixed in Soina Project | 50 | WIP
6 | 2020-08-05 | VASTU | Master Page | 30 | WIP
7 | 2020-08-06 | VASTU | Master Page | 40 | WIP
8 | 2020-08-07 | VASTU | Master Page | 50 | WIP
9 | 2020-08-10 | VASTU | Master Page | 60 | WIP
10 | 2020-08-11 | VASTU | Master Page | 75 | WIP
11 | 2020-08-12 | VASTU | Master Page | 100 | Completed
12 | 2020-08-13 | VASTU | Authorization,Session and Role | 100 | Completed
13 | 2020-08-13 | VASTU | Source Code Merge and Deployment | 50 | WIP
14 | 2020-08-14 | VASTU | Source Code Merge, Deployment and Bug fixing | 100 | Completed
15 | 2020-08-17 | VASTU | Testing Issues Fix | 100 | Completed
16 | 2020-08-18 | VASTU | Testing Issues Fix | 100 | Completed
17 | 2020-08-19 | VASTU | Testing Issues Fix | 100 | Completed
18 | 2020-08-20 | VASTU | Testing Issues Fix | 100 | Completed
19 | 2020-08-21 | VASTU | Testing Issues Fix | 100 | Completed
20 | 2020-08-24 | VASTU | Testing Issues Fix, Vastu Master Log | 100 | Completed
21 | 2020-08-25 | VASTU | Testing Issues Fix, Vastu Master Log | 100 | Completed
22 | 2020-08-26 | VASTU | Testing Issues Fix, Vastu Master Log | 100 | Completed
23 | 2020-08-27 | VASTU | Testing Issues Fix | 100 | Completed
24 | 2020-08-28 | VASTU | Testing Issues Fix | 100 | Completed
25 | 2020-08-31 | VASTU | Testing Issues Fix | 100 | Completed
26 | 2020-09-01 | VASTU | Testing Issues Fix | 100 | Completed
27 | 2020-09-02 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
28 | 2020-09-03 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
29 | 2020-09-04 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
30 | 2020-09-07 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
31 | 2020-09-08 | VASTU | Testing Issues Fix | 100 | Completed
32 | 2020-09-08 | SONIA | MrMax Testing and fixing Issue | 100 | Completed
33 | 2020-09-08 | QMVAR | SAW Discount issue looking | 100 | Completed
34 | 2020-09-09 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
35 | 2020-09-10 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
36 | 2020-09-14 | SONIA | Homax Testing and fixing Issue | 100 | Completed
37 | 2020-09-14 | QMVAR | Sony upload and Export KT from Mohan San | 100 | Completed
38 | 2020-09-15 | SONIA | Testing and fixing Issue | 100 | Completed
39 | 2020-09-16 | SONIA | Testing and fixing Issue | 100 | Completed
40 | 2020-09-17 | SONIA | Testing and fixing Issue | 100 | Completed
41 | 2020-09-18 | SONIA | Testing and fixing Issue | 100 | Completed
42 | 2020-09-21 | VASTU | Testing Issues Fix and New enhancement | 50 | WIP
43 | 2020-09-22 | VASTU | Testing Issues Fix and New enhancement | 100 | Completed
44 | 2020-09-23 | QMVAR | DRS Count - Saw Discount with out discount | 25 | WIP
45 | 2020-09-24 | QMVAR | DRS Count - Saw Discount with out discount | 65 | WIP
46 | 2020-09-25 | QMVAR | DRS Count - Saw Discount with out discount | 100 | Completed
47 | 2020-09-26 | SONIA | Testing and fixing Issue | 50 | WIP
48 | 2020-09-27 | SONIA | Testing and fixing Issue | 100 | Completed

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | QMVAr-RPA | Purchase Summary issue on date | 100% | Completed | Corrected the date logic and tested
2 | 2020-09-02 | Hayaai-B2B | Working on B2B stored procedure in creating the company | 80% | WIP
3 | 2020-09-03 | HAYAAI | Service Request -B2B issue tracker issues resolving | 40% | WIP
4 | 2020-09-04 | Sony-QMVAR | RMS MVS upload testing | 80% | WIP
5 | 2020-09-07 | Sony-QMVAR | RMS Invoice captcha integration with GOOGLE API | 60% | WIP
6 | 2020-09-08 | QMVAR-PR summary five days | Rahman San had given this task for credit info,had completed | 100% | Completed
7 | 2020-09-09 | HAYAAI-B2B | Trying to resolve B2B issues from issue tracke | 40% | WIP
8 | 2020-09-10 | HAYAAI-B2B | Trying to complete issues from issue tracker | 60% | WIP
9 | 2020-09-11 | QMVAR-Sony | RMS invoice captcha issues,relogin with recaptcha,error msg for 20 mins | 80% | WIP | Given code to Mohan sir
10 | 2020-09-14 | Hayaai-B2B | B2B-New api for product type addition | 60% | WIP
11 | 2020-09-15 | Hayaai-B2B | Product category api,IMEI check new API are developed | 100% | Completed
12 | 2020-09-16 | Hayaai-B2B | B2B issues from issue tracker | 100% | Completed
13 | 2020-09-17 | HAYAAI-B2B | Reports corrections and signup corrections | 70% | WIP
14 | 2020-09-18 | HAYAAI-B2B | signup corrections and table corrections | 80% | WIP
15 | 2020-09-19 | HAYAAI-B2B | Search errors in Service Request and Jib correction | 100% | Completed
16 | 2020-09-21 | HAYAAI-B2C | Issue description passing to Jobs failure | 70% | WIP
17 | 2020-09-22 | HAYAAI-B2B and B2C | Few corrections in B2B APP and flow on Pick Delivery change for B2C reviewing | 70% | WIP
18 | 2020-09-23 | QMVAR | DRS Count - Saw Discount with out discount | 100% | Completed
Warranty Status to be saved in Add Devices
19 | 2020-09-24 | HAYAAI-B2B | Pickup delivery new update customer info passing to Job | 100% | Completed
|  |  | New Push Notification while technician starting for Job | 60% | WIP
20 | 2020-09-25 | HAYAAI-QMVAR | B2B- Testing | 100% | Completed
|  |  | New functionality adding new API for technician tracking | 100% | Completed
|  |  | Pickup time correction as it was not stored correctly | 100% | Completed
21 | 2020-09-28 | HAYAAI-B2B | Issue corrections from issue tracker | 50% | WIP

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | VastuShastra & ISMI | 1) Mobile view - issue 2) ISMI Document Translation | 2) 60% | WIP
2 | 2020-09-02 | VastuShastra & ISMI | 1) Checked for Nav bar and Search vastu page fixed for Mobile view 2) ISMI Document Translation | 1)10% 2) 100% | Completed
3 | 2020-09-03 | VastuShastra | 1) Home,Search vastu,home vastu page fixed for Mobile view 2) working in Vastu tips and vastu report page | 2) 40% | WIP
4 | 2020-09-04 | VastuShastra | Admin panel back to application button fixed and working in Feedback and vastu report page | 40% | WIP
5 | 2020-09-07 | VastuShastra | mobile view in progress. | 75% | WIP
6 | 2020-09-08 | VastuShastra | mobile view in progress and issues are cleared in vastu. | 85% | WIP
7 | 2020-09-09 | VastuShastra | mobile view Login page background image need to fix and User manual created for Sonia | 100% | Completed
8 | 2020-09-10 | VastuShastra | mobile view feedback page fixed | 100% | WIP
9 | 2020-09-11 | VastuShastra | Checking for mobile view alignment issues | 70% | WIP
10 | 2020-09-14 | VastuShastra | Checking for mobile view alignment issues | 75% | WIP
11 | 2020-09-15 | VastuShastra | Checking for mobile view alignment issues | 80% | WIP
12 | 2020-09-16 | VastuShastra | Checking for mobile view alignment issues.Fixed few issues. | 85% | WIP
13 | 2020-09-17 | VastuShastra | mobile view issues closed | 95% | WIP
14 | 2020-09-18 | VastuShastra | All Issues fixed | 100% | Completed
15 | 2020-09-21 | VastuShastra , QMVAR | Issues fixed and QMVAR - ACCT_STMT in progress | 60% | WIP
16 | 2020-09-22 | QMVAR, Hayaai app | 1) QMVAR - ACCT_STMT 2)QMVAR - Daily_repairsetSetNP in progress. 3)Hayaai app screen designed | 1) 100% , 2) 60% , 3) 100% | WIP
17 | 2020-09-23 | QMVAR | QMVAR - Daily_repairsetSetNP | 100% | Completed
18 | 2020-09-24 | HAYAAI | WebsiteTranslation | 35% | WIP
19 | 2020-09-25 | HAYAAI | WebsiteTranslation | 70% | WIP
20 | 2020-09-28 | HAYAAI | WebsiteTranslation | 100% | Completed
20 | 2020-09-29 | HAYAAI | Login , nMVAR started | 30% | WIP
21 | 2020-09-30 | HAYAAI | Login issue only cleared , working in nMVAR | 50% | WIP
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | Soniya | DB Checking for Best Denki - best_mnt_vdr,best_mnt_shop | 100% | Completed
2 | 2020-09-02 | Soniya | DB Checking for Best Denki - best_mnt_cat,best_mnt_menu | 100% | Completed
3 | 2020-09-03 | Soniya | DB Checking for Best Denki - best_close,best_close_return | 50% | Completed
4 | 2020-09-04 | Soniya | DB Checking for Best Denki - best_err_mnt,best_exp_SB02 | 100% | Completed
5 | 2020-09-05 | Sat & Sun
6 | 2020-08-06
7 | 2020-09-07 | Soniya | DB Checking for Best Denki - best_exp_SB03,best_input | 100% | Completed
8 | 2020-09-08 | Soniya | DB Checking for Best Denki - best_ivc_close,best_ivc_close_return | 100% | Completed
9 | 2020-09-09 | Soniya | DB Checking for Best Denki - best_ivc_err_mnt,best_ivc_export | 100% | Completed
10 | 2020-09-10 | Soniya | DB Checking for Best Denki - best_ivc_import,best_ivc_input | 100% | Completed
11 | 2020-09-11 | Soniya | DB Checking for Best Denki - best_ivc_menu,best_ivc_report | 100% | Completed
12 | 2020-09-12 | Sat & Sun
13 | 2020-09-13
14 | 2020-09-14 | Soniya | DB Checking for Best Denki - best_ivc_search,best_report | 100% | Completed
15 | 2020-09-15 | Soniya | DB Checking for Best Denki - best_search,best_search_setup | 100% | Completed
16 | 2020-09-16 | Soniya | DB Checking for Best Denki - best_wrn_new | 100% | Completed
17 | 2020-09-17 | Soniya | DB Checking for Best Denki - best_yamada_import | 100% | Completed
18 | 2020-09-18 | Soniya | DB Checking for Best Denki 2 - best_intl_search | 100% | Completed
19 | 2020-09-19 | Sat & Sun
20 | 2020-09-20
21 | 2020-09-21 | QMVAR | QMVAR Monthly_Adandon(File Upload And Export) | 100% | Completed
22 | 2020-09-22 | Vastu | Vastu - Fixed Suman san raised issues | 100% | Completed
23 | 2020-09-23 | Vastu | Vastu - Fixed Suman san raised issues | 100% | Completed
24 | 2020-09-24 | Vastu | Vastu - Fixed Suman san raised issues | 100% | Completed
25 | 2020-09-25 | nQGCare | Analyzed nQGCare | 100% | Wip

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | Soniya | MrMAX_Mtr, MRMax Wrn | 100% | Completed
2 | 2020-09-02 | Soniya, selenium log file | MRMax Import | 100% | Completed
3 | 2020-09-03 | Vastu, selenium log file | Vastu pages design, selenium log file count | 50% | Wip
4 | 2020-09-04 | Vastu, selenium log file | Vastu Master pages design, selenium log file count | 100% | Completed
5 | 2020-09-05 | Sat & Sun
6 | 2020-08-06
7 | 2020-09-07 | Selenium log file Verifications | Selenium log file count , and Manually Upload Warranty All SSC'S (AUG,SEP(QMVAR)) | 100% | Completed
8 | 2020-09-08 | Selenium log file Verifications | Selenium log file count , and Manually Upload Warranty All SSC'S(JULY(QMVAR)) | 100% | Completed
9 | 2020-09-09 | Selenium log file Verifications, Soniya Project | Selenium log file count , and Invoice Update OOW, IW,EXW, record verification, Kuroganeya_INQUIRY | 100% | Completed
10 | 2020-09-10 | Selenium log file Verifications, Soniya Project | Selenium log file count , Soniya Project (Kuroganeya) | 100% | Completed
11 | 2020-09-11 | Selenium log file Verifications, Soniya Project | Selenium log file count , Soniya Project (Kuroganeya_REP) | 100% | Completed
12 | 2020-09-12 | Sat & Sun
13 | 2020-09-13
14 | 2020-09-14 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (STREAM) | 100% | Completed
15 | 2020-09-15 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (S5, best_ivc_close_return) | 100% | Completed
16 | 2020-09-16 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (admin) | 100% | Completed
17 | 2020-09-17 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (BIG_Input) | 100% | Completed
18 | 2020-09-18 | Selenium log file Verifications, Soniya Project Migration | Selenium log file count , Soniya Project (Homac_Import), Warranty Issue check(SSC1) | 100% | Completed
19 | 2020-09-19 | Sat & Sun
20 | 2020-09-20
21 | 2020-09-21 | Selenium log file Verifications, QMVAR | Selenium log file count , QMVAR Monthly_Reservationvation(File Upload And Export) | 100% | Completed
22 | 2020-09-22 | Selenium log file Verifications, QMVAR | Selenium log file count , QMVAR Monthly_Repairset(File Upload And Export) | 50% | Wip
23 | 2020-09-23 | QMVAR | QMVAR Monthly_Repairset(File Upload And Export) | 100% | Completed
24 | 2020-09-24 | Selenium log file Verifications, QMVAR | Selenium log file count , QMVAR SID1 Testing(File Upload And Export) | 100% | Completed
25 | 2020-09-25 | Selenium log file Verifications, Soniya | Selenium log file count , Soniya(nMVAR_Ai) | 50% | Wip
26 | 2020-09-28 | Selenium log file Verifications, Soniya | Selenium log file count , Soniya(nMVAR_Ai) | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | Soniya | Mr_Max Migration |  | completed
2 | 2020-09-02 | Vastu & Soniya | vastu Mobile and Mr_Max (Import) Migration |  | completed & WIP
3 | 2020-09-03 | Vastu | vastu Mobile |  | WIP
4 | 2020-09-04 | Vastu | vastu Mobile |  | WIP
5 | 2020-09-05 | SAT & SUN DAY
6 | 2020-09-06
7 | 2020-09-07 | Vastu | vastu Mobile |  | WIP
8 | 2020-09-08 | Vastu | vastu Mobile |  | WIP
9 | 2020-09-09 | Vastu | vastu Mobile and Kuroganeya Migration |  | WIP
10 | 2020-09-10 | soniya | Kuroganeya Migration |  | WIP
11 | 2020-09-11 | soniya | Kuroganeya Migration |  | completed
12 | 2020-09-12 | SAT & SUN DAY
13 | 2020-09-13
14 | 2020-09-14 | soniya | All denka Migration |  | completed
15 | 2020-09-15 | Vastu | vastu mobile |  | completed
16 | 2020-09-16 | soniya | BIC Migration |  | WIP
17 | 2020-09-17 | soniya | BIC Migration |  | completed
18 | 2020-09-18 | vastu | issue fixing |  | completed
19 | 2020-09-19 | SAT & SUN DAY
20 | 2020-09-20
21 | 2020-09-21 | QMVAR | daily_UnRepaipairset_NP |  | completed
22 | 2020-09-22 | QMVAR | daily_UndeliveredSet |  | completed
23 | 2020-09-23 | QMVAR | Daily_OS_specialtreatment |  | completed
24 | 2020-09-24 | Soniya | nQGcare_ipad_bat Migration |  | completed
25 | 2020-09-25 | Soniya | nMvar Migration |  | WIP
28 | 2020-09-28 | Soniya | nMvar_clct |  | WIP
29 | 2020-09-29 | Soniya | nMvar_clct,nMVAR_BKlog_bat |  | completed
30 | 2020-09-30 | Soniya | nMvar_MNT |  | completed
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Nirmal
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-09-01 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
2 | 2020-09-02 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
3 | 2020-09-03 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
4 | 2020-09-04 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
5 | 2020-09-07 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
6 | 2020-09-08 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
7 | 2020-09-09 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
8 | 2020-09-10 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
9 | 2020-09-11 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
10 | 2020-09-14 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
11 | 2020-09-15 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
12 | 2020-09-16 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
13 | 2020-09-17 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
14 | 2020-09-18 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, B2B, Vastu and Hayaai site | 100% | Completed
15 | 2020-09-21 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, Vastu and Hayaai site | 100% | Completed
16 | 2020-09-22 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, Vastu and Hayaai site | 100% | Completed
17 | 2020-09-23 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, Vastu and Hayaai site | 100% | Completed
18 | 2020-09-24 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, Vastu and Hayaai site | 100% | Completed
19 | 2020-09-25 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, Vastu and Hayaai site | 100% | Completed
20 | 2020-09-28 | B2C & Hayaai | Sanity testing on B2C app, QMVAR site, GSS site and Hayaai site & Regression testing on B2C, Vastu and Hayaai site | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Balaji
No | Date | Application | Task | % of completion | Status | Comments
1 | 07/09/2020 | Hayaai | Overview |  | Completed
2 | 08/09/2020 | Hayaai | Overview |  | Completed
3 | 09/09/2020 | Hayaai | Overview |  | Completed
4 | 10/09/2020 | Hayaai | Overview |  | Completed
5 | 11/09/2020 | Hayaai | Overview | 100% | Completed
6 | 12/09/2020 | WeekEnd
7 | 13/09/2020 | WeekEnd
8 | 14/09/2020 | QMVAR | SID |  | Completed
9 | 15/09/2020 | QMVAR | SID |  | Completed
10 | 16/09/2020 | QMVAR | SID |  | Completed
11 | 17/09/2020 | QMVAR | SID |  | Completed
12 | 18/09/2020 | QMVAR | SID | 50% | Completed
13 | 19/09/2020 | WeekEnd
14 | 20/09/2020 | WeekEnd
15 | 21/09/2020 | QMVAR | SID |  | Completed
16 | 22/09/2020 | QMVAR | SID |  | Completed
17 | 23/09/2020 | QMVAR | SID |  | Completed
18 | 24/09/2020 | QMVAR | SID |  | Completed
19 | 25/09/2020 | QMVAR | SID | 100% | Completed
20 | 26/09/2020 | WeekEnd
21 | 27/09/2020 | WeekEnd
22 | 28/09/2020 | Leave
23 | 29/09/2020 | QMVAR | SID | 100% | Completed | Integration done
24 | 30/09/2020 | QMVAR | SID PL Tracking |  | Gathering Req | Analyse