## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-04-29 | RPA Dotnet | [Backend] CRM | 30% | WIP | Tables are created at RPA Sale database, whereas relationship is penidng, after discussing with Mr Bharathi san, it will be over, if any changes or modification can be done.
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-05-27 | QMVAR | Account Report | 40% | WIP
2 | 2020-05-27 | MujiStore | Multi language integrated from Ram |  | Completed
3 | 2020-05-27 | MujiStore | Default load Japanes language |  | Completed
Status
WIP
Pending
Completed
Hold

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
2 | 2020-05-04 | Hayaai | Website design- Business page | 100% | Completed
2 | 2020-05-05 | Hayaai | Website design- Contact page & Business page popup | 60% | WIP
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-30 | DOTNET APP | Video | 70% | WIP | Retrive table Values for DB and Ui Design
2 | 2020-05-04 | DOTNET APP | Video | 100% | Completed
2 | 2020-05-04 | DOTNET APP | Presentation | 40% | WIP | Retrive table Values for DB and Ui Design
3 | 2020-05-05 | DOTNET APP | Presentation | 100% | Completed
4 | 2020-05-06 | DOTNET APP | Muji Multi Language(Resource Changing) | 50% | WIP | tblDeploySchedule, tblDeployStatu, SubnetController, DeploySchedulesController, FoldersController, FormatsController, HomeController, StoreGroupFoldersController, StoreGroupsController, StreamServersController, StreamServerSubnetsController, VideoFilesController, StreamServerFormats
5 | 2020-05-07 | DOTNET APP | Muji Multi Language(Resource Changing) | 100% | Completed | tblFolder, tblFolder, tblStreamServer, tblStreamServerSubnet, DeployLogs, DeploySchedules, DeployStatus, Formats, Shared, StoreMst, StoreSubnets, StreamServers, StreamServerSubnets, Subnets, VideoFiles
6 | 2020-05-08 | DOTNET APP | Hit Counter | 30% | WIP | Retrive Values for DB and Ui Design
7 | 2020-05-11 | DOTNET APP | Hit Counter, UserPresentation | 30% | WIP | UserPresentation Chages Completed and design Chages
8 | 2020-05-12 | DOTNET APP | Hit Counter | 100% | Completed
9 | 2020-05-13 | DOTNET APP | Hit Counter, SocialMedia | 60% | WIP | Hit Counter Design Changes Completed, SocialMedia Working
10 | 2020-05-14 | DOTNET APP | CountDrs Testing | 100% | Completed | Matching Values for all centers ssc1-ssc8
11 | 2020-05-15 | DOTNET APP | Mobile Srevice Centers , SocialMedia | 30% | WIP | retrive db and css design
12 | 2020-05-18 | DOTNET APP | Social Media | 30% | WIP | Insert table values
13 | 2020-05-19 | DOTNET APP | Social Media | 30% | WIP | GridView Show the table, Delete
14 | 2020-05-20 | DOTNET APP | Social Media, Count Drs Verified | 100% | Completed | Count Drs data check complted
15 | 2020-05-21 | DOTNET APP | PowerPoint Presentation design and dynamic download | 100% | Completed
16 | 2020-05-22 | DOTNET APP | Testing RPA_Sales Application | 50% | WIP | Login Page, User Management, Video Management, PPT Management
17 | 2020-05-26 | DOTNET APP | RPA_Sales Application (Language Changing), GSPN Password Changing | 100% | Completed | Login Page, User Management, CRM, SocialMedia, Task Management, Video Management, PPT Management, Dashboard, RPA Sample Reports
18 | 2020-05-27 | QMVQR, DOTNET APP | QMVAR PO_Confirmaion, RPA_Sales | 30% | WIP | PO_Confirmaion data check to verification Completed, RPA_Sales language Resource changing
Status
WIP
|  | Pending | ,
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
1 | 29/04/2020 | Rever B2C | IF full flow with technician tracking integration | 100% | Completed | APK sent.
Status
WIP
Pending
Completed
Hold