## アプリ配置 (必須)
| プログラム名 | プログラムID | プログラムの場所（現在）
ビックカメラ | 加入データ取り込み | BIC_Import_bat.exe | 192.168.150.100 D:\AP\server
| ワランティシステム | WRNDB.exe | C:\client
192.168.150.106 C:\client
| 管理メニュー | admin.exe | C:\client
192.168.150.106 C:\client
| 加入イレギュラー登録 | BIC_Input.exe | C:\client
| 総括表出力 | コジマ対応分_bic集計_分割_受信日.mdb | 192.168.150.108 C:\client
| 加入データ出力 | bic_txt_分割_受信日.mdb | 192.168.150.108 C:\client
| ヒトコミ提出用アプリ | BIC_DATA_appl.mdb | 192.168.150.108 C:\client
| ヒトコミ提出用ＤＢ | BIC_DATA.mdb | 192.168.150.108 C:\client
| ＳＱＬデータベース | bicdb_new | 192.168.150.102
ベスト電器 | メンテメニュー | best_mnt_menu.exe | C:\client
| 品種マスタメンテ | best_mnt_cat.exe | C:\client
| 店舗マスタメンテ | best_mnt_shop.exe | C:\client
| メーカマスタメンテ | best_mnt_vdr.exe | C:\client
| 加入メニュー | best_wrn_menu.exe | C:\client
| 加入取り込み | best_yamada_import.exe | C:\client
| 加入登録 | best_input.exe | C:\client
| 加入検索 | best_search.exe | C:\client
| 加入締め処理 | best_close.exe | C:\client
| 加入締め戻し処理 | best_close_return.exe | C:\client
| 加入エラー修正 | best_err_mnt.exe | C:\client
| 加入確定データ出力 | best_exp_SB02.exe | C:\client
| ベストレポート | Best_Report.exe | C:\client
| 請求メニュー | best_ivc_menu.exe | C:\client
| 請求データ取り込み | best_ivc_import.exe | C:\client
| 請求データ登録 | best_ivc_input.exe | C:\client
| 請求検索 | best_ivc_search.exe | C:\client
| 請求締め処理 | best_ivc_close.exe | C:\client
| 請求締め戻し処理 | best_ivc_close_return.exe | C:\client
| 請求エラー修正 | best_ivc_err_mnt.exe | C:\client
| 請求データ出力 | best_ivc_export.exe | C:\client
| 入金データ出力 | best_exp_SB03.exe | C:\client
| 請求レポート | best_ivc_report.exe | C:\client
| web data 作成 | best_web_data_bat.exe | 192.168.150.100 D:\AP\s5
| web data 作成 | best_web_data_sub1.exe | 192.168.150.100 D:\AP\s5
| web data 作成 | best_web_data_sub2.exe | 192.168.150.100 D:\AP\s5
| web data 作成 | best_web_data_sub3.exe | 192.168.150.100 D:\AP\s5
| web data 作成 | best_web_data_sub4.exe | 192.168.150.100 D:\AP\s5
| web修理情報検索 | s5.dll | 10.255.51.104 C:\webapp\Sonia
| カコイ取り込み | ｶｺｲ修理取込_new.mdb | C:\client
| 商品別加入集計 | 20_BEST商品別加入集計.mdb | 192.168.150.108
| 品種別事故状況別集計 | BEST集計_品種別事故状況別201303_201402.mdb | C:\client
| ＳＱＬデータベース | best_wrn_new | 192.168.150.102
| ＳＱＬデータベース(旧加入データ) | best_wrn_data2 | 192.168.150.102
| ＳＱＬデータベース(web閲覧用データ) | s5 | 192.168.150.102
| ＳＱＬデータベース(web閲覧用データ) | s5 | 10.255.51.105
ベスト電器（海外) | 海外メニュー | best_intl_menu.exe | C:\client
| 加入データ取り込み | best_import_intl.exe | C:\client
| 加入検索 | best_intl_search.exe | C:\client
| 請求締め処理 | best_intl_ivc_close.exe | C:\client
| 請求締め戻し処理 | best_intl_ivc_close_return.exe | C:\client
| 請求データ出力 | best_intl_ivc_export.exe | C:\client
| 請求データ登録 | best_intl_ivc_input.exe | C:\client
| 請求レポート | best_intl_ivc_report.exe | C:\client
| 台湾データ変換 | 台湾CMV.mdb | C:\client
| 加入締め処理 | Best_itel.mdb | C:\client
| 未計上データ取り込み | Best_itel_未計上取込み.mdb | C:\client
| ＳＱＬデータベース | best_intl | 192.168.150.102
オール電化 | 検索 | best_search_all8.exe | C:\client
| レポート | best_report_all8.exe | C:\client
| ＳＱＬデータベース | best_wrn_new | 192.168.150.102
ストリーム | 加入取り込み | STRM_import.exe | C:\client
| 検索 | STRM_search.exe | C:\client
| ＳＱＬデータベース | STRM | 192.168.150.102
ミスターマックス | 加入取り込み | MrMax_Import.exe | C:\client
| その他問い合わせ検索 | MrMAX_INQUIRY.exe | C:\client
192.168.150.106 C:\client
| マスタメンテ | MrMAX_Mtr.exe | C:\client
| 修理受付番号検索 | MrMAX_REP.exe | C:\client
192.168.150.106 C:\client
| 検索 | MrMax_Wrn.exe | C:\client
| ＳＱＬデータベース | MrMax_Wrn | 192.168.150.102
くろがねや | メニュー | Kuroganeya.exe | C:\client
| その他問い合わせ検索 | Kuroganeya_INQUIRY.exe | C:\client
192.168.150.106 C:\client
| 修理受付番号検索 | Kuroganeya_REP.exe | C:\client
192.168.150.106 C:\client
| 検索 | Kuroganeya_Wrn.exe | C:\client
| ＳＱＬデータベース | Kuroganeya | 192.168.150.102
ホーマック | 加入取り込み | Homac_import.exe | C:\client
| 加入検索 | Homac_search.exe | C:\client
192.168.150.106 C:\client
| メニュー | Homac.exe | C:\client
| ＳＱＬデータベース | Homac | 192.168.150.102
灰色は今回、修正不要となる予定です。

## App placement (necessary)
| Program name | Program ID |  | Program location (current)
Bic Camera | Subscription data acquisition | BIC_Import_bat.exe |  | 192.168.150.100 D:\AP\server
| Warranty system | WRNDB.exe |  | C:\client
192.168.150.106 C:\client
| Administration menu | admin.exe |  | C:\client
192.168.150.106 C:\client
| Subscription irregular registration | BIC_Input.exe |  | C:\client
| Summary table output | コジマ対応分_bic集計_分割_受信日.mdb | Kojima correspondence _ bic aggregation _ division_ received date .mdb | 192.168.150.108 C:\client
| Subscription data output | bic_txt_分割_受信日.mdb | bic_txt_division_ received date.mdb | 192.168.150.108 C:\client
| Hitcom submission application | BIC_DATA_appl.mdb |  | 192.168.150.108 C:\client
| Hitcom submission DB | BIC_DATA.mdb |  | 192.168.150.108 C:\client
| SQL database | bicdb_new |  | 192.168.150.102
Best Denki | Maintenance menu | best_mnt_menu.exe |  | C:\client
| Variety master maintenance | best_mnt_cat.exe |  | C:\client
| Store master maintenance | best_mnt_shop.exe |  | C:\client
| Manufacture master maintenance | best_mnt_vdr.exe |  | C:\client
| Subscription menu | best_wrn_menu.exe |  | C:\client
| Subscription import | best_yamada_import.exe |  | C:\client
| Subscription registration | best_input.exe |  | C:\client
| Subscription search | best_search.exe |  | C:\client
| Subscription closing process | best_close.exe |  | C:\client
| Subscription return processing | best_close_return.exe |  | C:\client
| Subscription error correction | best_err_mnt.exe |  | C:\client
| Subscription defined data output | best_exp_SB02.exe |  | C:\client
| Best report | Best_Report.exe |  | C:\client
| Billing menu | best_ivc_menu.exe |  | C:\client
| Billing data import | best_ivc_import.exe |  | C:\client
| Billing data registration | best_ivc_input.exe |  | C:\client
| Billing search | best_ivc_search.exe |  | C:\client
| Billing closing process | best_ivc_close.exe |  | C:\client
| Billing return processing | best_ivc_close_return.exe |  | C:\client
| Billing error correction | best_ivc_err_mnt.exe |  | C:\client
| Billing data output | best_ivc_export.exe |  | C:\client
| Deposit data output | best_exp_SB03.exe |  | C:\client
| Billing report | best_ivc_report.exe |  | C:\client
| web data creation | best_web_data_bat.exe |  | 192.168.150.100 D:\AP\s5
| web data creation | best_web_data_sub1.exe |  | 192.168.150.100 D:\AP\s5
| web data creation | best_web_data_sub2.exe |  | 192.168.150.100 D:\AP\s5
| web data creation | best_web_data_sub3.exe |  | 192.168.150.100 D:\AP\s5
| web data creation | best_web_data_sub4.exe |  | 192.168.150.100 D:\AP\s5
| web repair information search | s5.dll |  | 10.255.51.104 C:\webapp\Sonia
| Kakoi import | ｶｺｲ修理取込_new.mdb | Kakoi repair import_new.mdb | C:\client
| Subscription summary by product | 20_BEST商品別加入集計.mdb | 20_BEST Subscription summary by product.mdb | 192.168.150.108
| Summary by product type and accident status | BEST集計_品種別事故状況別201303_201402.mdb | BEST Summary_By product type Accident status 201303_201402.mdb | C:\client
| SQL database | best_wrn_new |  | 192.168.150.102
| SQL database (old subscription data) | best_wrn_data2 |  | 192.168.150.102
| SQL database (data for web browsing) | s5 |  | 192.168.150.102
| SQL database (data for web browsing) | s5 |  | 10.255.51.105
Best Denki (overseas) | Overseas menu | best_intl_menu.exe |  | C:\client
| Subscription data import | best_import_intl.exe |  | C:\client
| Subscription search | best_intl_search.exe |  | C:\client
| Billing closing process | best_intl_ivc_close.exe |  | C:\client
| Billing return process | best_intl_ivc_close_return.exe |  | C:\client
| Billing data output | best_intl_ivc_export.exe |  | C:\client
| Billing data registration | best_intl_ivc_input.exe |  | C:\client
| Billing report | best_intl_ivc_report.exe |  | C:\client
| Taiwan data conversion | 台湾CMV.mdb | Taiwan CMV.mdb | C:\client
| Subscription closing process | Best_itel.mdb |  | C:\client
| Unaccounted data import | Best_itel_未計上取込み.mdb | Best_itel_Unaccounted import.mdb | C:\client
| SQL database | best_intl |  | 192.168.150.102
All Denka | Search | best_search_all8.exe |  | C:\client
| Report | best_report_all8.exe |  | C:\client
| SQL database | best_wrn_new |  | 192.168.150.102
Stream | Subscription import | STRM_import.exe |  | C:\client
| Search | STRM_search.exe |  | C:\client
| SQL database | STRM |  | 192.168.150.102
Mr Max | Subscription import | MrMax_Import.exe |  | C:\client
| Other inquiry search | MrMAX_INQUIRY.exe |  | C:\client
192.168.150.106 C:\client
| Master maintenance | MrMAX_Mtr.exe |  | C:\client
| Repair reception number search | MrMAX_REP.exe |  | C:\client
192.168.150.106 C:\client
| Search | MrMax_Wrn.exe |  | C:\client
| SQL database | MrMax_Wrn |  | 192.168.150.102
Kuroganeya | Menu | Kuroganeya.exe |  | C:\client
| Other inquiry search | Kuroganeya_INQUIRY.exe |  | C:\client
192.168.150.106 C:\client
| Repair reception number search | Kuroganeya_REP.exe |  | C:\client
192.168.150.106 C:\client
| Search | Kuroganeya_Wrn.exe |  | C:\client
| SQL database | Kuroganeya |  | 192.168.150.102
Homac | Subscription import | Homac_import.exe |  | C:\client
| Subscription search | Homac_search.exe |  | C:\client
192.168.150.106 C:\client
| Menu | Homac.exe |  | C:\client
| SQL database | Homac |  | 192.168.150.102
Gray will not need to be modified this time.
Note:
Datasource and its database are from INI file of bin folder,But we can't find its server location for establishing the connection.
Eventhough specifying the MDB in its corresponding folder according to the sonia_indialab_english, I feel that they were not specifying the correct MDB.Because of the INI file of db is entriely different from MDB whatever they have specified.

## 毎月の固定作業をプログラム化した時の工数（オリジナル） (hidden)
毎月の固定作業をプログラム化した時の工数
| 作業内容 | 現プログラム
3日の作業 | ◆BIC 総括表作成（BIC、 AirBIC、コジマ） | コジマ対応分_bic集計_分割_受信日.mdb
| ◆BIC 加入データ保証期間別にしてCD用データ作成 | bic_txt_分割_受信日.mdb
| ◆BICコールログデータ抽出 | BIC_DATA_appl.mdb
| ◆ベストWebデータ抽出 | best_web_data_bat.exe best_web_data_sub1.exe best_web_data_sub2.exe best_web_data_sub3.exe best_web_data_sub4.exe
3日の夜間作業 | ◆ベストWebデータ切り替え
16日の作業 | ◆BIC 総括表作成（コジマ1～15） | コジマ対応分_bic集計_分割_受信日.mdb
20日の作業 | ◆BEST_加入締め処理 と 商品別加入集計 | 20_BEST商品別加入集計.mdb
末日の作業 | ◆品種別事故状況別集計 | BEST集計_品種別事故状況別201303_201402.mdb

## Missing DLLs
| Program name | Program ID |  | Program location (current) | INI File | Missing DLL & Supporting files | INI File | Remarks
Bic Camera | Subscription data acquisition | BIC_Import_bat.exe |  | 192.168.150.100 D:\AP\server |  | ActiveReports.Viewer.dll is missing in BIC_Import_bat project |  | Missing Dll Added, Application Successfully Build
| Warranty system | WRNDB.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll, CrystalDecisions.CrystalReports.Engine.dll,CrystalDecisions.ReportSource.dll and CrystalDecisions.Shared.dll are missing in WRNDB project |  | Crystal report Dll Added. Download from Google . Build Application without error
192.168.150.106 C:\client
| Administration menu | admin.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in admin project |  | Build Error (Grapecity.Win.Input.)
192.168.150.106 C:\client
| Subscription irregular registration | BIC_Input.exe |  | C:\client |  |  |  | Successfully Build
| Summary table output | コジマ対応分_bic集計_分割_受信日.mdb | Kojima correspondence _ bic aggregation _ division_ received date .mdb | 192.168.150.108 C:\client
| Subscription data output | bic_txt_分割_受信日.mdb | bic_txt_division_ received date.mdb | 192.168.150.108 C:\client
| Hitcom submission application | BIC_DATA_appl.mdb |  | 192.168.150.108 C:\client
| Hitcom submission DB | BIC_DATA.mdb |  | 192.168.150.108 C:\client
| SQL database | bicdb_new |  | 192.168.150.102
Best Denki | Maintenance menu | best_mnt_menu.exe |  | C:\client |  | Build-Ok
| Variety master maintenance | best_mnt_cat.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_mnt_cat project |  | Successfully Build
| Store master maintenance | best_mnt_shop.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing and office.dll is missing in best_mnt_shop project |  | Multiple version dll found, removed dll. Now able to build
| Manufacture master maintenance | best_mnt_vdr.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_mnt_vdr project |  | Successfully Build
| Subscription menu | best_wrn_menu.exe |  | C:\client |  | Build-Ok
| Subscription import | best_yamada_import.exe |  | C:\client |  | Build-Ok | best_wrn.ini(gss8888-PC,best_wrn_new)
| Subscription registration | best_input.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_input project |  | Rename @Form2 to Form2 and @Form3 to Form3 in VB file, Build Error (Grapecity.Win.Input.)
| Subscription search | best_search.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_search project and it requires the best_search_setup.dll |  | Build Error (Grapecity.Win.Input.)
| Subscription closing process | best_close.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_close project |  | Successfully Build
| Subscription return processing | best_close_return.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_close_return project |  | Successfully Build
| Subscription error correction | best_err_mnt.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_err_mnt.exe project |  | Successfully Build
| Subscription defined data output | best_exp_SB02.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_exp_SB02 project |  | Successfully Build
| Best report | Best_Report.exe |  | C:\client |  | ActiveReports,ActiveReports.PdfExport,ActiveReports.Viewer,DTS,Microsoft.office.core,Office and VBIDE dll are missing in Best_Report project |  | IssueFixed Add "Imports Excel = Microsoft.Office.Interop.Excel" top of Form1.vb, Now Successfully build
| Billing menu | best_ivc_menu.exe |  | C:\client |  | Build-Ok
| Billing data import | best_ivc_import.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_ivc_import project |  | Successfully Build
| Billing data registration | best_ivc_input.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_ivc_input project |  | Successfully Build
| Billing search | best_ivc_search.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_ivc_search project |  | Successfully Build
| Billing closing process | best_ivc_close.exe |  | C:\client |  | Build-Ok | best_wrn.ini (best_wrn_new_temp).But zip file shows BEST集計_品伺・事互・襟・201303_201402.mdb and 20_BEST商品・・渡集計.mdb
| Billing return processing | best_ivc_close_return.exe |  | C:\client |  | Build-Ok | best_wrn.ini (best_wrn_new_temp).But zip file shows BEST集計_品伺・事互・襟・201303_201402.mdb and 20_BEST商品・・渡集計.mdb
| Billing error correction | best_ivc_err_mnt.exe |  | C:\client |  | Grapecity.Win.Input.V20,ActiveReports,ActiveReports.PdfExport and ActiveReports.Viewer dlls are missing in best_ivc_err_mnt project |  | Missing Dll Added, Application Successfully Build
| Billing data output | best_ivc_export.exe |  | C:\client |  | Grapecity.Win.Input.V20 and Office dll is missing in best_ivc_export project |  | IssueFixed Add "Imports Excel = Microsoft.Office.Interop.Excel" top of Form1.vb, Now Successfully build
| Deposit data output | best_exp_SB03.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_exp_SB03 project |  | Successfully Build
| Billing report | best_ivc_report.exe |  | C:\client |  | Grapecity.Win.Input.V20,ActiveReports,ActiveReports.PdfExport and ActiveReports.Viewer dlls are missing in best_ivc_report project |  | Missing Dll Added, Application Successfully Build
| web data creation | best_web_data_bat.exe |  | 192.168.150.100 D:\AP\s5 | best_wrn_new | Build-Ok | best_wrn.ini(192.168.70.208,best_wrn_new),best_wrn_data2.ini(192.168.70.208,best_wrn_data2),s5.ini(192.168.70.208,s5)
| web data creation | best_web_data_sub1.exe |  | 192.168.150.100 D:\AP\s5 | best_wrn_new,s5x | Build-Ok | best_wrn.ini(gss-mo;catalog,best_wrn_new),s5.ini(10.10.1.3,s5x)
| web data creation | best_web_data_sub2.exe |  | 192.168.150.100 D:\AP\s5 | best_wrn_new_temp | Build-Ok | best_wrn.ini(sqa-sql2k5,best_wrn_new_temp),s5.ini(192.168.150.103,s5)
| web data creation | best_web_data_sub3.exe |  | 192.168.150.100 D:\AP\s5 | best_wrn_new_temp | Build-Ok | best_wrn.ini(source=sqa-sql2k5,best_wrn_new_temp),s5.ini(192.168.150.103,s5)
| web data creation | best_web_data_sub4.exe |  | 192.168.150.100 D:\AP\s5 | best_wrn_new_temp | Build-Ok | best_wrn.ini(source=sqa-sql2k5,best_wrn_new_temp),s5.ini(192.168.150.103,s5)
| web repair information search | s5.dll |  | 10.255.51.104 C:\webapp\Sonia |  | Build-Ok | where is S5.mdf
| Kakoi import | ｶｺｲ修理取込_new.mdb | Kakoi repair import_new.mdb | C:\client
| Subscription summary by product | 20_BEST商品別加入集計.mdb (20_BEST.mdb) | 20_BEST Subscription summary by product.mdb | 192.168.150.108
| Summary by product type and accident status | BEST集計_品種別事故状況別201303_201402.mdb(BEST201303_201402.mdb) | BEST Summary_By product type Accident status 201303_201402.mdb | C:\client
| SQL database | best_wrn_new |  | 192.168.150.102
| SQL database (old subscription data) | best_wrn_data2 |  | 192.168.150.102
| SQL database (data for web browsing) | s5 |  | 192.168.150.102
| SQL database (data for web browsing) | s5 |  | 10.255.51.105
Best Denki (overseas) | Overseas menu | best_intl_menu.exe |  | C:\client
| Subscription data import | best_import_intl.exe |  | C:\client
| Subscription search | best_intl_search.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll and best_intl_search_setup project is missing in best_intl_search project |  | Build Error (Grapecity.Win.Input.)
| Billing closing process | best_intl_ivc_close.exe |  | C:\client
| Billing return process | best_intl_ivc_close_return.exe |  | C:\client
| Billing data output | best_intl_ivc_export.exe |  | C:\client
| Billing data registration | best_intl_ivc_input.exe |  | C:\client
| Billing report | best_intl_ivc_report.exe |  | C:\client
| Taiwan data conversion | 台湾CMV.mdb | Taiwan CMV.mdb | C:\client
| Subscription closing process | Best_itel.mdb |  | C:\client
| Unaccounted data import | Best_itel_未計上取込み.mdb | Best_itel_Unaccounted import.mdb | C:\client
| SQL database | best_intl |  | 192.168.150.102
All Denka | Search | best_search_all8.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_search_all8 project |  | Build Error (Grapecity.Win.Input.)
| Report | best_report_all8.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in best_report_all8 project |  | Successfully Build
| SQL database | best_wrn_new |  | 192.168.150.102
Stream | Subscription import | STRM_import.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll and Microsoft.Office.Core dll is missing in STRM_import project |  | IssueFixed Add "Imports Excel = Microsoft.Office.Interop.Excel" top of Form1.vb, Now Successfully build
| Search | STRM_search.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in STRM_search project |  | Successfully Build
| SQL database | STRM |  | 192.168.150.102
Mr Max | Subscription import | MrMax_Import.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll ,VBIDE.dll, and Microsoft.Office.Core dll is missing in MrMax_Import project |  | IssueFixed Add "Imports Excel = Microsoft.Office.Interop.Excel" top of Form1.vb, Now Successfully build
| Other inquiry search | MrMAX_INQUIRY.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in MrMAX_INQUIRY project |  | Successfully Build
192.168.150.106 C:\client
| Master maintenance | MrMAX_Mtr.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in MrMAX_Mtr project |  | Successfully Build
| Repair reception number search | MrMAX_REP.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in MrMAX_REP project |  | Successfully Build
192.168.150.106 C:\client
| Search | MrMax_Wrn.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing and MrMax_Wrn_Setup is not loaded in MrMax_Wrn project |  | Successfully Build
| SQL database | MrMax_Wrn |  | 192.168.150.102
Kuroganeya | Menu | Kuroganeya.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll and Microsoft.Office.Core dll is missing in Kuroganeya project |  | IssueFixed Add "Imports Excel = Microsoft.Office.Interop.Excel" top of Form1.vb, Now Successfully build
| Other inquiry search | Kuroganeya_INQUIRY.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in Kuroganeya_INQUIRY project |  | Successfully Build
192.168.150.106 C:\client
| Repair reception number search | Kuroganeya_REP.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in Kuroganeya_REP project |  | Successfully Build
192.168.150.106 C:\client
| Search | Kuroganeya_Wrn.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in Kuroganeya_Wrn project |  | Successfully Build
| SQL database | Kuroganeya |  | 192.168.150.102
Homac | Subscription import | Homac_import.exe |  | C:\client |  | Build-Ok | Homac.ini(gss8888-pc,Homac)
| Subscription search | Homac_search.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in Homac_search project |  | Successfully Build
192.168.150.106 C:\client
| Menu | Homac.exe |  | C:\client |  | Grapecity.Win.Input.V20.dll is missing in Homac project |  | Rename @F00_Form02_3.vb to F00_Form02_3.vb, Successfully build
| SQL database | Homac |  | 192.168.150.102

## Ini File Details
| Program name | Program ID | File Name | Data Source | catalog | Database_Name | Developer | Status | Remarks
Bic Camera | Subscription data acquisition | BIC_Import_bat.exe | bicdb.ini | GSS8888-PC | bicdb_new | bicdb_new | Bharathi | Completed | Import Document Need tocheck functionality
| Warranty system | WRNDB.exe | bicdb.ini | GSS8888-PC | bicdb_new | bicdb_new | Bharathi | Completed | Working fine
| Administration menu | admin.exe | bicdb.ini | GSS8888-PC | bicdb_new | bicdb_new | Bharathi | Completed | Working fine.
Best Denki | Maintenance menu | best_mnt_menu.exe |  |  |  |  | Sabeena | Completed | Working fine.
| Variety master maintenance | best_mnt_cat.exe | best_wrn.ini | GSS-mo | best_wrn_new |  | Sabeena | Completed | Working fine.
| Store master maintenance | best_mnt_shop.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp |  | Sabeena | Completed | Working fine.
| Manufacture master maintenance | best_mnt_vdr.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp |  | Sabeena | Completed | Working fine.
| Subscription menu | best_wrn_menu.exe |  |  |  |  | Sabeena | Completed | Working fine.
| Subscription import | best_yamada_import.exe | best_wrn.ini | GSS8888-PC | best_wrn_new |  | Sabeena | Completed | Working Fine.Import Document Need tocheck functionality
| Subscription registration | best_input.exe | best_wrn.ini | gss8888-PC | best_wrn_new |  | Sabeena | Completed | Working fine.
| Subscription search | best_search.exe | best_wrn.ini | gss8888-PC | best_wrn_new |  | Sabeena | Completed | Working fine.-grapecity date issue commented 1 line.
| Subscription closing process | best_close.exe | best_wrn.ini | gss8888-pc | best_wrn_new |  | Sabeena | Completed | Working fine.
| Subscription return processing | best_close_return.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp |  | Sabeena | Completed | Working fine.
| Subscription error correction | best_err_mnt.exe | best_wrn.ini | GSS8888-PC | best_wrn_new |  | Sabeena | Completed | Working fine.
| Subscription defined data output | best_exp_SB02.exe | best_wrn.ini | GSS8888-PC | best_wrn_new |  | Sabeena | Completed | Working fine.
| Best report | Best_Report.exe | best_wrn.ini | GSSNWS01 | best_wrn_new |  | Sabeena | Completed | Working fine.
| Billing menu | best_ivc_menu.exe |  |  |  |  | Sabeena | Completed | Working fine.
| Billing data import | best_ivc_import.exe | best_wrn.ini,best_wrn_data.ini | sqa-sql2k5,sqa-sql2k5 | best_wrn_new,best_wrn_new_temp |  | Sabeena | Completed | Working fine.Import Document Need tocheck functionality
| Billing data registration | best_ivc_input.exe | best_wrn.ini,best_wrn_data2.ini | gss8888-PC,gss8888-PC | best_wrn_new,best_wrn_data2 |  | Sabeena | Completed | Working fine.
| Billing search | best_ivc_search.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp |  | Sabeena | Completed | Working fine.
| Billing closing process | best_ivc_close.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp |  | Sabeena | Completed | Need sp_best_ivc_close_01,sp_best_ivc_close_02
| Billing return processing | best_ivc_close_return.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp | best_wrn_new_temp | Bharathi | completed | Working fine.
| Billing error correction | best_ivc_err_mnt.exe | best_wrn.ini,best_wrn_data2.ini | gss8888-PC,gss8888-PC | best_wrn_new,best_wrn_data2 |  | Sabeena | Completed | Need SP_best_ivc_err_mnt_3,SP_best_ivc_err_mnt_4,SP_best_ivc_err_mnt_5,SP_best_ivc_err_mnt_6
| Billing data output | best_ivc_export.exe | best_wrn.ini,best_wrn_data2.ini | sqa-sql2k5,sqa-sql2k5 | best_wrn_new,best_wrn_data2_temp |  | Sabeena | Completed | Working fine.
| Deposit data output | best_exp_SB03.exe | best_wrn.ini | GSS8888-PC | best_wrn_new |  | Sabeena | Completed | Working fine.
| Billing report | best_ivc_report.exe | best_wrn.ini,best_wrn_data2.ini | gss8888-PC,gss8888-PC | best_wrn_new,best_wrn_data2 |  | Sabeena | Completed | Working fine.
| web data creation | best_web_data_bat.exe | best_wrn.ini | 192.168.70.208 | best_wrn_new | best_wrn | Vijay | completed | Working fine.
| web data creation | best_web_data_bat.exe | best_wrn_data2.ini | 192.168.70.208 | best_wrn_data2 | best_wrn_data2 | Vijay | completed | Working fine.
| web data creation | best_web_data_bat.exe | s5.ini | 192.168.70.208 | s5 | S5 | Vijay | completed | Working fine.
| web data creation | best_web_data_sub1.exe | best_wrn.ini | gss-mo | best_wrn_new | best_wrn | Vijay | completed | Working fine.
| web data creation | best_web_data_sub1.exe | s5.ini | 10.10.1.3 | s5x | S5 | Vijay | completed | Working fine.
| web data creation | best_web_data_sub2.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp | best_wrn | Vijay | completed | Working fine.
| web data creation | best_web_data_sub2.exe | s5.ini | 192.168.150.103 | s5 | S5 | Vijay | completed | Working fine.
| web data creation | best_web_data_sub3.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp | best_wrn | Vijay | completed | Working fine.
| web data creation | best_web_data_sub3.exe | best_wrn_data2.ini | sqa-sql2k5 | best_wrn_data2_temp | best_wrn_data2 | Vijay | completed | Working fine.
| web data creation | best_web_data_sub3.exe | s5.ini | 192.168.150.103 | s5 | S5 | Vijay | completed | Working fine.
| web data creation | best_web_data_sub4.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp | best_wrn | Vijay | completed | Working fine.
| web data creation | best_web_data_sub4.exe | s5.ini | 192.168.150.103 | s5 | S5 | Vijay | completed | Working fine.
| web repair information search | s5.dll | no ini found(DB from web.config) | GSS8888-PC | s5 | s5 | Bharathi | completed | Working fine
Best Denki (overseas) | Overseas menu | best_intl_menu.exe | [5 empty] | completed | Working fine.
| Subscription data import | best_import_intl.exe
| Subscription search | best_intl_search.exe
| Billing closing process | best_intl_ivc_close.exe
| Billing return process | best_intl_ivc_close_return.exe
| Billing data output | best_intl_ivc_export.exe
| Billing data registration | best_intl_ivc_input.exe
| Billing report | best_intl_ivc_report.exe
All Denka | Search | best_search_all8.exe | best_wrn.ini | sqa-sql2k5 | best_wrn_new_temp | best_wrn_new_temp | Vijay | completed | Working fine.-grapecity date issue commented 1 line.
| Report | best_report_all8.exe | best_wrn.ini | GSSNWS01 | best_wrn_new | best_wrn_new_temp | Vijay | completed | Working fine.
Stream | Subscription import | STRM_import.exe | STRM.ini | gss8888-pc | STRM | STRM | Vijay | completed | Working Fine.Import Document Need tocheck functionality
| Search | STRM_search.exe | STRM.ini | gss8888-pc | STRM | STRM | Vijay | Completed | Working fine.
Mr Max | Subscription import | MrMax_Import.exe | MrMAX_Wrn.ini | gss8888-pc | MrMAX_Wrn | MrMAX_Wrn | Prabu/Ram | WIP | We have create the table using codebehind The following Sps are missing sp_import01, sp_rb_chk, sp_err_chk_04, sp_wrn_chk, sp_wrn_chk_PB_1, sp_wrn_chk_PB_2, sp_err_chk_01, sp_err_chk_01_2, sp_err_chk_02, sp_err_chk_03, sp_err_chk_05, sp_err_list, sp_ok_list, sp_biz_list, sp_glist_glist, sp_glist_dtl_W, sp_glist_dtl, sp_glist_err, sp_glist_biz, sp_biz_list, sp_err_mnt01, sp_err_mnt02 Import Document Need tocheck functionality
| Other inquiry search | MrMAX_INQUIRY.exe | MrMAX.ini | gss8888-pc | MrMAX_Wrn | MrMAX_Wrn | Prabu/Ram | Completed | Working fine.- date issue so commented 1 line. We have create the table using codebehind
| Master maintenance | MrMAX_Mtr.exe | MrMAX.ini | gss8888-pc | MrMAX_Wrn | MrMAX_Wrn | Prabu/Ram | Completed | Working fine.- We have create the table using codebehind
| Repair reception number search | MrMAX_REP.exe | MrMAX.ini | gss8888-pc | MrMAX_Wrn | MrMAX_Wrn | Prabu/Ram | Completed | Working fine.- We have create the table using codebehind
| Search | MrMax_Wrn.exe | MrMAX.ini | gss8888-pc | MrMAX_Wrn | MrMAX_Wrn | Prabu/Ram | Completed | Working fine.- We have create the table using codebehind
Kuroganeya | Menu | Kuroganeya.exe | Kuroganeya.ini | gss8888-pc | Kuroganeya | Kuroganeya_1 | Bharathi | completed | Working fine.Import Document Need tocheck functionality
| Other inquiry search | Kuroganeya_INQUIRY.exe | Kuroganeya.ini | soniasrv05 | Kuroganeya_temp | Kuroganeya_temp | Bharathi | completed | Working fine
| Repair reception number search | Kuroganeya_REP.exe | Kuroganeya.ini | soniasrv05 | Kuroganeya_temp | Kuroganeya | Bharathi | completed | Working fine
| Search | Kuroganeya_Wrn.exe | Kuroganeya.ini | soniasrv05 | Kuroganeya_temp | Kuroganeya | Bharathi | completed | Working fine
Homac | Subscription import | Homac_import.exe | Homac.ini | gss8888-pc | Homac | Homac | Bharathi | completed | Import Document Need tocheck functionality
| Subscription search | Homac_search.exe | Homac.ini | gss8888-pc | Homac | Homac | Bharathi | completed | Working fine.
| Menu | Homac.exe | Homac.ini | gss8888-pc | Homac | Homac | Bharathi | completed | Working fine.Import Document Need tocheck functionality

## App_Issue
Module | Program name | Program ID
Bic Camera | Administration menu | admin.exe
Best Denki | Subscription registration | best_input.exe
| Subscription search | best_search.exe
Best Denki (overseas) | Subscription search | best_intl_search.exe
All Denka | Search | best_search_all8.exe
Module | Program name | Program ID
Best Denki | Subscription registration | best_input.exe
Homac | Menu | Homac.exe
Module | Program name | Program ID
Best Denki | Best report | Best_Report.exe
| Billing data output | best_ivc_export.exe
Stream | Subscription import | STRM_import.exe
Mr Max | Subscription import | MrMax_Import.exe
Kuroganeya | Menu | Kuroganeya.exe
Module | Program name | Program ID
Best Denki | web data creation | best_web_data_bat.exe
| web data creation | best_web_data_sub1.exe
| web data creation | best_web_data_sub2.exe
| web data creation | best_web_data_sub3.exe
| web data creation | best_web_data_sub4.exe
| Billing data import | best_ivc_import.exe
| Billing data registration | best_ivc_input.exe
| Billing error correction | best_ivc_err_mnt.exe
| Billing data output | best_ivc_export.exe
| Billing report | best_ivc_report.exe
Module | Program name | Program ID
Bic Camera | Subscription data acquisition | BIC_Import_bat.exe
Best Denki | Subscription import | best_yamada_import.exe
| Billing data import | best_ivc_import.exe
Stream | Subscription import | STRM_import.exe
Mr Max | Subscription import | MrMax_Import.exe
Homac | Subscription import | Homac_import.exe

## DataBase_Details
Prabhu |  |  |  | Ram |  |  |  | sabeena |  |  |  | Bharathi |  |  |  | Vijay
ServerName | Database Name | Table Name | Remarks | ServerName | Database Name | Table Name | Remarks | ServerName | Database Name | Table Name | Remarks | ServerName | Database Name | Table Name | Remarks | ServerName | Database Name | Table Name | Remarks
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | M_category |  |  | MrMAX_Wrn | CLS | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | best_wrn_new_temp | CLS_CODE |  | VIJAYAKUMAR\SQLEXPRESS | S5 | ivc_data
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | Q_DTL |  |  | MrMAX_Wrn | CLS_CODE | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | best_wrn_new_temp | Wrn_ivc |  | VIJAYAKUMAR\SQLEXPRESS | S5 | Shop_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | CLS_CODE |  |  | MrMAX_Wrn | ICDT_DATA | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | best_wrn_new_temp | sp_best_ivc_close_return_01(sp) |  | VIJAYAKUMAR\SQLEXPRESS | S5 | wrn_data
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | INQUIRY_DATA |  |  | MrMAX_Wrn | INQUIRY_DATA | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | best_wrn_new_temp | sp_best_ivc_close_return_01(sp) |  | VIJAYAKUMAR\SQLEXPRESS | S5 | wrn_data_corp
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | CLS |  |  | MrMAX_Wrn | EMPL | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | CLS_CODE |  | VIJAYAKUMAR\SQLEXPRESS | S5 | Wrn_ivc
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | EMPL |  |  | MrMAX_Wrn | M_category | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | CNT_MTR |  | VIJAYAKUMAR\SQLEXPRESS | S5 | Wrn_sub
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | ICDT_DATA |  |  | MrMAX_Wrn | M08_KBN_CAT | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | EMPL |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn | ivc_data
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | ICDT_DTL |  |  | MrMAX_Wrn | SHOP | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | ICDT_DATA |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn | Shop_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | M08_KBN_CAT |  |  | MrMAX_Wrn | STTS_F_UPD | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | ICDT_DTL |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn | wrn_data
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | SHOP |  |  | MrMAX_Wrn | V_cls_003 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | Inport_Err_Log |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn | wrn_data_corp
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | STTS_F_UPD |  |  | MrMAX_Wrn | V_cls_006 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | Inport_log |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn | Wrn_ivc
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | STTS_F_UPD2 |  |  | MrMAX_Wrn | V_cls_014 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | INQUIRY_DATA |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn | Wrn_sub
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | WRN_DATA |  |  | MrMAX_Wrn | V_cls_015 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | LAST_IMPORT_FILE |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_data2 | ivc_data
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | WRN_DATA_UPD |  |  | MrMAX_Wrn | V_cls_016 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | M_category |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_data2 | Shop_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | xa |  |  | MrMAX_Wrn | V_cls_017 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | M_item |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_data2 | wrn_data
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | 02_売上データ |  |  | MrMAX_Wrn | V_cls_018 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | M_maker |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_data2 | wrn_data_corp
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | 01_取込データ |  |  | MrMAX_Wrn | V_cls_019 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | RCV_ERR |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_data2 | Wrn_ivc
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | V_MAX_SEQ |  |  | MrMAX_Wrn | V_cls_020 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | SHOP |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_data2 | Wrn_sub
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | W01_総括表 |  |  | MrMAX_Wrn | V_cls_021 | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | STTS_F_UPD |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | All8_Wrn_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | W02_明細 |  |  | MrMAX_Wrn | V_ICDT_DTL | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | txt_data_all |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | Shop_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | V_Wrn_N30 |  |  | MrMAX_Wrn | WRN_DATA | [5 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | txt_data_all_temp |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | Pref_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | V_Wrn_E30 | [9 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | V_cls024 |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | All8_Memo
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | M07_PB_ﾏｯﾁﾝｸﾞ | [9 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | WRN_DATA |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | All8_Wrn_sub
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | M09_KBN_ITEM | [9 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | WRN_DATA_UPD |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | Cat_mtr
LAPTOP-12JOLGQH\MSSQL | MrMAX_Wrn | V_PB固定 | [9 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | REPAIR_FIN |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | vdr_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | RCV_ERR |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | Wrn_ivc
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new |  |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | Q_DTL |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new | All8_Memo
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | Q_DATA |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | All8_Wrn_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | Q_MASTER |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | Shop_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | sp_mikan(sp) |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | Pref_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | bicdb_new | sp_kan(sp) |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | All8_Memo
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | cls |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | All8_Wrn_sub
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | CLS_CODE |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | Cat_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | err |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | vdr_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | Exception |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | Wrn_ivc
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | fee_mtr |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | item_mtr |  | VIJAYAKUMAR\SQLEXPRESS | best_wrn_new_temp | All8_Memo
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | Memo |  | VIJAYAKUMAR\SQLEXPRESS | STRM | cat_code
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | Shop_mtr |  | VIJAYAKUMAR\SQLEXPRESS | STRM | Cat_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | txt_all |  | VIJAYAKUMAR\SQLEXPRESS | STRM | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | vdr_mtr |  | VIJAYAKUMAR\SQLEXPRESS | STRM | memo
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | WRN_MAIN |  | VIJAYAKUMAR\SQLEXPRESS | STRM | txt_data
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | WRN_SUB |  | VIJAYAKUMAR\SQLEXPRESS | STRM | v_cls_001
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | section_mtr |  | VIJAYAKUMAR\SQLEXPRESS | STRM | v_cls_002
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | line_mtr |  | VIJAYAKUMAR\SQLEXPRESS | STRM | vdr_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | cls_mtr |  | VIJAYAKUMAR\SQLEXPRESS | STRM | wrn_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sub_cls_mtr |  | VIJAYAKUMAR\SQLEXPRESS | STRM | Wrn_sub
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | CX_WRN_SUB
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | CX_WRN_MAIN
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_err_list
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_soukatsu_list
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_soukatsu_list_2
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_anshin_list
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_anshin_list_2
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_CX_list
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_err_list2
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_Shop_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_vdr_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_item_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Homac | sp_section_mtr
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | CNT_MTR
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | EMPL
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | ICDT_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | ICDT_DTL
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | INQUIRY_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | M_category
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | M_maker
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | SHOP
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | STTS_F_UPD
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | WRN_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | WRN_DATA_UPD
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | Q_DTL
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya | V_cls_022
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | CLS
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | EMPL
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | M_category
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | M_maker
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | SHOP
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | STTS_F_UPD
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | WRN_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_1 | V_cls_022
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | EMPL
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | ICDT_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | INQUIRY_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | M_category
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | SHOP
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | WRN_DATA
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_003
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_021
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_020
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_019
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_018
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_017
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_016
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_015
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_014
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | Kuroganeya_temp | V_cls_006
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | aclog
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | acnt
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | CLS_CODE
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | wrn_data
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | WRN_MAIN
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | WRN_SUB
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | sp_search(sp)
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | wrn_data
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | ivc_data
[12 empty] | DESKTOP-A8LLUUG\SQLEXPRESS | s5 | shop_mtr

## Table_Missing
| Program name | Program ID | Database File Name | Table_Name | Remarks
All Denka | Search | best_search_all8.exe | best_wrn_data2.sql | Wrn_ivc | Table Missing, But find table in another two database best_intl.sql and best_wrn_new.sql, So combined two table in to one table reason is field and data type mismatch, Added one field Securities_no
| Report | best_report_all8.exe | best_wrn_data2.sql | Wrn_ivc | Table Missing, But find table in another two database best_intl.sql and best_wrn_new.sql, So combined two table in to one table reason is field and data type mismatch, Added one field Securities_no

## Field Missing
| Program name | Program ID | Database File Name | Table_Name | Field Name | Remarks
All Denka | Search | best_search_all8.exe | best_wrn_data2.sql | wrn_data | isdt
| Search | best_search_all8.exe | best_wrn_data2.sql | wrn_data | isdt2
| Search | best_search_all8.exe | best_wrn_data2.sql | wrn_data | data
| Report | best_report_all8.exe | best_wrn_data2.sql | wrn_data | isdt
| Report | best_report_all8.exe | best_wrn_data2.sql | wrn_data | isdt2
| Report | best_report_all8.exe | best_wrn_data2.sql | wrn_data | data