## SEP-2020
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | QMVAR | DRS Count Design | 100% | Completed
2 | 2020-10-01 | RPA | Testing Data | 100% | Completed
2 | 2020-10-02 |  | Holiday
3 | 2020-10-03 |  | Week off
4 | 2020-10-04 |  | Week off
5 | 2020-10-05 | Soniya | Creating Setup file | 50% | WIP
6 | 2020-10-06 | Soniya | creating Setup file | 100% | Completed
7 | 2020-10-07 | QMVAR | Layout Designing |  | WIP
8 | 2020-10-08 | Emplogin | Adding assests Detatils | 50% | WIP
9 | 2020-10-09 | Emplogin | Adding assests Detatils | 100% | Completed
10 | 2020-10-10 |  | Week off
11 | 2020-10-11 |  | Week off
12 | 2020-10-12 | Emplogin | Adding assests Detatils and responisble view | 100% | Completed
13 | 2020-10-13 | QMVAR | Adding assests Detatils | 100% | WIP
14 | 2020-10-14 | QMVAR | stored management added in Monthly target | 100% | Completed
15 | 2020-10-15 | QMVAR | adding layout in analysis file upload | 70% | WIP
16 | 2020-10-16 | QMVAR | adding layout in analysis file Export | 50% | WIP
17 | 2020-10-17 |  | Week off
18 | 2020-10-18 |  | Week off
19 | 2020-10-19 | QMVAR | adding layout in analysis report and stored managemant | 50% | WIP
20 | 2020-10-20 | soniya | migration testing issue | 100% | Completed
21 | 2020-10-21 | QMVAR | fixing alignment | 30% | WIP
22 | 2020-10-22 | QMVAR | fixing alignment | 50% | WIP
23 | 2020-10-23 | QMVAR | fixing alignment | 60% | WIP
24 | 2020-10-24 |  | Week off
25 | 2020-10-25 |  | Week off
26 | 2020-10-26 |  | Week off
27 | 2020-10-27 | QMVAR | issue fixing |  | WIP
28 | 2020-10-28 | QMVAR | issue fixing |  | WIP
29 | 2020-10-29 | QMVAR | issue fixing |  | WIP
30 | 2020-10-30 | QMVAR | issue fixing |  | WIP

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | QMVAR | QMVAR Fixing |  | Completed
2 | 2020-11-03 | Nmvar | Nmvar Migration |  | WIP
3 | 2020-11-04 | Nmvar | Nmvar Migration |  | WIP
4 | 2020-11-05 | Nmvar | Nmvar Migration |  | WIP
5 | 2020-11-06 | Nmvar | Nmvar Migration |  | WIP
6 | 2020-11-07 | SAT & SUN DAY
7 | 2020-11-08
8 | 2020-11-09 | Nmvar | Nmvar Migration |  | WIP
9 | 2020-11-10 | Nmvar | Nmvar Migration |  | WIP
10 | 2020-11-11 | Nmvar & soniya | Nmvar Migration |  | WIP
11 | 2020-11-12 | soniya | issue fixing |  | WIP
12 | 2020-11-13 | soniya | issue fixing |  | Completed
13 | 2020-11-14 | SAT & SUN DAY
14 | 2020-11-15
15 | 2020-11-16 | soniya | issue fixing |  | Completed
16 | 2020-11-17 | Nmvar | Nmvar Migration |  | Completed
17 | 2020-11-18 | soniya | issue fixing |  | WIP
18 | 2020-11-19 | soniya | issue fixing |  | Completed
19 | 2020-11-20 | personal leave
20 | 2020-11-21 | SAT & SUN DAY
21 | 2020-11-22
22 | 2020-11-23 | soniya | issue fixing |  | Completed
23 | 2020-11-24 | soniya | issue fixing |  | WIP
24 | 2020-11-25 | soniya | issue fixing |  | Completed
25 | 2020-11-26 | nMVAR | Migration |  | WIP
26 | 2020-11-27 | nMVAR | Migration |  | WIP
28 | 2020-11-28 | SAT & SUN DAY
29 | 2020-11-29
30 | 2020-11-30 | nMVAR | nMVAR Migration Activuty report | 70% | WIP
Status
| WIP | WIP
| Pending | Pending
| Completed | Completed
| Hold | Hold

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | nMVAR | nMVAR Migration |  | Completed
2 | 2020-12-02 | nMVAR | nMVAR Activitt Report Desging |  | WIP
3 | 2020-12-03 | nMVAR | nMVAR Activitt Report Desging |  | WIP
4 | 2020-12-04 | nMVAR | nMVAR Activitt Report Desging |  | Completed
5 | 2020-12-05
6 | 2020-12-06
7 | 2020-12-07 | nMVAR | nMVAR Activitt Report Ttesting |  | Completed
8 | 2020-12-08 | nMVAR | nMVAR Setup creating |  | Completed
9 | 2020-12-09 | nMVAR | nMVAR Issue fixing in Activity report |  | WIP
10 | 2020-12-10 | nMVAR | nMVAR Issue fixing in Activity report |  | Completed
11 | 2020-12-11 | QMVAR 2.0 | Design issue fixing |  | WIP
12 | 2020-12-12
13 | 2020-12-13
14 | 2020-12-14 | QMVAR 2.0 | Design issue fixing |  | WIP
15 | 2020-12-15 | QMVAR 2.0 | Design issue fixing |  | WIP
16 | 2020-12-16 | QMVAR 2.0 | Design issue fixing |  | Completed
17 | 2020-12-17 | QMVAR 2.0 | Design issue fixing in scroll bar |  | Completed
18 | 2020-12-18 | QMVAR 2.0 | Design issue fixing in dialog box |  | Completed
19 | 2020-12-19
20 | 2020-12-20
21 | 2020-12-21 | QMVAR 2.0 | Design issue fixing |  | WIP
22 | 2020-12-22 | QMVAR 2.0 | Design issue fixing |  | WIP
23 | 2020-12-23 | QMVAR 2.0 | Design issue fixing |  | Completed
24 | 2020-12-24 | QMVAR 2.0 | Design issue fixing in scroll bar |  | Completed
25 | 2020-12-25
26 | 2020-12-26
27 | 2020-12-27
28 | 2020-12-28 | QMVAR 2.0 | Design issue fixing |  | WIP
29 | 2020-12-29 | QMVAR 2.0 | Design issue fixing |  | Completed
30 | 2020-12-30 | QMVAR 2.0 | Design issue fixing |  | Completed
31 | 2020-12-31 | QMVAR 2.0 | Design issue fixing |  | Completed
Status
| WIP | WIP
| Pending | Pending
| Completed | Completed
| Hold | Hold

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-01 | Holiday
2 | 2021-01-02
3 | 2021-01-03
4 | 2021-01-04 | QMVAR 2.0 | Design issue fixing in firexfox and ie |  | WIP
5 | 2021-01-05 | QMVAR 2.0 | Design issue fixing in firexfox and ie |  | Completed
6 | 2021-01-06 | QMVAR 2.0 | Design issue fixing |  | Completed
7 | 2021-01-07 | Mujistore & nMVAR | Mujistore Design issue fixing and nMVAR testing setup files |  | WIP
8 | 2021-01-08 | Mujistore & nMVAR | Mujistore Design issue fixing and nMVAR testing setup files |  | Completed
9 | 2021-01-09 | Holiday
10 | 2021-01-10
11 | 2021-01-11 | QMVAR 2.0 | Adding sony design |  | Completed
12 | 2021-01-12 | GitHub | Source code adding in Github |  | WIP
13 | 2021-01-13 | GitHub & QMVAR | adding user management and serivce center |  | Completed
14 | 2021-01-14 | Holiday
15 | 2021-01-15
16 | 2021-01-16
17 | 2021-01-17
18 | 2021-01-18 | Emergency leave
19 | 2021-01-19 | QMVAR 2.0 | Create RPA Task |  | WIP
20 | 2021-01-20 | QMVAR 2.0 | Create RPA Task |  | WIP
21 | 2021-01-21 | QMVAR 2.0 | Create RPA Task |  | WIP
22 | 2021-01-22 | QMVAR 2.0 | Create RPA Task |  | Completed
23 | 2021-01-23 | Holiday
24 | 2021-01-24
25 | 2021-01-25 | Laptop ssd changing | Laptop ssd changing |  |  | Laptop servies
26 | 2021-01-26 | Holiday
27 | 2021-01-27 | Laptop Software installed | Laptop Software installed
28 | 2021-01-28 | Holiday
29 | 2021-01-29 | QMVAR 2.0 | Change password screen |  | Completed
30
31
Status
|  | WIP | WIP
|  | Pending | Pending
|  | Completed | Completed
|  | Hold | Hold

## FEB-2021
No | Date | Application | Task | % of completion | Status | Comments
| 2021-02-01 | QMVAR 2.0 | QMVAR Design changing |  | Completed
| 2021-02-02 | QMVAR 2.0 | Issue fixing |  | WIP
| 2021-02-03 | QMVAR 2.0 | Issue fixing |  | Completed
| 2021-02-04 | QMVAR 2.0 | Dashboard Design Changing |  | Completed
| 2021-02-05 | 1.nMVAR 2.QMVAR 2.0 | 1. nMVAR issue fixing 2.Qmvar Issue fixing |  | 1. Completed 2.WIP
| 2021-02-06 | Holiday
2021-02-07
| 2021-02-08 | QMVAR 2.0 | Issue fixing |  | WIP
| 2021-02-09 | QMVAR 2.0 | Issue fixing |  | Completed
| 2021-02-10 | QMVAR 2.0 | Issue fixing |  | WIP
| 2021-02-11 | QMVAR 2.0 | Issue fixing |  | Completed
| 2021-02-12 | QMVAR 2.0 | Adding new change request |  | WIP
| 2021-02-13 | Holiday
2021-02-14
| 2021-02-15 | QMVAR 2.0 | Adding new change request |  | WIP
| 2021-02-16 | 1.nMVAR 2.QMVAR 2.0 | 1. nMVAR issue fixing 2.Qmvar Issue fixing |  | 1.WIP 2.WIP
| 2021-02-17 | 1.nMVAR | 1. nMVAR issue fixing |  | 1. WIP
| 2021-02-18 | 1.nMVAR | 1. nMVAR issue fixing |  | 1. WIP
| 2021-02-19 | QMVAR 2.0 | Adding new change request |  | WIP
| 2021-02-20 | Holiday
2021-02-21
| 2021-02-21 | QMVAR 2.0 | Adding new change request |  | WIP
| 2021-02-23 | 1.nMVAR 2.QMVAR 2.0 | 1. nMVAR issue fixing 2.Qmvar Issue fixing |  | 1.WIP 2.WIP
| 2021-02-24 | 1.nMVAR | 1. nMVAR issue fixing |  | Completed
| 2021-02-25 | QMVAR 2.0 | Adding new change request |  | 1. WIP
| 2021-02-26 | 1.QMVAR 2.0 2.Mujistore | 1.Adding new change request 2.Adding japanese language |  | 1.Completed 2.Completed
| 2021-02-27 | Holiday
2021-02-28

## MAR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-03-01 | 1.Mujistore 2. RPA | 1.Mujistore languge adding 2. RPA Data checking |  | Completed
2 | 2021-03-02 | 1.QMVAR | Issue fixing |  | WIP
3 | 2021-03-03 | 1.QMVAR | Issue fixing |  | Completed
4 | 2021-03-04 | 1.Mujistore | 1.Mujistore issue fixing, adding japanese language |  | Completed
5 | 2021-03-05 | 1.Mujistore | 1.Mujistore issue fixing, adding japanese language |  | Completed
6 | 2021-03-06 | Holiday
7 | 2021-03-07
8 | 2021-03-08 | 1.Mujistore | 1.Mujistore issue fixing |  | WIP
9 | 2021-03-09 | 1.Mujistore 2 .nMVAR | 1.Mujistore issue fixing 2.Active report ddesign changing |  | 1.Completed 2.WIP
10 | 2021-03-10 | nMVAR | Active report ddesign changing |  | WIP
11 | 2021-03-11 | nMVAR | Active report ddesign changing |  | WIP
12 | 2021-03-12 | nMVAR | Active report ddesign changing |  | WIP
13 | 2021-03-13 | Holiday
14 | 2021-03-14
15 | 2021-03-15 | QMVAR | Sony CR |  | Completed
16 | 2021-03-16 | nMVAR | Active report ddesign changing |  | WIP
17 | 2021-03-17 | nMVAR | Active report ddesign changing |  | Completed
18 | 2021-03-18 | 1.Mujistore | 1.Mujistore issue fixing |  | WIP
19 | 2021-03-19 | nMVAR | Active report ddesign changing |  | WIP
20 | 2021-03-20 | Holiday
21 | 2021-03-21
22 | 2021-03-22 | QMVAR 2.O | Adding Apple service center | Completed | Completed
23 | 2021-03-23 | 1.Mujistore | 1.Mujistore issue fixing | Completed | Completed
24 | 2021-03-24 | 1.Mujistore 2.QMVAR V2.O | 1.Mujistore Denied IP address adding 2.QMVAR Design fixing | 1.WIP 2.WIP | 1.WIP 2.WIP
25 | 2021-03-25 | QMVAR 2.O | 1.Adding Apple user generating pdf 2.Design Changing | 1.WIP 2.WIP | 1.WIP 2.WIP
26 | 2021-03-26 | QMVAR 2.O | 1.Adding Apple user generating pdf 2.Design Changing | 1.WIP 2.Completed | 1.WIP 2.Completed
27 | 2021-03-27 | Holiday
28 | 2021-03-28
29 | 2021-03-29 | QMVAR 2.O | 1.Adding Apple user generating pdf | Completed | Completed
30 | 2021-03-30 | 1.Mujistore | 1.Mujistore issue fixing | 1.WIP | 1.WIP
31 | 2021-03-31 | 1.Mujistore 2.QMVAR V2.O | 1.Mujistore 2.QMVAR Design fixing | 1.WIP 2.Completed | 1.WIP 2.Completed
Status
|  | WIP | WIP
|  | Pending | Pending
|  | Completed | Completed
|  | Hold | Hold

## April-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-04-01 | QMVAR 2.O | 1.CR from apple service center |  | Completed
2 | 2021-04-02 | QMVAR 2.O | 1.CR from apple service center |  | Completed
3 | 2021-04-03 | Holiday
4 | 2021-04-04
5 | 2021-04-05 | Muji | 1 Design Changes |  | WIP
6 | 2021-04-06 | Holiday
7 | 2021-04-07 | Muji | 1 Design Changes |  | Completed
8 | 2021-04-08 | nMVAR | Issue Fixed |  | WIP
9 | 2021-04-09 | nMVAR | Issue Fixed |  | Completed
10 | 2021-04-10 | Holiday
11 | 2021-04-11
12 | 2021-04-12 | Muji | 1 Design Changes |  | WIP
13 | 2021-04-13 | Holiday
14 | 2021-04-14
15 | 2021-04-15 | Muji | 1 Design Changes |  | WIP
16 | 2021-04-16 | Muji | 1 Design Changes |  | WIP
17 | 2021-04-17 | Holiday
18 | 2021-04-18
19 | 2021-04-19 | Muji | 1 Design Changes |  | Completed
20 | 2021-04-20 | Muji | 1 Design Changes |  | Completed
21 | 2021-04-21 | Muji | 1 Design Changes |  | Completed
22 | 2021-04-22 | Muji | 1 Design Changes |  | Completed
23 | 2021-04-23 | Muji | 1 Design Changes |  | Completed
24 | 2021-04-24
25 | 2021-04-25
26 | 2021-04-26 | Muji | 1 Design Changes |  | Completed
27 | 2021-04-27 | Muji | 1 Design Changes |  | Completed
28 | 2021-04-28 | RPA | Data validation |  | Completed
29 | 2021-04-29 | Muji | 1 Design Changes |  | Completed
30 | 2021-04-30 | Muji | 1 Design Changes |  | Completed
31 | 2021/04/31
Status
|  | WIP | WIP
|  | Pending | Pending
|  | Completed | Completed
|  | Hold | Hold

## May-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-05-01 | Holiday
2 | 2021-05-02
3 | 2021-05-03 | Muji | 1 Design Changes |  | WHF
4 | 2021-05-04 | Muji | 1 Design Changes |  | Completed
5 | 2021-05-05 | Muji | 1 Design Changes |  | Completed
6 | 2021-05-06 | Muji | 1 Design Changes |  | Completed
7 | 2021-05-07 | Muji | 1 Design Changes |  | Completed
8 | 2021-05-08 | Holiday
9 | 2021-05-09
10 | 2021-05-10 | Muji | 1 Design Changes |  | WHF
11 | 2021-05-11 | Muji | 1 Design Changes |  | Completed
12 | 2021-05-12 | Muji | 1 Design Changes |  | Completed
13 | 2021-05-13 | Muji | 1 Design Changes |  | Completed
14 | 2021-05-14 | Holiday
15 | 2021-05-15
16 | 2021-05-16
17 | 2021-05-17 | Muji | 1 Design Changes | WHF | WHF
18 | 2021-05-18 | Muji | 1 Design Changes |  | Completed
19 | 2021-05-19 | Muji | 1 Design Changes |  | Completed
20 | 2021-05-20 | Muji | 1 Design Changes |  | Completed
21 | 2021-05-21 | Muji | 1 Design Changes |  | Completed
22 | 2021-05-22 | Holiday
23 | 2021-05-23
24 | 2021-05-24 | Muji | Muji change request |  | WHF
25 | 2021-05-25 | Muji | Muji change request |  | WHF
26 | 2021-05-26 | Muji | Muji change request |  | WHF
27 | 2021-05-27 | Muji | Muji change request |  | WHF
28 | 2021-05-28 | Muji | Muji change request |  | Completed
29 | 2021-05-29
30 | 2021-05-30
31 | 2021/04/31
Status
|  | WIP | WIP
|  | Pending | Pending
|  | Completed | Completed
|  | Hold | Hold

## June-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-06-01 | Muji | Muji change request |  | WHF
2 | 2021-06-02 | Muji | Muji change request |  | Completed
3 | 2021-06-03 | Muji | Muji change request |  | WHF
4 | 2021-06-04 | Muji | Muji change request |  | WHF
5 | 2021-06-05 | Holiday
6 | 2021-06-06
7 | 2021-06-07 | Muji | Muji Regerssion |  | Completed
8 | 2021-06-08 | Muji | Muji change request |  | WHF
9 | 2021-06-09 | Muji | Muji change request |  | WHF
10 | 2021-06-10 | Muji | Muji change request |  | Completed
11 | 2021-06-11 | Muji | Muji change request |  | Completed
12 | 2021-06-12 | Holiday
13 | 2021-06-13
14 | 2021-06-14 | Sick Leave
15 | 2021-06-15 | Muji | Adding 1. stream server 2.Store subnet batch 3.streamserverlogs validation |  | Completed
16 | 2021-06-16 | Muji | 1.Username displayed as unknown in top right corner of the page 2.Administration results not showing 3.Store number not in Japanese in View Logs 7. Stream Server View Log--Remarks message not aligned properly and Language not showing correctly 12.Error occurred on Import when the space present before Folder name. 13.Subnet ID --> Subnet Number in Stream Server View Logs |  | Completed
17 | 2021-06-17 | Muji | 1.Username displayed as unknown in top right corner of the page 2.Administration results not showing 3.Store number not in Japanese in View Logs 14.Validation missing for store number in Store subnet batch 15.Change Header in CSV. SSServer--> Stream Server Name, IPAddress--> Server IP Address, BelongingSubnet--> Subnet IP Address |  | Completed
18 | 2021-06-18 | Muji | Align folder management |  | Completed
19 | 2021-06-19 | Holiday
20 | 2021-06-20
21 | 2021-06-21 | Muji | Create New design in User Management |  | WIP
22 | 2021-06-22 | Muji | Create New design in User Management |  | WIP
23 | 2021-06-23 | Muji | Create New design in User Management |  | Completed
24 | 2021-06-24 | Muji | Design changes in folder management |  | Completed
25 | 2021-06-25 | Muji | Create New design in Store Subnet |  | WIP
26 | 2021-06-26
27 | 2021-06-27
28 | 2021-06-28 | Muji | Add old functionality in Store Subnet |  | WIP
29 | 2021-06-29 | Muji | Add old functionality in Store Subnet |  | Completed
30 | 2021-06-30 | Muji | Add delete in storegroup |  | Completed
31

## July-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-07-01 | Muji | Add user old functonlity |  | Completed
2 | 2021-07-02 | Muji | Fixed Regression issues |  | Completed
3 | 2021-07-03 | Holiday
4 | 2021-07-04
5 | 2021-07-05 | Muji | Add delete in Store group |  | WIP
6 | 2021-07-06 | Muji | Add delete in Store group |  | Completed
7 | 2021-07-07 | Muji | change old layout |  | WIP
8 | 2021-07-08 | Muji | change old layout |  | WIP
9 | 2021-07-09 | Muji | change old layout |  | Completed
10 | 2021-07-10 | Holiday
11 | 2021-07-11
12 | 2021-07-12 | Muji | change toVideo Change request old screen page |  | WIP
13 | 2021-07-13 | Muji | change to Video Change request old screen page |  | Completed
14 | 2021-07-14 | Muji | change to Video Change request old screen page issue fixed |  | Completed
15 | 2021-07-15 | Muji | Adding and modify resources |  | Completed
16 | 2021-07-16 | Muji | design changes in media approval page and video all page |  | Completed
17 | 2021-07-17 | Holiday
18 | 2021-07-18
19 | 2021-07-19 | Muji | Add 3 links in video all page |  | WIP
20 | 2021-07-20 | Muji | Add 3 links in video all page |  | Completed
21 | 2021-07-21 | Holiday
22 | 2021-07-22 | Muji | changing colour in mujistore all page |  | Completed
23 | 2021-07-23 | Muji | changing colour in mujistore all page |  | Completed
24 | 2021-07-24 | Holiday
25 | 2021-07-25
26 | 2021-07-26 | MJA | create a login page |  | WIP
27 | 2021-07-27 | MJA | create a login page |  | Completed
28
29
30
31