## JAN-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-01-02 | RPA GSS | 1. Running the Service Order Parts Number extraction task is in progress, so far 260 records were extracted out of 584, whereas above 300 records is yet to fetch and it is going on. | 45% | WIP
2 | 2023-01-03 | RPA GSS | 1.The extracting a parts number from GSPN has been completed for the SSC10, and converted to CSV , and uploaded at QMVAR LIVE successfully for sevice order parts number capture monthly task. | 100% | Completed
|  |  | 2. Running the Service Order Parts Number extraction task is in progress, so far 300 records were extracted out of 859, whereas above 500 records is yet to fetch and it is going on for the SSC11 | 40% | WIP
3 | 2023-01-04 | RPA GSS | 1.The extracting a parts number from GSPN has been completed for the SSC11, and converted to CSV , and uploaded at QMVAR LIVE successfully for sevice order parts number capture monthly task. | 100% | Completed
|  |  | 1. Created a SERVICE ORDER PARTS NUMBER CAPTURING MONTHLY TASK with minimal functionality to download from GSPN site and creating a CSV file and uploading it to QMVAR has been completed, | 50% | WIP
2. Whereas the integration and testing of the post integration is work in progress
4 | 2023-01-05 | RPA GSS | 1. The integration and testing of the post integration has been completed for SERVICE ORDER PARTS NUMBER CAPTURING MONTHLY TASK, and it is running smoothly. | 100% | Completed
|  |  | 2. The integration and testing of the post integration has been completed for INVOICE_UPDATE_EXC_IW_MONTHLY TASK, and it is running smoothly. | 100% | Completed
|  |  | 3. The integration and testing of the post integration has been completed for INVOICE_UPDATE_IW_MONTHLY TASK, and it is running smoothly. | 100% | Completed
5 | 2023-01-06 | RPA GSS | 1. Created a RETURN CREDIT MONTHLY TASK with minimal functionality to download from GSPN site and creating a CSV file and uploading it to QMVAR has been completed, whereas the integration is work in progress | 80% | WIP
|  |  | 2. The integration and testing of the post integration has been completed for INVOICE_UPDATE_OOW_MONTHLY TASK, and it is running smoothly. | 100% | Completed
6 | 2023-01-09 | RPA GSS | 1. The integration and testing of the post integration has been completed for RETURN CREDIT MONTHLY TASK, and it is running smoothly. | 100% | Completed
2. whereas the PARTS_IO_Monthly task is work in progress from mamatha san side.
Note:
Once we receive the customized code for the Parts_IO Monthly task, then we can integrate that and test it and this is the last task from the monthly task.
7 | 2023-01-10 | RPA GSS | 1. The integration and testing of the post integration has been completed for Parts_IO Monthly TASK, and it is running smoothly. | 100% | Completed
|  |  | 2. Development has been completed for the monthly tasks, whereas a long testing is work in progress | 50% | WIP
8 | 2023-01-11 | RPA GSS | 1. A long testing is work in progress for the entire tasks, In addition to that Mohan san has suggested that to implement to run a specific task by controlling it from configuration file as common one and it will be excluded for the Service Order Pending and Parts Number capturing tasks. | 50% | WIP
9 | 2023-01-12 | RPA GSS | 1. A long testing is work in progress for the entire tasks, so far we have tested a six tasks from 26 tasks and remains are in progress. | 60% | WIP
10 | 2023-01-13 | RPA GSS | 1. A New logic has been implemented in the integrated tasks to run only selected (failed) tasks if any tasks are failed and it is success, whereas a long testing is work in progress for the remaining tasks | 70% | WIP
11 | 2023-01-18 | RPA GSS | 1. The task integration testing is work in progress and around 15 tasks are tested and it is running smoothly and another 11 tasks are to be tested and it is work in progress. | 80% | WIP
12 | 2023-01-19 | RPA GSS | 1. A few corrections received from the DRS DAILY TASK due to the record counts are not updated, it has been fixed, tested in all SSCs and it is running smoothly. | 100% | Completed
|  |  | 2. The task integration testing is work in progress and around 18 tasks are tested and it is running smoothly and another 8 tasks are to be tested and it is work in progress. | 80% | WIP
13 | 2023-01-23 | RPA GSS | 1. The task integration testing is work in progress and around 22 tasks are tested and it is running smoothly and another 4 tasks are to be tested and it is work in progress | 90% | WIP
14 | 2023-01-24 | RPA GSS | 1. The testing has been completed for the task integration process for the all tasks and it is running smoothly from download to upload for the daily, weekly, 10 days and monthly tasks. | 100% | Completed
|  |  | 2. A separate task has been created for the Service Order Pending task with Parts number capturing task as it is a long running tasks and it is tested and it is running smoothly | 100% | Completed
15 | 2023-01-25 | RPA GSS | 1. The auto upgradation code has been copied for around 13 tasks to download browser if task fails due to higher version of browser and copy it to respective folder (copied and tested) and another 13 tasks are work in progress, mostly it will be completed by Friday evening. | 60% | WIP
16 | 2023-01-27 | RPA GSS | 1. The auto upgradation code has been copied for all the tasks to download browser if task fails due to higher version of browser and copy it to respective folder (copied and tested) and it is running smoothly. | 100% | Completed
|  |  | 2. The updated integrated tasks has been shared to Mohan san along with tasks list. | 100% | Completed
17 | 2023-01-30 | RPA GSS | 1. Renaming the integrated files (tasks) has been done, and renamed the same at integrated tasks, tested with daily tasks and it is success, whereas the monthly tasks are work in progress. | 65% | WIP
18 | 2023-01-31 | RPA GSS | 1. Renaming the integrated files ( All 26 tasks+ two Master tasks) has been done and the same had been implemented at integrated Master task(file). | 75% | WIP
2. Centralized logs has been implemented to find error location, line number with filename during task executions in all 28 files.
3. Whereas, Except monthly tasks (Service Order Pending and Capturing Parts Number Monthly tasks are yet to be tested)
4. A 25 tasks are tested and only three tasks are work in progress and it is long running test case.
|  |  | 5. MFA (taskname) has been inserted at all 28 files to identify the task before MFA authentication approval. | 100% | Completed

## FEB-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-02-01 | RPA GSS | 1. A few customization has been done at all 28 tasks of the integrated, tested for the daily, 10days, weekly and monthly tasks and all are running smoothly. | 100% | Completed
2. Whereas, Testing of the Parts Number Capturing task is work in progress and it will be completed by 20:00 today and following that, I will share all 28 files to Mohan san tonight.
2 | 2023-02-02 | RPA GSS | 1. Running the Service Order Parts Number extraction task is in progress, so far 300 records were extracted out of 800, whereas above 500 records is yet to fetch and it is going on for the SSC10 and SSC11 | 50% | WIP
2. The both are (SSC10 & SSC11) having around 1500 records and they are fetching in parallelly.
3. These tasks are running contineously
3 | 2023-02-03 | RPA GSS | 1.The extracting a parts number from GSPN has been completed for the SSC10 and SSC11, and converted to CSV , and uploaded at QMVAR LIVE successfully for sevice order parts number capture monthly task. | 100% | Completed
|  |  | 2. A few customizations for the integrated tasks has been completed, tested and they are running smoothly from download to upload smoothly.( Daily, Weekly, 10Days and Monthly tasks), and the updated source code has been shared to Mohan san Now. | 100% | Completed
4 | 2023-02-06 | RPA GSS | 1. A few customization has been done to record a final status of the each task at log file during the master task execution and also preparing a final status report in html format and sending it in email are work in progress( GSPN integrated tasks process) | 60% | WIP
5 | 2023-02-07 | RPA GSS | 1. Status of the each task has been recorded at Task_Success_List csv file once it is completed with success (SSCCODE,Taskname, Status and Date with time etc) and similarly, status of the failures task will be recorded at Task_Failures_List csv file if any task is getting failed during integrated task execution. | 80% | WIP
2. Following that, we will be preparing these files into html report and sending these to the specific emails and it is work in progress
3. Now, we have recorded the task status at Task_Success_List.csv and Task_failures.csv files and it is done for the Integrated GSPN1 tasks(26 tasks)
4. Similarly, we need to do for the Integrated GSPN2 tasks (Service Order Pending and Capturing Parts number monthly tasks (2 tasks)
5. Till now, sending email with attachments has been completed and success, whereas converting these into html reports is work in progress
6 | 2023-02-08 | RPA GSS | 1. Creating a unique processid, applying at all (28 tasks) the tasks as parameters where methods are defined, commenting processid at each task within code, and commenting database update codes at all 28 tasks are done and whereas, a testing is work in progress based on Mohan san suggestion. | 60% | WIP
7 | 2023-02-09 | RPA GSS | 1. A 26 tasks has been tested individually and it is working fine, whereas a 2 tasks (SERVICE Order Pending task and Capturing parts number tasks) are testing is in progress. | 80% | WIP
8 | 2023-02-10 | RPA GSS | 1. A 2 tasks has been tested individually for the Service Order Pending and The capturing parts numbers tasks and it is running smoothly. | 100% | Completed
|  |  | 2. Following that, we have tested a master tasks (Integrated_GSPN1 tasks and Integrated_GSPN2 tasks) and they are running smoothly. | 100% | Completed
|  |  | 3. Creating a report from these tasks,and sending this report in the email body is work in progress. | 90% | WIP
9 | 2023-02-13 | RPA GSS | 1. Creating a report from these tasks,and sending this report in the email body is work in progress. | 95% | WIP
2. Internet issue from 5:30 PM onwards
10 | 2023-02-15 | RPA GSS | 1. Creating a report from 28 tasks has been done for the task status and sending in the email as collective report has been done. | 100% | Completed
2. The updated source code has been shared to Mohan san.
11 | 2023-02-16 | RPA GSS | 1. Renamed the all integrated tasks with uppercase and updated the same at where these are called or imported. | 100% | Completed
2. New logic has been implemented to exit program if no tasks are selected to run, tested and it is running smoothly
3. Checking status of the no data found for all integrated tasks and it is work in progress
4. For the SONY, the certificate to be installed by Mohan san and it is work in progress
12 | 2023-02-17 | RPA GSS | 1. So far, checking no data found has been completed for all daily tasks, whereas checking no data found is work in progress for 10days,weekly and monthly tasks | 50% | WIP
13 | 2023-02-20 | RPA GSS | 1. checking no data found has been completed for all daily, 10days, weekly tasks, whereas checking no data found is work in progress for monthly tasks. | 70% | WIP
14 | 2023-02-21 | RPA GSS | 1. Checking no data found has been completed for all daily, 10days, weekly and monthly tasks. | 100% | Completed
|  |  | 2. Checking with data found test is work in progress | 50% | WIP
15 | 2023-02-22 | RPA GSS | 1. Checking with data found has been completed for the all integrated task and it is working fine for single SSC. | 100% | Completed
|  |  | 2. Checking with data found for the multiple SSCs are work in progress | 50% | WIP
16 | 2023-02-23 | RPA GSS | 1. Checking with data found for the multiple SSCs are work in progress and now it is running for SSC11,SSC3 and SSC7 | 80% | WIP
|  |  | 2. Data issue at GRS-Details during task running due to invoice mismatch, and hence upload was failed and it has been fixed with new logic implementation, and it is running smoothly, | 100% | Completed
3. Whereas this new logic will be implemented at Main task already running (GRS-GRDetails task)
17 | 2023-02-24 | RPA GSS | 1 In GRS_Details Daily task, as we had discussion with Mohan san, we have implemented a new logic to click invoice number/delivery number till last invoice number, tested and it is running smoothly. This has been applied at Integrated task also. The updated source code has been shared. | 100% | Completed
|  |  | 2. In Integrated_GSPN1_DAILY tasks, the 24 tasks are checked with No data found, data found, with single SSC and with Multiple SSCs, and they are running smoothly. | 100% | Completed
The updated source code has been shared.
|  |  | 3. In Integrated_GSPN2_Monthly tasks, (only 2 tasks) due to data availability is less in QMVARTest and long running testing time, we will be checking for no data found and data found for Single SSC and Multiple SSCs from QMVARLive on Monday. | 20% | WIP
18 | 2023-02-27 | RPA GSS | 1.The testing has been completed for no data found and data found cases for the Integrated_GSPN2_Monthly tasks, tested in Single and Multiple SSCs and they are running smoothly. The updated source code has been shared to Mohan san. | 100% | Completed
19 | 2023-02-28 | RPA GSS | 1. A new suggestion from Mohan san has been received for the Integrated_GSPN1_DAILY tasks and Integrated_GSPN2_Monthly tasks to record task count and task success count, nodatacount,datafoundcount, taskfailurecount, uploadsuccesscount, uploadfailurecount status and etc at RPALIVELOG table in database and it is work in progress. | 40% | WIP

## MAR-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-03-01 | RPA GSS | 1. We have done a few changes towards to record in database like taskcount,tasksuccesscount for the integrated tasks record task count and task success count, nodatacount,datafoundcount, taskfailurecount, uploadsuccesscount, uploadfailurecount status at RPALIVESTATUS table. | 70% | WIP
2. nodata found values from srcrecordcount has been changed to -99 and srcstatustxt values has been set as 'NO DATA FOUND" at 26 tasks
3. datafoundtxt values is set as 'Downloaded' to have a uniformity at 26 tasks
4. Upload Success status are made as one 'Upload Success' irrespective of the return message once upload success at 26 tasks
2 | 2023-03-02 | RPA GSS | 1. Created a userdefined function to fetch records from RPALIVELOG table and manipulate the data according to the requirements and the same to be updated at RPALIVESTATUS table (like taskcount and taskcount etc) for the Integrated_GSPN1_DAILY and Integrated_GSPN2_MONTHLY Tasks. | 100% | Completed
|  |  | 2. After implementing this, we have tested it at Integrated_GSPN1_DAILY tasks, and it is updating at database as expected. | 30% | WIP
3. Testing it at Integrated_GSPN2_MONTHLY is work in progress
3 | 2023-03-03 | RPA GSS | 1. The testing has been completed for the Integrated_GSPN2_MONTHLY tasks, Also made unique words are used to record tasks status at 26 tasks and it is recording at database as expected. | 100% | Completed
2. Also tested at MULTIPLE SSCs and it is running smoothly.
4 | 2023-03-06 | RPA SONY | 1. A common login function has been created to do a single login purpose, tested and it is running smoothly towards to creating a minimal functionality. | 100% | Completed
|  |  | 2. A correction (downloading a same file twice) has been fixed as SONY is running at Edge/Chrome browser) at SONY_PARTS_ORDER_LIST_DAILY_V2 task, tested and it is running smoothly. | 100% | Completed
3 |  |  | 3. Based on Mohan san, this has been corrected and implemented at existing task before going into the integration portions.
5 | 2023-03-07 | RPA SONY | 1. As environment setup with new bot is going on to test exisiting tasks of RPA SONY at newbot, and during testing , a few issues are occuring like unwanted characters or contents are created and hence the upload is getting failed, and hence, we are correcting the main tasks before the integration process. | 50% | WIP
2. Today, 11 tasks of the Scheduling Daily task testing is work in progress, during this a five CSV files are failed at uploads, and likewise we have to test at other tasks and it is work in progress
6 | 2023-03-08 | RPA SONY | 1. The task of Scheduling Report Daily has been tested once fixed the uploading issue, now it is downloading and smoothly for all 11 CSV files. | 100% | Completed
2. Created a user-defined function program to converting the 11 excel files to CSV files, tested and it is functioning fine.
3. The updated source code has been shared.
7 | 2023-03-09 | RPA SONY | 1. A few uploading issue at Schedule Report Monthly tasks has been fixed by creating a new userdefined function and it is tested and it is running smoothly for SONY_SCHEDULE_REPORT_MONTHLY_TASKS (it is having four csv files to download and upload) | 100% | Completed
2. Also tested the SONY_APNEWSIS_DAILY and SONY_APNEWSISREPORT_DAILY Tasks at newbot system and it is running smoothly.
8 | 2023-03-10 | RPA SONY | We have tested all the six tasks of SONY, in that only four tasks were having upload issues and it has been fixed, tested and they are running smoothly from download to upload. | 100% | Completed
1. SONY_SCHEDULE_REPORT_DAILY_V1
2. SONY_SCHEDULE_REPORT_MONTHLY_V1
3. SONY_STOCKLIST_MONTHLY_V1
4. SONY_PARTS_ORDER_LIST_DAILY_V2
whereas, a two tasks are running without any issue for the below mentioned:
5. SONY_APNEWSIS_DAILY_V2
6. SONY_APNEWSISREPORT_DAILY_V2
With this, the environment setup also done.
9 | 2023-03-13 | RPA SONY | 1. Created a SONY_PARTS_ORDER_LIST_DAILY_V1 TASK with minimal functionality to download from SONY site and creating a CSV file and uploading it to QMVAR has been completed. | 100% | Completed
|  |  | 2. Creating a SONY_APNEWSIS_DAILY_TASK is work in progress (it contains three tasks like Outbound, Inbound and RPSI Inquiry tasks). | 10% | WIP
10 | 2023-03-14 | RPA SONY | 1. Created a SONY_APNEWSIS_DAILY_TASK with minimal functionality to download or extract informations from the SONY website for the Inbound task, Outbound task and RPSI Inquiry task. | 100% | Completed
|  |  | 2. Converting as CSV files from the extracted informations are done. | 100% | Completed
|  |  | 3. All three CSV files are uploading success. | 100% | Completed
|  |  | 4. Now the updation in database at RPALIVE Log and RPALIVE Status are work in progress for the SONY_APNEWSIS_DAILY_TASK. | 100% | Completed
|  |  |  | 80% | WIP
11 | 2023-03-15 | RPA SONY | 1. The updating in database at RPALIVELOG and RPALIVESTATUS are taking place for the SONY_APNEWSIS_DAILY_TASK and a few more times it has been tested and verified and it is fine. | 100% | Completed
|  |  | 2. Created a SONY_STOCKLIST_MONTHLY_TASK with minimal functionality to download from the SONY website and converting the xls file to CSV and uploading is done, whereas, a few more testing is work in progress. | 60% | WIP
12 | 2023-03-16 | RPA SONY | 1. A few more testing is also done, test completed for SONY_STOCKLIST_MONTHLY TASK and it is running smoothly. | 100% | Completed
|  |  | 2. Created a SONY_SCHEDULE_REPORT_MONTHLY_TASK with minimal functionality to download from the SONY website and converting the xls file to CSV and uploading is done, whereas, a few more testing is work in progress (it is having four csv files). | 80% | WIP
|  |  | 3. In SONY_SCHEDULE_REPORT_DAILY_V1 TASKS, as it has issue during CSV conversions at 'IN_daily_RepairsetSet_NP and it is failed during csv conversion by pandas and Now it has been fixed by placing right encoding approach and it is running and uploading smoothly.(it is having 11 CSV files) | 100% | Completed
13 | 2023-03-17 | RPA SONY | 1. Created a SONY_SCHEDULE_REPORT_DAILY_TASK (it is having a source files 31 and uploading file a 11 csv files) with minimal functionality to download from the SONY website and converting the xls file to CSV and uploading is done, whereas, a few more testing is work in progress. The task is ready to download for previous datefolder data, whereas to download from Friday to Monday datefolder data is work in progress. | 50% | WIP
14 | 2023-03-20 | RPA SONY | 1. With aim of of single login, Dowloading from Friday to Sunday date folders files from the SONY site are completed if a downloading day is Monday, whereas selecting datewise files to convert CSV is work in progress for the SONY_SCHEDULE_REPORT_DAILY_TASK and it is having a 31 Excel files towards 11 output CSV files (totally 93 excels files, 33 CSV files on Mondays to process) | 70% | WIP
15 | 2023-03-21 | RPA SONY | 1. downloaded threedays folder files from the SONY_SCHEDULE_REPORT_DAILY_TASK if the task is running on Mondays and still selecting and converting excel files to CSV files((totally 93 excels files, 33 CSV files on Mondays to process and upload them) are work in progress. | 80% | WIP
16 | 2023-03-23 | RPA SONY | 1. Merging downloaded files from sony site for the SONY_SCHEDULE_REPORT_DAILY_TASK , and converting these files into CSV files towards uploading is completed, whereas to do the same for the multiple datefolder is work in progress. | 90% | WIP
17 | 2023-03-24 | RPA SONY | 1. Testing of CSV conversion of the downloaded files and uploading CSV files for the multiple datefolder files from the sony site are work in progress. | 95%
18 | 2023-03-27 | RPA SONY | 1. Testing of CSV conversion of the downloaded files and uploading CSV files for the multiple datefolder files from the sony site are completed, and it is functioning fine for the SONY_SCHEDULE_REPORT_DAILY_TASK | 100% | Completed
|  |  | 2. Whereas, we need to check that how to record a no data found cases when no datefolders are found at sony site and it is work in progress for the SONY_SCHEDULE_REPORT_DAILY_TASK | 30% | WIP
19 | 2023-03-28 | RPA SONY | 1. The testing with no data found has been completed for the SONY_SCHEDULE_REPORT_DAILY_TASK when a no datefolder exists at SONY site and it is running smoothly. | 100% | Completed
2. Also tested for no data found when a certain files are not presented in the datefolder
|  |  | 3. With this, the customization has been completed for all the SONY tasks, and the integration process is work in progress | 10% | WIP
20 | 2023-03-29 | RPA SONY | 1. Created a master file to integrate all the sony tasks, whereas we have integrated the SONY_SCHEDULE_REPORT DAILY TASKS (which is having 31 excel files and 11 CSV files) on it and the testing is work in progress and another four tasks are yet to be started to integrate. | 20% | WIP
21 | 2023-03-30 | RPA SONY | 1. Integration has been completed for the below mentioned tasks and the same had been tested and they are running smoothly from download to upload. | 100% | Completed
a). Integrated_SONY_SCHEDULE_REPORT_DAILY (31 files and 11 CSV files)
b). Integrated_SONY_APNEWSIS_DAILY (3 CSV files)
c). Integrated_SONY_PARTS_ORDER_LIST_DAILY (1CSV)
Note: The integration has been completed for the Daily tasks, whereas the integration is work in progress for the monthly tasks
22 | 2023-03-31 | RPA SONY | 1. The integration of monthly tasks has been completed for the below mentioned tasks: | 100% | Completed
a). Integrated_SONY_SCHEDULE_REPORT_MONTHLY_V1 (4 files, 4 CSV)
b). Integrated_SONY_STOCKLIST_MONTHLY_V1 (1 File, 1CSV)
Note: The integration has been completed for the Daily and Monthly of the SONY tasks, whereas the testing is work in progress

## APR-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-04-03 | RPA SONY | 1. The testing of the integrated tasks are work in progress of the SONY Tasks | 70% | WIP
|  | RPA GSS | 2. A correction received from the ACTIVITY_DAILY task from Mohan san due to None return from Get_last_run_date function and it has been fixed, tested and it is running smoothly. | 100% | Completed
2 | 2023-04-04 | RPA SONY | 1. The testing of the post integration has been completed, and it is running smoothly from download to upload smoothly of the SONY Tasks | 100% | Completed
2. The below mentioned tasks of Daily and Monthly are integrated:
1. SONY_SCHEDULE_REPORT_DAILY_V1
2. SONY_SCHEDULE_REPORT_MONTHLY_V1
3. SONY_STOCKLIST_MONTHLY_V1
4. SONY_PARTS_ORDER_LIST_DAILY_V2
5. SONY_APNEWSIS_DAILY_V2
6. The Master file is INTEGRATED_SONY_TASKS_V1
3 | 2023-04-05 | RPA SONY | 1. Supported to Mohan san to implement and testing the Sony integrated tasks | 100% | Completed
|  |  | 2. Downloaded and installation are completed for the wordpress framework | 100% | Completed
|  |  | 3. Research and Development for the word press framework is going on. | 10% | WIP
4 | 2023-04-06 | RPA GSS | 1. Research and Development for the word press framework is going on.
2. Learned about that How to download and install the Plugins and include to the site to create a new page and etc.
5 | 2023-04-10 | RPA GSS | 1. A correction received from Activity Daily task due to logging error (unicode character error from the status text) and it has been fixed by encoding in log file with new approach and it is tested at few SSCs and it is running smoothly. | 100% | Completed
|  |  | 2. Research and Development is in progress about wordpress for the plugins (https://wordpress.org/plugins/woocommerce/) |  | WIP
6 | 2023-04-11 | RPA GSS | 1. A few modifications request has been received from Mohan san for the PARTS_OVERDUE_MONTHLY_PARTS task and it is work in progress.
|  |  | 2. Downloading/Exporting the stockoverview files from QMVAR LIVE for four month has been completed and the same had been moved to temp folder for the PARTS_OVERDUE_MONTHLY_PARTS task |  | WIP
3. Generating start date and end date for the three months dynamically done etc
7 | 2023-04-12 | RPA GSS | 1. A two user-defined functioins were created to generate four month's start date dynamically to apply in few places | 50% | WIP
a). getting_start_date_four_months()
b). get_month_year_nums()
2. A few customizations are work in progress from downloading from QMVAR and continuing etc
3. Recording during task execeution in database is work in progress
8 | 2023-04-13 | RPA GSS | 1 . A few customisations has been completed for download from GSPN and download from QMVAR , and the testing is work in progress for the PartsTurnOver task | 70% | WIP
2. Recording task execution at RPALIVESTATUS and RPALIVELOG has been completed for downloading from GSPN, whereas recording task execution for export from QMVAR is work in progress
9 | 2023-04-17 | RPA GSS | 1. The customization and testing has been completed for the PartsTurnOver task for single SSC and multiple SSCs and they are functioning smoothly as expected. | 100% | Completed
2 The updated source code has been shared.
10 | 2023-04-18 | RPA GSS | 1. A few styles applying at PartsTurnOver Daily and Monthly reports using Openpyxl and Pandas library and sending these reports in the email as attachment are work in progress. | 50% | WIP
2. A two user defined functions are created towards these reports.
11 | 2023-04-19 | RPA GSS | 1. Creating a monthly report for the PartsTurnOver process, and sending it in the email has been completed, tested for a single SSC, whereas testing for the Multiple SSCs is work in progress. | 70% | WIP
12 | 2023-04-20 | RPA GSS | 1. Creating a daily report for the PartsTurnOver process, and sending it in the email has been completed, tested for a single SSC, whereas testing for the Multiple SSCs is work in progress. | 70% | WIP
2. we are working on to send an email with 12 files for all SSCs as one email.
13 | 2023-04-21 | RPA GSS | 1. The testing with multiple SSCs has been completed for the PartsTurnOver process to create daily and monthly reports and the same will be attached as one email for all the SSCs and it is running smoothly. | 100% | Completed
2. A separate user-defined function has been created to send email with all attachment as one
3. Once the email sent, all the reports will be moved to backup folder dynamically.
4. The updated source code has been shared to Mohan san.
14 | 2023-04-25 | RPA GSS | 1. A correction received for the Parts Turn Over Task due to QMVAR failed and it has been fixed, tested and it is running smoothly | 100% | Completed
|  | Augmented Reality | 1. Doing Research and development about Augmented Reality is work in progress
15 | 2023-04-26 | Augmented Reality | 1. Doing Research and development about openCV library for Augmented Reality
|  |  | 2. A few customizations has been done like targetdate generating dynamically for the SRN Weekly Task process. | 20%
3. A scheduler approach has been implemented and whereas the testing and other steps are work in progress
16 | 2023-04-27 | RPA GSS | 1. Generating a list and finding index position to insert blank rows at after 60th days, at 90th days has been completed by creating a user-defined functions for the SRN Weekly Task process | 100%
2. total value has been calculated for the Purchase total column
3. Whereas the other steps are work in progress
17 | 2023-04-28 | RPA GSS | 1. The email sending issue at server side was the None error from cc mail address, it has been fixed, tested and it is running smoothly and Mohan san also informed us that now it is sending the email attachments smoothly for the PartsTurnOver process. | 100% | Completed
|  |  | 2. A three user-defined functions has been created towards applying styles, inserting blank rows at different places, applying different coloring based on days count for the SRN Weekly reports and integrated the same code and the testing is work in progress. | 70% | WIP
3. Whereas sending these reports as attachment in the email and other calculations for the stock overview reports are work in progress

## MAY-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-05-02 | RPA GSS | 1. A Correction Received for the Activit Task Daily failed due to unspecified error, whereas after applying log with try/except, it is tested in multiple SSCs and it is functioning smoothly, | 100% | Completed
|  |  | 2. One user-defined function has been defined to apply style and to get summation of total stock value and it is implemented at SRN weekly task and the testing is work in progress | 60% | WIP
2 | 2023-05-03 | RPA GSS | 1. The ACTIVITY task has been executed for the date from 28-04-2023 to 02-05-2023 and uploaded at QMVARLIVE for the SSC3,SSC6,SSC8,SSC9,SSC10 and SSC11. (five days) | 100% | Completed
|  |  | 2. A correction received for the Activity task due to sql query is returning None at Mohan san system from database and whereas, the same task is running at newbot, and after had a discussion with Mohan san, we have to decided to not to check about task last run date, and will be implementing newly if the day is monday it should run from friday to sunday separately for each day and otherwise it will run on the previous day date, and it is work in progress. | 60% | WIP
3 | 2023-05-04 | RPA GSS | 1. Based on the discussion had with Mohan san, we have implemented a new logic to generate 3 days list if the dayname is 'Monday or else it will generate a Previous day date to run task as usual for the ACTIVITY_DAILY Task. | 100% | Completed
2.It is tested with Single and Multiple SSCs and it is running smoothly.
|  |  | 3. Created a user-defined function to send email with attachments for all SSCs and Single SSCs and the same had been implemented and the testing has been completed for the single SSC and whereas testing at multiple SSCs is work in progress for the SRN Weekly process task | 70% | WIP
4 | 2023-05-05 | RPA GSS | 1. Created a Final reports for the SRN weekly process has been completed, file moving to backup, little beauty correction also compeleted and whereas a testing with multiple SSCs is going on | 90% | WIP
|  | AUG REALITY | 2. Usage of system camera with OpenCv has been studied and accessed, a video has been recorded and stored it using OpenCV module and the reading the image and converting into gray color and stored it are done and other steps are in progress.
5 | 2023-05-08 | RPA GSS | 1. The testing at SRN weekly task process has been completed at multiple SSCs, generating reports, applying styles, formatting colums and sending these reports as single attachment in email smoothly and the updated source code has been shared. | 100% | Completed
|  | AUG REALITY | 2. Doing Research and development about the Augmented Reality in OpenCV and learned about removing background image and adding new background images to the foreground images.
6 | 2023-05-09 | RPA GSS | 1. A few environment setup has been done and tested the olbbot machine with GSPN task, it is running smoothly. | 100% | Completed
|  | AUG REALITY | 2. Doing Research and development about the Augmented Reality using OpenCV python and it is in progress |  | WIP
7 | 2023-05-10 | RPA GSS | 1. A few enhancement has been requested by Mohan san at SRN Weekly task process to place purchase_total and total_stock_value in the email body and the same had been implemented, a few fine tuning about sending email structure and it is also done. Now the testing is in progress. | 80% | WIP
|  | AUG REALITY | 2. Doing Research and development about the Augmented Reality using OpenCV python and it is in progress based on the feedback received from the meeting today.
8 | 2023-05-11 | RPA GSS | 1. A beauty correction received for the SRN weekly task to display the inline table at email body, it has been completed, testing is work in progress | 90% | WIP
|  | AUG REALITY | 2. Doing Research and Development Augmented Reality is in progress
9 | 2023-05-12 | RPA GSS | 1. A few correction in email body table has been done and testing with multiple SSCs are work in progress as long run process and each SSC will run for minimum 2 hours during testing at GSPN site. | 95% | WIP
2. Doing Research and Development Augmented Reality is in progress (accessing mobile with system)
10 | 2023-05-15 | RPA GSS | 1. The testing at SRN weekly task process with multiple SSCs is going on and it will be completed by 9:00pm tonight. | 100% | Completed
2. Doing Research and Development about Augmented Reality is in progress (accessing mobile with system and applying background images are done) whereas the a few blurring or distortion at livestream videos occurring and yet to be removed
|  |  | 3. A correction received from the activity daily task, and it has been fixed, tested and it is running smoothly. | 100% | Completed
11 | 2023-05-16 | AUG REALITY | 1. Doing Research and Development about Augmented Reality and the learning is in progress
2. Using system webcam, we could capture the live and remving background, and adding new background images
3. Using mobile IP WebCam app, we could capture the live and removing background, adding a new background for the live is done.
4. Loading the image from the system and removing the background and adding a background image are done.
12 | 2023-05-17 | AUG REALITY | 1. Doing Research and Development about Augmented Reality is in progress (changing background video of live stream to local video and etc) |  | WIP
13 | 2023-05-18 |  | Leave due to urgent
14 | 2023-05-19 | RPA GSS | 1. A few corrections received from the Warranty and GRS-Daily tasks failed due to server down, and it has been fixed by new logic to run task at any machine and tested it at few SSCs and they are running smoothly. | 100% | Completed
|  | AUG REALITY | 2. Doing Research and Development about Augmented Reality and continuing the learning process
15 | 2023-05-22 | AUG REALITY | 1. Doing Research and Development about Augmented Reality and continuing the learning process
|  |  | 2. Around 80% has been completed for the POC and other steps are work in progress for the Augmented Readlity. | 80% | WIP
16 | 2023-05-23 | AUG REALITY | 1. Doing Research and Development about Augmented Reality and continuing the learning process
|  |  | 2. The first POC towards Augmented Readlity has been completed with different overlay images. | 100% | Completed
17 | 2023-05-24 | AUG REALITY | 1. Doing Research and Development about Augmented Reality and continuing the learning process (multiple image overlay at background process is work in progress) | 60% | WIP
18 | 2023-05-25 | AUG REALITY | 1. Doing Research and Development about Augmented Reality and continuing the learning process (multiple images has been placed as overlay at single background image) 2. Multiple images overlay done | 100% | Completed
19 | 2023-05-26 | AUG REALITY | 1. Doing Research and Development about Augmented Reality and continuing the learning process using Unity software.
20 | 2023-05-29 | AUG REALITY | 1. Went to Mambalam to collect my system due to hard disk weak and replaced this with new hard disc, installed OS and installing the all other softwares like python with related libraries, Unity software for Augmented Reality etc.
2. Learning Unity software towards Augmented Reality
21 | 2023-05-30 | AUG REALITY | 1. Learing Unity Software towards Augmented Readlity etc (Learning about Menu and Tools in Unity software)
22 | 2023-05-31 | AUG REALITY | 1. Doing Research and Development to convert python App to Apk for mobile Android and the learning is in progress
2. Also, we need to study the Kivy module to create app for the same and it is in progress.

## JUNE-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-05-31 | AUG REALITY | 1. Doing Research and Development to convert python App to Apk for mobile Android and the learning is in progress
2. Also, we need to study the Kivy module to create app for the same and it is in progress.
2 | 2023-06-01 | RPA GSS | 1. A few correction received from the DRS daily task due to file existing error. | 100% | Completed
The file exist error during file renaming and moving to download folder once download is complete has been fixed by using shutil.move(fname,dname) instead of os.rename(fname,dname) with try/except along with log recording and it is tested at few SSCs and it is functioning smoothly at DRS Daily task.
2. The Service Order Pending Monthly task is running for the SSC11 and it is in progress
|  | AR | 3. The converting background applying task to dynamic responsive task is work in progress | 40% | WIP
3 | 2023-06-02 | AR | 1. The converting background applying task to dynamic responsive task is work in progress
2. Changing the background has been completed dynamically, whereas changing background by click event is work in progress
4 | 2023-06-05 | AR | 1. Changing the background has been completed dynamically using Flask framework and saving the combined image has been completed, |  | WIP
5 | 2023-06-06 | AR | 1. Taking selfie with new background has been completed, whereas other steps are work in progress to render it in web browser | 80% | WIP
6 | 2023-06-07 | AR | 1. Taking selfie with new background has been completed, whereas other steps are work in progress to render it in web browser
2. Doing research and development to get clear foreground video after applying the background image and it is learning in progress
3. Background subtraction from video stream is work in progress
7 | 2023-06-08 | AR | 1. Doing research and development to get clear foreground video after applying the background image and it is learning in progress
2. Background subtraction from video stream is work in progress
8 | 2023-06-09 | AR | 1. Doing research and development to get clear foreground video after applying the background image and it is learning in progress
2. Studying the color applying to create foreground image is work in progress
9 | 2023-06-12 | AR | 1. Installation has been completed for XAMPP, and placed the files which received from Kalairasan san, it is working at my system
2. Installation of XAMPP at New bot has been done based on Mohan san, and still a few issues at newbot, and the bot machine to be to test from remotely,
3. My system can be accessed as server, whereas the webcam is not accessing at client side and yet to be studied to fix this.
10 | 2023-06-13 | AR | 1. The distortion issue at video stream after changing the background, trying to fix it and it is learning in progress
11 | 2023-06-14 | AR | 1. The distortion issue at video stream after changing the background, trying to fix it and it is learning in progress
2. Also we need to study about Google colab to fix this this and it is yet to start.
12 | 2023-06-15 | AR | 1. The learning the OPENCV Framework towards to get clear image after changing the background with different approach and it is learning in progress.
2. Also we have tried to get clear foreground image after applying twice background based on Mamatha san, still the issue exists.
13 | 2023-06-16 | AR | 1. Doing Research and development towards to get a clear video without distortions after changing the removing background using OpenCV framework and etc.
2. Supported to responsive design to take a picture with proper screen size.
14 | 2023-06-19 | AR | 1. Doing Research and development in OpenCV framework to change realtime background and to get a clear foreground video and it is learning progress.
2. Also studying about Flask with OpenCV.
15 | 2023-06-20 | AR | 1. Supporting to responsive design to change background and best fit to screen at mobile device.
2. Doing research and development about Flask with OpenCV towards responsive designings related to Augmented Reality.
16 | 2023-06-21 | Web Dev | 1. Doing Research and studying about FLASK Frame work towards web development
2. Studying and Analysing the CrowdFunding document and progress in analysing
3. Supporting to responsive design for the AR
17 | 2023-06-22 | CrowdFunding | 1. Studied and Analyzed the CrowdFunding document
2. Installation of Visual Studio 2019 has been completed and the learning is in progress
3. Installation of SSMS 19 mssql server has been completed
18 | 2023-06-23 | DOTNET/CrowdFundig | 1. Learning the ASP.NET is in progress.
2. Learned About ASP.NET web controls
19 | 2023-06-26 | DOTNET/CrowdFundig | 1. Learning the ASP.NET is in progress.
2. Learning the registration form with database in ASP.NET is in progress
20 | 2023-06-27 | DOTNET/CrowdFundig | 1. Learning the registration form with database in ASP.NET is in progress (CRUD Operation means Create, Read, Update and Delete operation at MSSQL Server using ASP.NET with C#)
2. Data viewing in the GRIDVIEW
21 | 2023-06-28 | Android Studio | 1. Downloading and Installation of the Android Studio has been completed successfully.
2. Based on Matheshwari san's instruction 'chigmunk version of Android studio has been (old version) installed
3. The learning process about Android Studio is in progress
22 | 2023-06-30 | Android Studio | 1. Learnt about that how to create a simple application in android studio, studied about folder structures and details about each folder and its important, and how to call the text and apply in layout dynamically and other is learning is in progress

## JULY-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-07-03 | Android | 1. Doing Research and Development about Android and the learning process is progress
2. Learnt, Practised and developed a simple calculator Application and viewed in system emulator
2 | 2023-07-04 | Wordpress | 1. The XAMPP server has been installed (Apache and MySQL)
2. The Wordpress framework has been installed
3. The GiveWP plugin is installed towards crowd fund raising site development
4. Please find the simple report about the forementioned points as attachment.
5. styling and color are yet to be applied.
3 | 2023-07-05 | Android | 1. Created a simple login App without database and without registration
2. Exported a Calculator App as APK file and installed at Android mobile, tested and it is functioning smoothly
3. Doing Research and Development about Android and the learning process is progress
4 | 2023-07-06 | Android | 1. Doing Research and Development about Android and the learning process is progress
2. Learnt, Practised and developed using click events from one page to another page, and about design components,
3. Learnt about to create a multiple activity and practiced
5 | 2023-07-07 | Android | 1. Doing Research and Development about Android and the learning process is progress
2. CRUD operation in Android Studio is in progress
6 | 2023-07-10 | Android | 1. Learnt about CRUD operation with SQLite in Android studio.
2. KT has been received about Instant fix and splash screen for the Hayaai app.
7 | 2023-07-11 | Android | 1. Learnt about ButterKife style method in Android studio.
2. Learning is in progress for the recyclerview
3. KT has been received for the folder structure and views etc from Matheswari san.
8 | 2023-07-12 | Android | 1. Learning wordpress and a few customized at plugins for the Crowdfunding site in wordpress and it is in progress
2. KT has been received about B2B App for a few menus
3. Learning and doing practice about android studio
9 | 2023-07-13 | Android | 1. Learning wordpress and a few customized at plugins for the Crowdfunding site in wordpress and it is in progress
2. Today, there was no KT for B2B from Matheswari san due to she is busy in other works , she will continue from tomorrow onwards.
3. Supported to install wordpress, plugins etc to Prabhu san and explained to him and also shared to him from completed one.
10 | 2023-07-14 | Android | 1. The KT has been received from Matheswari san about B2B and etc.
2. Supported towards Crowdfunding site,(plugins, editing and etc)
3. Learning and doing practice about fragments in android studio.
11 | 2023-07-17 | CrowdFunding | 1. Learning wordpress and creating a report for donor list (donation received reports like donation id, donor firstname, donor date, donor amount for the admin's rights.
2. SQL query has been created to get donor report
3. KT has been received to convert from Angularweb to Android.
4. Installation of Angular, Node.js are in progress.
12 | 2023-07-18 | CrowdFunding | 1. Learning and developing a crowdfunding site using wordpress
2. Report generation of the donor detailed reports is in progress
13 | 2023-07-19 | Android | 1. Setting up envionmental for Jdk, android, gradle and testing is in progress and etc
2 Installation of Node.js, Angular had been completed, tested and it is functioning smoothly.
14 | 2023-07-20 | Android | 1. Converting (Build) Angular web to Android APK had been done.(all steps are done)
2. Created APK has been installed at Mobile, it is success
3. Login with a provided credential is success in mobile app of Penna care..
4. Learning about git cloning is in progress
15 | 2023-07-21 | Android | 1. Learning and developing about Fragments in android and the learning is in progress
2. Practicing and building from Angular web to Android APK
16 | 2023-07-24 | Android | 1. Supported to wordpress towards crowdfund to create a in popup after click at Report meu
2. Learnt about App publishing in Google play store from Matheswari san (KT)
3. Learnt about push notifications at firebase from Matheswari san (KT)
17 | 2023-07-25 | Android | 1. Supported to wordpress towards crowdfund to create a in popup after click at Report menu and downloading as excel reports
2. Practicing and building from Angular web to Android APK with little modification from the source,
3. Practicing the debug with mobile app for the Penna care
18 | 2023-07-26 | Android | 1. Learning and developing about Angular web and it is in progress
2. Just started basic of Angular
19 | 2023-07-27 | Android | 1. Created a documents to build from Angular to Android APK
2. Practicing the debug with mobile app for the Penna care
3. Testing a Hayaa App and checking with Physical devices
4. Testing with B2B is in progress
20 | 2023-07-28 | Android | 1. Testing with B2B has been completed after creating or build an APK
2. Testing with HAYAAY APP done
3. Updated the Angular to Android APK build documents
4. A few doubts are clarified about Server Key from the Google console
5. Updated build documents has been shared to Karan san.
6. RPA LIVE SOURCE CODE has been received from Mohan san today.
21 | 2023-07-31 | Android | 1. Learning and Practising Angular etc
2. Learning about Fragments in Android
|  | RPA GSS | 1. Task executed for SSC11 of the Service Order Pending Monthly task.

## AUG-23
No | Date | Application | Task | % of completion | Status | Comments
1 | 2023-08-01 | Angular | 1. Strurcture of folders and code analyzing about angular to android done
2. KT has been given to Karan san to build from Angular to Android
3. KT has been received from Karan san about iOS build, whereas I need to sit next him to practice further
4. Learning Angular is in progress.
2 | 2023-08-02 | DOTNET | 1. Learning process is in progress about the C#.
2. Visual Studio has been updated to include Winows Application support
3. Learnt about data types in the C# and it is in progress
4. Simple windows application studied and created with a few controls in winform.
3 | 2023-08-03 | RPA GSS | 1. A few corrections received for the below mentioned tasks due to the downloaded filename has been changed at GSPN site and hence these tasks are failed during CSV file creation and it has been fixed, tested and they are running smoothly.
2. DRS DAILY TASK
3. POC DAILY TASK
4. ServiceOrderCancelled DAILY Task
5. PR SUMMARY DAILY TASK
4 | 2023-08-04 | RPA GSS | 1. A few corrections received for the below mentioned tasks due to the downloaded filename has been changed at GSPN site and hence these tasks are failed during CSV file creation and it has been fixed, tested and they are running smoothly.
2. PRSUMMARY-10DAYS TASK
3. PRDETAILS-10Days TASK
4. ServiceOrderCancelled DAILY Task
5. Invoice Update OOW weekly task
5 | 2023-08-07 | RPA GSS | 1. A few corrections received from the Service Order Cancelled Daily task due to table collapsed at excel file during download, and it has been fixed tested and it is running smoothly
2. A few corrections received from SRNCustom(PARTS_OVERDUE_MONTHLY_NoneCustom_23Aug07) monthly task, and it is work in progress
3. Learning about windows applications in DOTNET and etc
6 | 2023-08-08 | RPA GSS | 1. A few corrections received for the ServiceOrderCancelled Daily task, the issue has been fixed, whereas the record count is mismatching and the validation is going on. | 100% | Completed
2. A few corrections received from SRNCustom(PARTS_OVERDUE_MONTHLY_NoneCustom_23Aug07) monthly task, and it is work in progress
7 | 2023-08-09 | RPA GSS | 1. Doing and checking, and testing the SRNCustom(Parts_OverDue_monthly task) due to contents, filename issue are in progress and it is a big process and each SSC will run for two and half hours. | 40% | WIP
8 | 2023-08-10 | RPA GSS | 1. The Correction, downloaded filename issue has been fixed, tested at SRNCUSTOME(Parts_overdue_monthly) task and it is running smoothly | 100% | Completed
|  |  | 2. A few correction, downloaded filename issue, contents issue has been fixed, tested at SSC3,SSC10,SSC11 and it is running from download to upload smoothly (implemented to support Export/DailyReportstatus.xls files.). | 100% | Completed
|  |  | 3. A few correction is received for the Invoice update Exc Iw Monthly task and it is work in progress | 10% | WIP
9 | 2023-08-11 | RPA GSS | A few corrections received due to downloading filename changed at GSPN site during download has been fixed for the below mentioned tasks, tested and they are running smoothly | 100% | Completed
1. INVOICE_UPDATE_OOW_MONTHLY_V2 TASK
2. INVOICE_UPDATE_EXC_IW_MONTHLY_V2 TASK
3. INVOICE_UPDATE_IW_MONTHLY_V2 TASK
|  |  | 4. ACTVITY DAILY TASK is work in progress | 10% | WIP
10 | 2023-08-14 | RPA GSS | A few corrections received due to downloading filename changed at GSPN site during download has been fixed for the below mentioned tasks, tested and they are running smoothly
|  |  | 1. Activity daily task | 100% | Completed
|  |  | 2. SERVICE_ORDER_PARTS_NO_CAPTURE_MONTHLY_HARD_V1_23Aug14 is work in progress | 20% | WIP
|  |  | 3. SERVICE_ORDER_PENDING_MONTHLY task is work in progress | 40% | WIP
11 | 2023-08-16 | RPA GSS | 1. A few correction received for the Service Order Cancelled Daily task, it has been fixed (content issue and filename issue), tested and it is running smoothly. | 100% | Completed
|  |  | 2. SERVICE_ORDER_PARTS_NO_CAPTURE_MONTHLY_HARD_V1_23Aug14 task is having issue of (filename issue during download) hass been fixed,the testing is going on and it is work in progress | 80% | WIP
3. SERVICE_ORDER_PENDING_MONTHLY task is work in progress

## SEP-23
No | Date | Application | Task | % of completion | Status | Comments

## OCT-23
No | Date | Application | Task | % of completion | Status | Comments
1

## NOV-23
Date | Application | Task | % of completion | Status | Comments

## DEC-23
Date | Application | Task | % of completion | Status | Comments