## APR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 01/05/2021 | WeekEnd
2 | 02/05/2021 | WeekEnd
3 | 03/05/2021 | Mujistore | File Import Implementation going on
4 | 04/05/2021 | Mujistore | File Import Csv File converting going on
5 | 05/05/2021 | Mujistore | Adding columns and read and write csv file in code going on
6 | 06/05/2021 | Leave | SickLeave
7 | 07/05/2021 | Leave | SickLeave
8 | 08/05/2021 | WeekEnd
9 | 09/05/2021 | WeekEnd
10 | 10/05/2021 | Leave | SickLeave
11 | 11/05/2021 | Leave | SickLeave
12 | 12/05/2021 | Leave | SickLeave
13 | 13/05/2021 | Mujistore | Video Deploy status update not populated, analyse the code
14 | 14/05/2021 | Holiday | Ramzan
15 | 15/05/2021 | WeekEnd
16 | 16/05/2021 | WeekEnd
17 | 17/05/2021 | Mujistore | video Deploy status update not populated and video All option video populate not working, going on
18 | 18/05/2021 | Mujistore | video Deploy status update not populated and video All option video populate not working, code changed
19 | 19/05/2021 | Mujistore | video Deploy status update not populated and video All option video populate not working, tested and sent to deployment
20 | 20/05/2021 | Mujistore | Video All menu, scrollbar gather requirement and analyse the code
21 | 21/05/2021 | Mujistore | video All menu, scrollbar gather requirement, code changes going on
22 | 22/05/2021 | WeekEnd
23 | 23/05/2021 | WeekEnd
24 | 24/05/2021 | QmVar | 6 issues fixed in QMVar and Mujistore development stopped
25 | 25/05/2021 | QmVar | 5 issues fixed in QmVar
26 | 26/05/2021 | QmVar | 6 issues fixed in Qmvar and sent to deployment
27 | 27/05/2021 | QmVar | 8 issues fixed in QMVAR
28 | 28/05/2021 | QmVar | 18 issues fixed in QMVAR
29 | 29/05/2021 | WeekEnd
30 | 30/05/2021 | WeekEnd
31 | 31/05/2021