## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | VASTU | Checking date time issue | 100% | Completed
2 | 2020-10-01 | RPA Dotnet | Project set up | 100% | Completed
3 | 2020-10-05 | QMVAR | DRS Count - Saw Discount changes and Issue | 100% | Completed
4 | 2020-10-06 | QMVAR | DRS Count - Saw Discount Summary & Details | 50% | WIP
5 | 2020-10-07 | QMVAR | DRS - Daily Revenue | 20% | WIP
6 | 2020-10-08 | QMVAR | DRS - Daily Revenue | 40% | WIP
7 | 2020-10-09 | QMVAR | DRS - Daily Revenue | 50% | WIP
8 | 2020-10-12 | QMVAR | DRS - Daily Revenue | 65% | WIP
9 | 2020-10-13 | QMVAR | DRS - Daily Revenue | 80% | WIP
10 | 2020-10-14 | QMVAR | DRS - Daily Revenue | 100% | Completed
15 | 2020-10-15 | SONIA | Go through Soica Project MDB File Application | 100% | Completed
16 | 2020-10-16 | SONIA | Check Suma Email and Start work application | 10% | WIP
17 | 2020-10-19 | SONIA | Access DB Migration - BIC CAMERA - 1 | 10% | WIP
18 | 2020-10-20 | SONIA | Access DB Migration - BIC CAMERA - 1 | 30% | WIP
19 | 2020-10-21 | SONIA | Access DB Migration - BIC CAMERA - 1 | 50% | WIP
20 | 2020-10-22 | SONIA | Access DB Migration - BIC CAMERA - 1 | 60% | WIP
21 | 2020-10-23 | SONIA | Access DB Migration - BIC CAMERA - 1 | 70% | WIP
22 | 2020-10-27 | SONIA | Access DB Migration - BIC CAMERA - 1 | 85% | WIP
23 | 2020-10-28 | SONIA | Access DB Migration - BIC CAMERA - 1 | 100% | Completed
24 | 2020-10-29 | SONIA | Analyze DB Migration for without Form DB
25 | 2020-10-29 | QMVAR | Help Balaji San for PL Tracking Sheet SONY
Status
WIP
Pending
Completed
Hold

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | SONIA | Changes completed in Bic_Report_soukatsu Project | 100% | Completed
2 | 2020-11-03 | SONIA | Set up file created for BIC CAMERA Module | 100% | Completed
3 | 2020-11-04 | SONIA | Analysis Bic Report Ivc | 100% | Completed
4 | 2020-11-05 | SONIA | Working Bic Report Ivc | 10% | WIP
5 | 2020-11-06 | SONIA | Working Bic Report Ivc | 20% | WIP
6 | 2020-11-09 | SONIA | Working Bic Report Ivc | 30% | WIP
7 | 2020-11-10 | SONIA | Working Bic Report Ivc | 40% | WIP
8 | 2020-11-11 | SONIA | Working Bic Report Ivc | 60% | WIP
9 | 2020-11-12 | SONIA | Working Bic Report Ivc | 80% | WIP
10 | 2020-11-13 | SONIA | Working Bic Report Ivc | 100% | Completed
11 | 2020-11-16 | SONIA | MS Access Program Issue fix | 50% | WIP
12 | 2020-11-17 | SONIA | MS Access Program Issue fix | 100% | Completed
13 | 2020-11-18 | SONIA | Bic_Report_soukatsu | 50% | WIP
14 | 2020-11-19 | SONIA | Bic_Report_soukatsu | 100% | Completed
15 | 2020-11-20 | SONIA | Best_Report_Ivc | 50% | WIP
16 | 2020-11-23 | SONIA | Best_Report_Ivc | 100% | Completed
17 | 2020-11-24 | nMAVAR | nMAVAR Project issue | 100% | Completed
18 | 2020-11-25 | SONIA | Best_Report_Ivc Latest DB issue fixed | 100% | Completed
19 | 2020-11-26 | SONIA | Bic_Report_soukatsu Latest DB issue fixed | 100% | Completed
20 | 2020-11-27 | SONIA | Coordinate SONIA issue | 100% | Completed
30 | 2020-11-30 | SONIA | Best_Report_Ivc Latest DB Working | 100% | Completed

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | SONIA | Support SONIA Project | 100% | Completed
2 | 2020-12-01 | OTHER | Prepare issue and requirement document | 100% | Completed
3 | 2020-12-02 | SONIA | Best_Report_Ivc | 100% | Completed
4 | 2020-12-03 | SONIA | Bic_Report_soukatsu | 10% | WIP
5 | 2020-12-03 | SONIA | Discussion with japan team regarding Best_Report_Ivc & Bic_Report_Soukatsu | 20% | WIP
6 | 2020-12-04 | SONIA | Bic_Report_soukatsu | 30% | WIP
7 | 2020-12-07 | SONIA | Bic_Report_soukatsu | 40% | WIP
8 | 2020-12-08 | SONIA | Bic_Report_soukatsu | 50% | WIP
9 | 2020-12-09 | SONIA | Bic_Report_soukatsu | 60% | WIP
10 | 2020-12-10 | SONIA | Bic_Report_soukatsu | 70% | WIP
11 | 2020-12-11 | SONIA | Bic_Report_soukatsu | 80% | WIP
12 | 2020-12-14 | SONIA | Bic_Report_soukatsu | 90% | WIP
13 | 2020-12-15 | SONIA | Bic_Report_soukatsu | 100% | Completed
14 | 2020-12-16 | SONIA | Mr_Max_Import Issue worked | 100% | Completed
15 | 2020-12-16 | SONIA | STRM_Import issue working | 30% | WIP
16 | 2020-12-17 | SONIA | STRM_Import issue working | 100% | Completed
18 | 2020-12-18 | SONIA | Bic_Report_soukatsu issue fixed | 100% | Completed
19 | 2020-12-21 | SONIA | STRM_Import issue checking | 100% | Completed
20 | 2020-12-22 | SONIA | Performance issue checking MrMax_Import | 30% | WIP
21 | 2020-12-22 | Muji Store | refresh the application | 20% | WIP
22 | 2020-12-22 | SONIA | Functional issue informed elaya san in Bic_Report_soukatsu Project | 100% | Completed
23 | 2020-12-23 | Muji Store | refresh the application | 30% | WIP
24 | 2020-12-24 | Muji Store | refresh the application | 40% | WIP
25 | 2020-12-25 | Muji Store | refresh the application | 50% | WIP
26 | 2020-12-25 | Muji Store | KT Given to Entire team | 30% | WIP
27 | 2020-12-28 | SONIA | Testing issue | 50% | WIP
28 | 2020-12-29 | SONIA | Testing issue | 100% | Completed
29 | 2020-12-30 |  | Leave
30 | 2020-12-31 |  | Leave

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-04 | Muji Store | Issue fixing | 10% | WIP
2 | 2021-01-05 | General | GitHub source control | 30% | WIP
3 | 2021-01-06 | General | GitHub source control | 50% | WIP
4 | 2021-01-07 | Muji Store | Documentation | 30% | WIP
5 | 2021-01-08 | Muji Store | Documentation | 60% | WIP
6 | 2021-01-11 | Muji Store | Documentation | 100% | Completed
7 | 2021-01-12 | Muji Store | YouTube Private Video |  | WIP
8 | 2021-01-13 | Muji Store | YouTube Private Video |  | WIP
9 | 2021-01-18 | SONIA | Change request | 100% | Completed
10 | 2021-01-19 | Muji Store | YouTube Private Video |  | WIP | Unable create Private video list
11 | 2021-01-20 | SONIA | Bug fixing | 100% | Completed
12 | 2021-01-20 | Muji Store | Bug fixing | 100% | Completed
13 | 2021-01-21 | Muji Store | YouTube Private Video |  | WIP
14 | 2021-01-22 | Muji Store | YouTube Private Video |  | WIP
15 | 2021-01-25 | General | System HD,OS Software Update | 50% | WIP
16 | 2021-01-27 | General | System HD,OS Software Update | 100% | Completed
17 | 2021-01-29 | SONIA | Bug fixing | 100% | Completed

## FEB-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-02-01 | SONIA | Bug fixing | 100% | Completed
2 | 2021-02-02 | SONIA | Bug fixing | 100% | Completed
3 | 2021-02-03 | SONIA | Bug fixing | 100% | Completed
4 | 2021-02-04 | SONIA | Bug fixing | 100% | Completed
5 | 2021-02-05 | Muji Store | Issue fixing | 100% | Completed
6 | 2021-02-08 | NMVAR | Bug fixing | 100% | Completed
7 | 2021-02-08 | Muji Store | Functional checking | 10% | WIP
8 | 2021-02-09 | Muji Store | Functional checking | 40% | WIP
9 | 2021-02-10 | Muji Store | Functional checking | 70% | WIP
10 | 2021-02-11 | Muji Store | Google drive |  | WIP
11 | 2021-02-12 | Muji Store | Google drive |  | WIP
12 | 2021-02-15 | Muji Store | Google drive |  | WIP
13 | 2021-02-16 | Muji Store | Google drive |  | WIP
14 | 2021-02-17 | Muji Store | Google drive |  | WIP | Able to login and google drive files
15 | 2021-02-18 | NMVAR | Active Report checking | 50% | WIP
16 | 2021-02-19 | NMVAR | Active Report checking | 100% | Completed
17 | 2021-02-22 | SONIA | MrMax_Wrn | 100% | Completed | New Request
18 | 2021-02-23 | QMVAR | Weekly Revenue | 100% | Completed
19 | 2021-02-24 | SONIA | MrMax_Wrn | 100% | Completed
20 | 2021-02-24 | QMVAR | Weekly Revenue | 30% | WIP
21 | 2021-02-25 | QMVAR | Weekly Revenue | 100% | Completed
22 | 2021-02-25 | Muji Store | Code Merge and Deployment | 100% | Completed
23 | 2021-02-26 | Muji Store | Bug fixing | 100% | Completed

## MAR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-03-01 | Muji Store | Issue fixing and Deployment | 100% | Completed
2 | 2021-03-02 | Muji Store | App and DB clean up Demo3 | 100% | Completed
3 | 2021-03-03 | Muji Store | Testing and Documentation | 30% | WIP
4 | 2021-03-04 | Muji Store | Testing and Documentation | 60% | WIP
5 | 2021-03-05 | Muji Store | Testing and Documentation | 100% | Completed
6 | 2021-03-08 | SONIA | MrMax_Wrn | 100% | Completed | New Request
7 | 2021-03-08 | Muji Store | Bug fixing | 100% | Completed
8 | 2021-03-09 | Muji Store | Bug fixing | 100% | Completed
9 | 2021-03-09 | Muji Store | Application and database clean up | 100% | Completed
10 | 2021-03-10 | Muji Store | Admin page documentation | 20% | WIP
11 | 2021-03-10 | Muji Store | Attend Japan team meeting | 100% | Completed
12 | 2021-03-11 | Muji Store | Admin page documentation | 30% | WIP
13 | 2021-03-12 | Muji Store | Admin page documentation | 60% | WIP
14 | 2021-03-15 | Muji Store | Admin page documentation | 100% | Completed
15 | 2021-03-16 | Muji Store | New changes & Bug Fixing |  | WIP
16 | 2021-03-17 | Muji Store | New changes & Bug Fixing |  | WIP
17 | 2021-03-18 | Muji Store | New changes & Bug Fixing |  | WIP
18 | 2021-03-19 | Muji Store | New changes & Bug Fixing |  | WIP
19 | 2021-03-22 | Muji Store | New changes & Bug Fixing |  | WIP
20 | 2021-03-23 | Muji Store | New changes & Bug Fixing |  | WIP
21 | 2021-03-24 | Muji Store | New changes & Bug Fixing |  | WIP
22 | 2021-03-25 | Muji Store | New changes & Bug Fixing |  | WIP
23 | 2021-03-26 | Muji Store | New changes & Bug Fixing |  | WIP
24 | 2021-03-29 | Muji Store | New changes & Bug Fixing |  | WIP
25 | 2021-03-30 | Muji Store | New changes & Bug Fixing |  | WIP
26 | 2021-03-31 | SOINA | Homac Project New Changes (Homac,Homac_Search,Homac_Import) | 30% | WIP

## APR-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-04-01 | SOINA | Homac Project New Changes (Homac,Homac_Search,Homac_Import) | 60% | WIP
2 | 2021-03-02 | SOINA | Homac Project New Changes (Homac,Homac_Search,Homac_Import) | 100% | Completed
3 | 2021-03-05 | SOINA | Homac Project New Changes (Homac_Search) | 100% | Completed
4 | 2021-03-05 | Muji Store | Japanese file name error correction | 100% | Completed
5 | 2021-03-07 | Muji Store | Folder management screen - Tree structure view |  | WIP
6 | 2021-03-08 | Muji Store | Folder management screen - Tree structure view |  | WIP
7 | 2021-03-09 | Muji Store | Folder management screen - Tree structure view |  | WIP
8 | 2021-03-12 | Muji Store | Folder management screen - Tree structure view |  | WIP
9 | 2021-03-13 | Muji Store | Folder management screen - Tree structure view | 100% | Completed
10 | 2021-03-14 | Muji Store | Muji Store issue fixing
11 | 2021-03-15 | Muji Store | Muji Store issue fixing
12 | 2021-03-16 | NMVAR | Issue fixing in Reports
13 | 2021-03-19 | Muji Store | Folder Tree structure - Index page
14 | 2021-03-20 | Muji Store | Folder Tree structure - Index page
15 | 2021-03-21 | Muji Store | Muji Store issue fixing
16 | 2021-03-22 | Muji Store | Muji Store issue fixing
17 | 2021-03-23 | Muji Store | Muji Store issue fixing
18 | 2021-03-23 | NMVAR | Issue fixing in Reports - checking
19 | 2021-03-26 | Muji Store | Muji Store issue fixing
20 | 2021-03-27 |  | Sick Leave
21 | 2021-03-28 | Muji Store | Muji Store issue fixing
22 | 2021-03-29 | Muji Store | Folder Tree structure - Index page
23 | 2021-03-30 | Muji Store | Folder Tree structure - Index page
24
25
26

## MAY-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-05-03 | Muji Store | Bug Fixing | 100% | Completed
2 | 2021-05-04 | Muji Store | Bug Fixing | 100% | Completed
3 | 2021-05-05 | Muji Store | Bug Fixing | 100% | Completed
4 | 2021-05-06 | Muji Store | Stream Server Import | 20% | WIP
5 | 2021-05-07 | Muji Store | Leave |  | WIP
6 | 2021-05-10 | Muji Store | Stream Server Import | 40% | WIP
7 | 2021-05-11 | Muji Store | Stream Server Import | 60% | WIP
8 | 2021-05-12 | Muji Store | Stream Server Import | 80% | WIP | Additional Three table Added
9 | 2021-05-13 | Muji Store | Stream Server Import | 100% | Completed | Additional Three table Added
10 | 2021-05-17 | Muji Store | Bug Fixing | 100% | Completed
11 | 2021-05-18 | Muji Store | Bug Fixing | 100% | Completed
12 | 2021-05-19 | Muji Store | Bug Fixing | 100% | Completed
13 | 2021-05-20 | Muji Store | Bug Fixing | 100% | Completed
14 | 2021-05-21 | Muji Store | Analyze Japan team requirement, Prepare Estimation and requirement Document | 100% | Completed
15 | 2021-05-24 | Muji Store | Anyone can see any video if the ip address is registered under subnet mgt | 70% | WIP
16 | 2021-05-25 | Muji Store | Anyone can see any video if the ip address is registered under subnet mgt | 100% | Completed
17 | 2021-05-25 | Muji Store | map the entire things (store, store group, ip address, server and video) based on FOLDER | 20% | WIP
18 | 2021-05-26 | Muji Store | map the entire things (store, store group, ip address, server and video) based on FOLDER | 50% | WIP
19 | 2021-05-27 | Muji Store | map the entire things (store, store group, ip address, server and video) based on FOLDER | 90% | WIP
20 | 2021-05-28 | Muji Store | map the entire things (store, store group, ip address, server and video) based on FOLDER | 100% | WIP
21 | 2021-05-28 | Muji Store | Support Team Members | 100% | Completed
22 | 2021-05-31 | Muji Store | Bug Fixing |  | WIP
22 | 2021-05-31 | Muji Store | Store Number Add in Store Master table | 30% | WIP

## JUN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-06-01 | Muji Store | Store Number Add in Store Master table | 100% | Completed
2 | 2021-06-02 | Muji Store | Stream Server Import Add Store Number | 100% | Completed
3 | 2021-06-03 | Muji Store | Bug Fixing | 100% | Completed
4 | 2021-06-04 | Muji Store | Bug Fixing | 100% | Completed
5 | 2021-06-07 | Muji Store | Bug Fixing | 100% | Completed
6 | 2021-06-08 | Muji Store | Bug Fixing | 100% | Completed
7 | 2021-06-09 | Muji Store | Bug Fixing | 100% | Completed
8 | 2021-06-10 | Muji Store | Subnet Number changes | 30% | WIP
9 | 2021-06-11 | Muji Store | Subnet Number changes | 60% | WIP
10 | 2021-06-14 | Muji Store | Subnet Number changes | 100% | Completed
11 | 2021-06-15 | Muji Store | Without Logout able see video update session information | 40% | WIP
12 | 2021-06-15 | Muji Store | Convert Int16 to Int32 Entire Application | 100% | Completed
12 | 2021-06-16 | Muji Store | Without Logout able see video update session information | 100% | Completed
13 | 2021-06-17 | Muji Store | Old source code go through | 100% | Completed
14 | 2021-06-18 | Muji Store | Estimation for new changes with old souce finding functional issues | 100% | Completed
15 | 2021-06-21 | Muji Store | Folder Management | 20% | WIP
16 | 2021-06-22 | Muji Store | Folder Management | 40% | WIP
17 | 2021-06-23 | Muji Store | Folder Management | 60% | WIP
18 | 2021-06-24 | Muji Store | Folder Management | 100% | Completed
19 | 2021-06-25 | Muji Store | Folder Management Bug fixing | 100% | Completed
20 | 2021-06-28 | Muji Store | Bug Fixing (Remove unwanted columns) | 100% | Completed
21 | 2021-06-29 | Muji Store | Bug Fixing (Remove unwanted columns) | 100% | Completed
22 | 2021-06-30 | Muji Store | Stream server import changes | 50% | WIP

## JUL-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-07-01 | Muji Store | Stream server import changes | 100% | Completed
2 | 2021-07-02 | Muji Store | Bug Fixing | 100% | Completed
3 | 2021-07-05 | Muji Store | Store group code review | 100% | Completed
4 | 2021-07-05 | Muji Store | CDN convert to local | 100% | Completed
5 | 2021-07-06 | Muji Store | Video all message - 読み込みエラー = Video not playing 配信の完了しているサーバーがありません。= Subnet not available or server not accessible - Completed Need to test | 100% | Completed
6 | 2021-07-06 | Muji Store | Feedback - IP Address displayed in writer name column | 100% | Completed
7 | 2021-07-06 | Muji Store | Stream Server Logs - Remove Server IP Address/Server Name column in Export or hide Export button | 100% | Completed
8 | 2021-07-06 | Muji Store | Stream Server Import - Change second line - All fields are mandatory | 100% | Completed
9 | 2021-07-07 | Muji Store | Code review for completed pages | 100% | Completed
10 | 2021-07-07 | Muji Store | Role Access for Stream server and view log | 50% | WIP
11 | 2021-07-08 | Muji Store | Role Access for Stream server and view log | 100% | Completed
12 | 2021-07-08 | Muji Store | Confirmation message issue fixed in Store,Subnet and Store group | 100% | Completed
13 | 2021-07-09 | Muji Store | Video change Request and Approval Existing Functionality Implemented | 100% | Completed
14 | 2021-07-12 | Muji Store | Bug Fixing | 100% | Completed
15 | 2021-07-13 | Muji Store | Code review for changes | 100% | Completed
16 | 2021-07-13 | Muji Store | Code review for Video change Approval Existing functional | 100% | Completed
17 | 2021-07-13 | Muji Store | Bug Fixing | 100% | Completed
18 | 2021-07-14 | Muji Store | Bug Fixing | 100% | Completed
19 | 2021-07-14 | Muji Store | Code Review | 100% | Completed
20 | 2021-07-15 | Muji Store | Muji Store Unknown Japanes issue fixed | 100% | Completed
21 | 2021-07-15 | Muji Store | Feedback issue without login issue fixed | 100% | Completed
22 | 2021-07-16 | Muji Store | User management - Video Change request user issues --Videos not listed in Video change request page --Search button showing two times and clear button missing --"Unable to update with thumbnail in video change request" message showing when clicking update button in Edit | 100% | Completed
23 | 2021-07-19 | Muji Store | Screen after login timeout.display login screen after time out. Do not allow access/login if the link is directly copy-pasted. http://153.153.161.67/ncrmujvideodemo2/Menus http://153.153.161.67/ncrmujvideodemo2/Menus/InfoMenus http://153.153.161.67/ncrmujvideodemo2/SubnetAll | 100% | Completed
24 | 2021-07-19 | Muji Store | TOP screen when accessed (1st attachment) The screen displayed when accessing the server is the following "Folder >> Table of Contents" screen, so please make it same. | 50% | WIP
25 | 2021-07-20 | Muji Store | TOP screen when accessed (1st attachment) The screen displayed when accessing the server is the following "Folder >> Table of Contents" screen, so please make it same. | 100% | Completed
26 | 2021-07-21 |  | HoliDay
27 | 2021-07-22 | Muji Store | On clicking Update button Server Error - 404 - File or directory not found. | 100% | Completed
28 | 2021-07-23 | Muji Store | Bug Fixing | 100% | Completed
29 | 2021-07-26 | MJA | Document and Frame Work | 30% | WIP
30 | 2021-07-27 | Muji Store | Media table changes | 30% | WIP
31 | 2021-07-27 | Muji Store | Media table changes | 100% | Completed
32 | 2021-07-28 | MJA | Angular JS learning | 20% | WIP
33 | 2021-07-28 | Muji Store | MujiStore DB Checking | 100% | Completed
34 | 2021-07-29 | Muji Store | MujiStore DB Migration | 50% | WIP
35 | 2021-07-30 | Muji Store | MujiStore DB Migration | 100% | Completed

## AUG-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-08-02 | Muji Store | Bug Fixing | 100% | Completed
2 | 2021-08-03 | Muji Store | Bug Fixing | 100% | Completed
3 | 2021-08-04 | Muji Store | PrePare Deployment for Web Server Enviornment | 50% | WIP
4 | 2021-08-05 | Muji Store | PrePare Deployment for Web Server Enviornment | 100% | Completed
5 | 2021-08-06 | Muji Store | Application Deployment in Client Place(NCR) | 100% | Completed
6 | 2021-08-09 | Muji Store | Bug Fixing | 100% | Completed
7 | 2021-08-10 | Muji Store | Bug Fixing | 100% | Completed
8 | 2021-08-11 | Muji Store | Bug Fixing | 100% | Completed
9 | 2021-08-12 | Muji Store | Application Deployment in Client Place(NCR) | 100% | Completed
10 | 2021-08-13 | MJA | Table Design | 30% | WIP
11 | 2021-08-16 | Muji Store | Video Resolution checking |  | WIP
12 | 2021-08-17 | Muji Store | Video Resolution checking |  | WIP
13 | 2021-08-18 | Muji Store | Video Resolution checking & working | 100% | Completed
14 | 2021-08-18 | Muji Store | Video Resolution working | 30% | WIP
15 | 2021-08-20 | Muji Store | Video Resolution working | 60% | WIP
16 | 2021-08-21 | Muji Store | Video Resolution working | 100% | Completed
17 | 2021-08-23 | Muji Store | Bug Fixing | 100% | Completed
18 | 2021-08-24 | Muji Store | Bug Fixing Deployment Document pack | 100% | Completed
19 | 2021-08-25 | Muji Store | Bug Fixing Deployment Document pack | 100% | Completed
20 | 2021-08-26 | MJA | Table Design |  | WIP
21 | 2021-08-27 | MJA | Server checking code walk thrrough |  | WIP
22 | 2021-08-30 | MJA | Server checking code walk thrrough |  | WIP
22 | 2021-08-31 | MJA | Application Hosting in Dev Server | 40% | WIP

## SEP-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-09-01 | MJA | Application Hosting in Dev Server | 80% | WIP
2 | 2021-09-02 | Muji Store | Application Hosting in Dev Server | 100% | Completed
3 | 2021-09-02 | Muji Store | MujiStore Application Clean up | 50% | WIP
4 | 2021-09-03 | Muji Store | Deployment ,KT from QMVAR changes and Deployment changes working | 20% | WIP
5 | 2021-09-04 | Muji Store | Deployment changes Working(Original Media, User Name and format Quality changes) | 70% | WIP
6 | 2021-09-05 | Muji Store | Deployment changes Working(Original Media, User Name and format Quality changes) | 100% | Completed
7 | 2021-09-06 | Muji Store | Deployment changes Working(Original Media, User Name and format Quality changes) | 100% | Completed
8 | 2021-09-07 | Muji Store | Video Quanlity Enhancement | 70% | WIP
9 | 2021-09-08 | Muji Store | Video Quanlity Enhancement and Deployment | 100% | Completed
10 | 2021-09-09 | QMVAR_V2 | DashBoard Changes | 20% | WIP
11 | 2021-09-10 | QMVAR_V2 | DashBoard Changes | 40% | WIP
12 | 2021-09-11 | QMVAR_V2 | DashBoard Changes | 60% | WIP
14 | 2021-09-13 | QMVAR_V2 | DashBoard Changes | 80% | WIP
15 | 2021-09-14 | QMVAR_V2 | DashBoard Changes | 100% | Completed
16 | 2021-09-15 | Muji Store | Code Cleanup | 20% | WIP
17 | 2021-09-16 | Muji Store | Code Cleanup | 60% | WIP
18 | 2021-09-17 | Muji Store | Code Cleanup & Application Hosting in Dev Server | 100% | Completed
19 | 2021-09-20 | Muji Store | testing and bug fixing | 40% | WIP
20 | 2021-09-21 | Muji Store | testing and bug fixing | 100% | Completed
21 | 2021-09-22 | Muji Store | Leave
22 | 2021-09-23 | Muji Store | Gone through folder tree structure | 50% | WIP
23 | 2021-09-24 | Muji Store | Gone through folder tree structure | 100% | Completed
24 | 2021-09-27 | Muji Store | Subnet changes | 25% | WIP
25 | 2021-09-28 | Muji Store | Subnet changes | 50% | WIP
26 | 2021-09-29 | Muji Store | Subnet changes | 75% | WIP
27 | 2021-09-30 | Muji Store | Subnet changes | 100% | Completed

## OCT-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-10-01 | Muji Store | Default Page Folder display using store group checking | 50% | WIP
2 | 2021-10-02 |  | Holiday
3 | 2021-10-03 |  | Holiday
4 | 2021-10-04 | Muji Store | Default Page Folder display using store group checking | 100% | Completed
5 | 2021-10-05 | Kaisokku | Frame work creation | 25% | WIP
6 | 2021-10-06 | Kaisokku | Frame work creation | 50% | WIP
7 | 2021-10-07 | Muji Store | Folder Structure option 5 working | 50% | WIP
8 | 2021-10-08 | Muji Store | Folder Structure option 5 working | 100% | Completed
9 | 2021-10-09 |  | Holiday
10 | 2021-10-10 |  | Holiday
11 | 2021-10-11 | Muji Store | Folder Structure option 1 working | 100% | Completed
12 | 2021-10-12 | Muji Store | Folder Structure option 6 working | 50% | WIP
14 | 2021-10-13 | Muji Store | Folder Structure option 6 working | 100% | Completed
15 | 2021-10-14 | Penna | API Call import and display data | 25% | WIP
16 | 2021-10-15 | Penna | API Call import and display data | 50% | WIP
17 | 2021-10-16 |  | Holiday
18 | 2021-10-17 |  | Holiday
19 | 2021-10-18 | Penna | API Call import and display data | 100% | Completed
20 | 2021-10-19 | Penna | API Call Integration | 100% | Completed
21 | 2021-10-20 | Kaisokku | Code Walk through | 25% | WIP
22 | 2021-10-21 | Kaisokku | Video Management | 10% | WIP
23 | 2021-10-21 | Penna | API Call Modification YREALIZATION | 25% | WIP
24 | 2021-10-22 |  | Leave
25 | 2021-10-23 |  | Holiday
26 | 2021-10-24 |  | Holiday
27 | 2021-10-25 | Kaisokku | Video Management | 25% | WIP
28 | 2021-10-26 | Kaisokku | Video Management | 50% | WIP
29 | 2021-10-27 | Penna | API New Request LOGI_COST Analyses
30 | 2021-10-27 | Kaisokku | Video Management | 75% | WIP
31 | 2021-10-28 | Kaisokku | Video Management | 100% | Completed
32 | 2021-10-29 |  | Leave
33 | 2021-10-30 |  | Holiday
34 | 2021-10-31 |  | Holiday

## NOV-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-11-01 | Penna | Web API Task | 50% | WIP
2 | 2021-11-02 | Penna | Web API Task | 100% | Completed
3 | 2021-11-03 | Kaisokku | Video Management issue fixing | 100% | Completed
4 | 2021-11-04 |  | Holiday - Deepavali
5 | 2021-11-05 | Muji Store | Subnet issue checking | 100% | Completed
6 | 2021-11-06 |  | Weekend
7 | 2021-11-07 |  | Weekend
8 | 2021-11-08 | Muji Store | Subnet issue woking | 30% | WIP
9 | 2021-11-09 | Muji Store | Subnet issue woking | 70% | WIP
10 | 2021-11-10 | Muji Store | Subnet issue woking | 100% | Completed
11 | 2021-11-11 | Kaisokku | Project Co ordinate | 100% | Completed
12 | 2021-11-12 | Penna | Web API Task | 30% | WIP
13 | 2021-11-13 |  | Weekend
14 | 2021-11-14 |  | Weekend
15 | 2021-11-15 |  | Leave
16 | 2021-11-16 | Penna | Web API Task | 70% | WIP
17 | 2021-11-17 | Penna | Web API Task | 100% | Completed
18 | 2021-11-18 |  | Leave
19 | 2021-11-19 | Kaisokku | Demo Link Videp Working | 30% | WIP
20 | 2021-11-20 |  | Weekend
21 | 2021-11-21 |  | Weekend
22 | 2021-11-22 | Kaisokku | Demo Link Videp Working | 60% | WIP
23 | 2021-11-23 |  | Leave
24 | 2021-11-24 | Kaisokku | Half day Leave / Demo Link Video working
25 | 2021-11-25 | Penna | Half day Leave / Web API Task
26 | 2021-11-26 | Kaisokku | Demo Link Video working
27 | 2021-11-27 |  | Weekend
28 | 2021-11-28 |  | Weekend
29 | 2021-11-29 |  | Leave
30 | 2021-11-30 | Kaisokku | Image Working
31 | 2021/11/31 | Kaisokku | Image Working

## DEC-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-12-01 | Kaisokku | Image Checking using FFMPEG | 50% | WIP
2 | 2021-12-02 |  | Leave
3 | 2021-12-03 | Kaisokku | Image Checking using FFMPEG | 100% | Completed
4 | 2021-12-04 |  | Holiday
5 | 2021-12-05 |  | Holiday
6 | 2021-12-06 | Penna | Middleware Working | 25% | WIP
7 | 2021-12-07 | Penna | Middleware Working | 50% | WIP
| 2021-12-07 | SOINA | Ms Access Application | 100% | Completed
8 | 2021-12-08 | Penna | Middleware Working | 75% | WIP
9 | 2021-12-09 |  | Leave
10 | 2021-12-10 | Penna | Middleware Working | 100% | Completed
11 | 2021-12-11 |  | Holiday
12 | 2021-12-12 |  | Holiday
14 | 2021-12-13 | Penna | Middleware Working | 50% | Completed
15 | 2021-12-14 | Muji Store | Store, Subnet, Store group issue woking | 25% | WIP
16 | 2021-12-15 | Muji Store | Store, Subnet, Store group issue woking | 70% | WIP
17 | 2021-12-16 | Muji Store | Store, Subnet, Store group issue woking | 100% | Completed
18 | 2021-12-17 | Penna | Middleware Working | 30% | WIP
19 | 2021-12-18 |  | Holiday
20 | 2021-12-19 |  | Holiday
21 | 2021-12-20 | Penna | Middleware Working | 60% | WIP
22 | 2021-12-21 | Penna | Middleware Working | 100% | Completed
23 | 2021-12-22 | expirationnotice | Database Migration | 30% | WIP
24 | 2021-12-23 | expirationnotice | Database Migration | 60% | WIP
25 | 2021-12-23 | Penna | Read only user created | 100% | Completed
26 | 2021-12-24 | expirationnotice | Database Migration | 100% | Completed
27 | 2021-12-25 |  | Holiday
28 | 2021-12-26 |  | Holiday
29 | 2021-12-27 | expirationnotice | Search page | 0% | WIP
30 | 2021-12-27 | Penna | One more IP Address added in existing Read only user | 100% | Completed
31 | 2021-12-28 | expirationnotice | Reports |  | WIP
32 | 2021-12-29 | expirationnotice | Reports |  | WIP
33 | 2021-12-30 | expirationnotice | Reports |  | WIP
34 | 2021-12-31 | expirationnotice | Reports |  | WIP

## JAN-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-01-01 |  | HoliDay
2 | 2022-01-02 |  | HoliDay
3 | 2022-01-03 | expirationnotice | Reports | WIP
4 | 2022-01-04 | expirationnotice | Reports | WIP
5 | 2022-01-05 | expirationnotice | Reports | WIP
6 | 2022-01-06 | expirationnotice | Reports | WIP
7 | 2022-01-07 | expirationnotice | Reports | WIP
8 | 2022-01-08 |  | HoliDay
9 | 2022-01-09 |  | HoliDay
10 | 2022-01-10 | expirationnotice | Reports | WIP
11 | 2022-01-10 | Penna | Scheduler issue
12 | 2022-01-11 | expirationnotice | Reports | Completed |  | 1 Report completed
13 | 2022-01-11 | Penna | Scheduler issue
14 | 2022-01-12 | expirationnotice | Reports | Completed |  | 2nd Report completed
15 | 2022-01-13 | expirationnotice | Reports | WIP
16 | 2022-01-14 |  | HoliDay(Pongal)
17 | 2022-01-15 |  | HoliDay
18 | 2022-01-16 |  | HoliDay
19 | 2022-01-17 | expirationnotice | Reports | Completed |  | 3rd Report completed
20 | 2022-01-18 |  | HoliDay(Thaipoosam)
21 | 2022-01-19 | expirationnotice | Reports | WIP
22 | 2022-01-20 |  | Leave(PL)
23 | 2022-01-21 | expirationnotice | Reports | WIP
24 | 2022-01-22 |  | HoliDay
25 | 2022-01-23 | expirationnotice | HoliDay | Completed |  | 4th Report & English conversion completed
26 | 2022-01-24 | Penna MiddleWare |  | WIP
27 | 2022-01-25 | Penna MiddleWare |  | WIP
28 | 2022-01-26 |  | HoliDay(Republic Day)
29 | 2022-01-27 | Penna MiddleWare |  | WIP
30 | 2022-01-28 | Penna MiddleWare |  | Completed
31 | 2022-01-29 |  | HoliDay
32 | 2022-01-30 |  | HoliDay
33 | 2022-01-31 | expirationnotice |  | WIP

## FEB-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-02-01 | expirationnotice | Database user create and access | 30% | WIP
2 | 2022-02-02 | expirationnotice | Database user create and access | 60% | WIP
3 | 2022-02-03 | expirationnotice | Database user create and access | 100% | Completed
4 | 2022-02-04 | YAARAA-Reverpro | Query changes | 100% | Completed
5 | 2022-02-05 |  | Holiday
6 | 2022-02-06 |  | Holiday
7 | 2022-02-07 | Penna Scheduler | Log Changes | 50% | WIP
8 | 2022-02-08 | Penna Scheduler | Log Changes | 100% | Completed
9 | 2022-02-09 | expirationnotice | Report issue | 50% | WIP
10 | 2022-02-10 | expirationnotice | Report issue | 100% | Completed
11 | 2022-02-10 | Penna Scheduler | Log Changes(Scheduler days split) | 50% | WIP
12 | 2022-02-11 | Penna Scheduler | Log Changes(Scheduler days split) | 100% | Completed
13 | 2022-02-12 |  | Holiday
14 | 2022-02-13 |  | Holiday
15 | 2022-02-14 | YAARAA-Reverpro | Dashboard Query | 25% | WIP
16 | 2022-02-15 | YAARAA-Reverpro | Dashboard Query | 50% | WIP
17 | 2022-02-16 | YAARAA-Reverpro | Dashboard Query | 75% | WIP
18 | 2022-02-17 | YAARAA-Reverpro | Dashboard Query | 100% | Completed
19 | 2022-02-18 | expirationnotice | Mysql Setup | 25% | WIP
20 | 2022-02-19 |  | Holiday
21 | 2022-02-20 |  | Holiday
22 | 2022-02-21 | expirationnotice | Mysql Setup | 50% | WIP
23 | 2022-02-22 | YAARAA-Reverpro | Dashboard Query (Change Request) | 100% | Completed
24 | 2022-02-23 | YAARAA-Reverpro | Dashboard Query (Change Request) | 100% | Completed
25 | 2022-02-24 | Penna Scheduler | Change Request | 100% | Completed
26 | 2022-02-25 | Loft | Image Process |  | WIP
27 | 2022-02-26 |  | Holiday
28 | 2022-02-27 |  | Holiday
29 | 2022-02-28 | Loft | Image Process |  | WIP
30 | 2022-03-01
31 | 2022-03-02
32 | 2022-03-03
33 | 2022-03-04
34 | 2022-03-05

## MAR-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-03-01 | OBIC_HW | Learning | 10% | WIP
2 | 2022-03-01 | expirationnotice | DLL creation | 100% | Completed
3 | 2022-03-02 | OBIC_HW | Learning | 20% | WIP
4 | 2022-03-03 | OBIC_HW | Learning | 40% | WIP
5 | 2022-03-04 | YAARAA-Reverpro | Dash board Query | 10% | WIP
6 | 2022-03-05 |  | Holiday
7 | 2022-03-06 |  | Holiday
8 | 2022-03-07 | OBIC_HW | New Chages working | 25% | WIP
9 | 2022-03-08 | OBIC_HW | New Chages working | 50% | WIP
10 | 2022-03-09 | OBIC_HW | New Chages working | 75% | WIP
11 | 2022-03-10 | OBIC_HW | New Chages working | 100% | Completed
12 | 2022-03-11 | YAARAA-Reverpro | Dash board Query | 20% | WIP
13 | 2022-03-12 |  | Holiday
14 | 2022-03-13 |  | Holiday
15 | 2022-03-14 | YAARAA-Reverpro | Dash board Query | 50% | WIP
16 | 2022-03-15 | OBIC_HW | New Chages working Partial search | 50% | WIP
17 | 2022-03-16 | OBIC_HW | New Chages working Partial search | 100% | Completed
18 | 2022-03-17 | YAARAA-Reverpro | Dash board Query | 100% | Completed
19 | 2022-03-18 | OBIC_HW | New Chages working Partial search with out space | 100% | Completed
20 | 2022-03-19 |  | Holiday
21 | 2022-03-20 |  | Holiday
22 | 2022-03-21 | OBIC_HW | New Chages working Partial search with out space | 100% | Completed
23 | 2022-03-21 | YAARAA-Reverpro | Dash board Query | 100% | Completed
24 | 2022-03-22 | OBIC_HW | New Chages working | 100% | Completed
25 | 2022-03-22 | YAARAA-Reverpro | Warrenty Query | 50% | WIP
26 | 2022-03-22 | QMVAR | Service order pending Engineering assigned Query | 50% | WIP
27 | 2022-03-23 | YAARAA-Reverpro | Warrenty Query | 100% | Completed
28 | 2022-03-23 | QMVAR | Service order pending Engineering assigned Query | 100% | Completed
29 | 2022-03-24 |  | Leave
30 | 2022-03-25 | Penna MRP | Frame work | 50% | WIP
31 | 2022-03-26 |  | Holiday
32 | 2022-03-27 |  | Holiday
33 | 2022-03-28 | Penna MRP | Frame work | 100% | Completed
34 | 2022-03-29 | Penna MRP | Database | 100% | Completed
35 | 2022-03-29 |  | Anguaar JS Learning - Angular Topics | 20% | WIP
36 | 2022-03-30 | YAARAA-Reverpro | Dash board Query | 100% | Completed
37 | 2022-03-31 | expirationnotice | Import Issue | 30% | WIP
38 | 2022-03-31 | YAARAA-Reverpro | Dash board Query | 100% | Completed

## APR-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-04-01 | expirationnotice | Import Issue | 50% | WIP
2 | 2022-04-02 |  | Holiday
3 | 2022-04-03 |  | Holiday
4 | 2022-04-04 | expirationnotice | Import Issue & Performance issue | 80% | WIP
5 | 2022-04-05 | expirationnotice | Import Issue & Performance issue | 100% | Completed
| 2022-04-05 | Penna MRP | Package Import | 10% | WIP
6 | 2022-04-06 |  | AngularJs Training
7 | 2022-04-07 |  | AngularJs Training
8 | 2022-04-08 |  | AngularJs Training
9 | 2022-04-09 |  | Holiday
10 | 2022-04-10 |  | Holiday
11 | 2022-04-11 |  | AngularJs Training
12 | 2022-04-12 |  | AngularJs Training
13 | 2022-04-13 |  | AngularJs Training
14 | 2022-04-14 |  | Tamil New Year Holiday
15 | 2022-04-15 |  | Good Friday Holiday
16 | 2022-04-16 |  | Holiday
17 | 2022-04-17 |  | Holiday
18 | 2022-04-18 |  | AngularJs Training CRUD
19 | 2022-04-19 | expirationnotice | Report issue working | 50% | WIP
20 | 2022-04-19 |  | Linux Server checking
21 | 2022-04-20 | expirationnotice | Report issue working | 100% | Completed
22 | 2022-04-20 |  | Linux Server checking
23 | 2022-04-20 |  | AngularJs Training WebAPI
24 | 2022-04-21 |  | AngularJs Training WebAPI
25 | 2022-04-22 |  | AngularJs Training WebAPI
26 | 2022-04-23 |  | Holiday
27 | 2022-04-24 |  | Holiday
28 | 2022-04-25 |  | Linux Server checking
29 | 2022-04-26 |  | Linux Server checking
30 | 2022-04-27 | expirationnotice | Changes issue fixing
31 | 2022-04-28 | expirationnotice | Changes issue fixing
32 | 2022-04-29 | expirationnotice | Changes issue fixing
33 | 2022-04-30 |  | Holiday

## MAY-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-05-01 |  | Holiday
2 | 2022-05-02 | SolarWinds | Requirement understanding
3 | 2022-05-03 | SolarWinds | Requirement understanding
4 | 2022-05-04 | SolarWinds | Database creation | 20% | WIP
5 | 2022-05-05 | SolarWinds | Database creation | 50% | WIP
| 2022-05-06 | SolarWinds | Database creation | 100% | Completed
6 | 2022-05-07 |  | Holiday
7 | 2022-05-08 |  | Holiday
8 | 2022-05-09 | SolarWinds | Requirement understanding
9 | 2022-05-10 | SolarWinds | document create for clarification
10 | 2022-05-11 |  | Leave
11 | 2022-05-12 | SolarWinds | Framework
12 | 2022-05-13 | SolarWinds | Framework and KT from Suma San
13 | 2022-05-14 |  | Holiday
14 | 2022-05-15 |  | Holiday
15 | 2022-05-16 | SolarWinds | Design Document walkthrough
16 | 2022-05-17 | SolarWinds | Assign Task and some specific task
17 | 2022-05-18 | SolarWinds | Import Proto type create & co ordinate
18 | 2022-05-19 | SolarWinds | Import Proto type create & co ordinate
19 | 2022-05-20 | SolarWinds | Import Proto type create & co ordinate
20 | 2022-05-21 |  | Holiday
21 | 2022-05-22 |  | Holiday
22 | 2022-05-23 | SolarWinds | co ordinage give solution
23 | 2022-05-24 | SolarWinds | co ordinage give solution
24 | 2022-05-25 | SolarWinds | Co ordinate
25 | 2022-05-26 | SolarWinds | Co ordinate
26 | 2022-05-27 | SolarWinds | Co ordinate, Code Merge and deployment
27 | 2022-05-28 | SolarWinds | Co ordinate,testing and Issue fixing
28 | 2022-05-29 | SolarWinds | Co ordinate, Code Merge and deployment
29 | 2022-05-30 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
30 | 2022-05-31 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment

## JUN-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-06-01 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
2 | 2022-06-02 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
3 | 2022-06-03 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
4 | 2022-06-04 |  | Holiday
5 | 2022-06-05 |  | Holiday
| 2022-06-06 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
6 | 2022-06-07 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
7 | 2022-06-08 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
8 | 2022-06-09 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
9 | 2022-06-10 |  | Leave
10 | 2022-06-11 |  | Holiday
11 | 2022-06-12 |  | Holiday
12 | 2022-06-13 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
13 | 2022-06-14 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
14 | 2022-06-15 | SolarWinds | Co ordinate,testing, issue fixing, Code Merge and deployment
15 | 2022-06-16 | SolarWinds | User Name from windows login
16 | 2022-06-17 | SolarWinds | User Name from windows login
17 | 2022-06-18 |  | Holiday
18 | 2022-06-19 |  | Holiday
19 | 2022-06-20 | SolarWinds | User Name from windows login
20 | 2022-06-21 | SolarWinds | User Name from windows login
21 | 2022-06-22 | SolarWinds | User Name from windows login
22 | 2022-06-23 |  | Leave
23 | 2022-06-24 |  | Leave
24 | 2022-06-25 |  | Holiday
25 | 2022-06-26 |  | Holiday
26 | 2022-06-27 | SolarWinds | User Name from windows login
27 | 2022-06-28 | SolarWinds | User Name from windows login
28 | 2022-06-29 | SolarWinds | Issue fixing
29 | 2022-06-30 | SolarWinds | Issue fixing

## JUL-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-07-01 | SolarWinds | Email Modify Details
2 | 2022-07-02 |  | Holiday
3 | 2022-07-03 |  | Holiday
4 | 2022-07-04 | SolarWinds | Email Modify Details
5 | 2022-07-05 |  | AWS Cloud Angular Application Hosting
6 | 2022-07-06 |  | AWS Cloud Angular Application Hosting
7 | 2022-07-06 |  | AWS IAM User
8 | 2022-07-07 |  | AWS IAM User
9 | 2022-07-08 |  | AWS IAM User
10 | 2022-07-09 |  | Holiday
11 | 2022-07-10 |  | Holiday
12 | 2022-07-11 |  | AWS IAM User
13 | 2022-07-12 |  | AWS IAM User
14 | 2022-07-13 |  | AWS IAM User
15 | 2022-07-14 |  | AWS Corss PlatForm
16 | 2022-07-15 |  | AWS Corss PlatForm
17 | 2022-07-16 |  | Holiday
18 | 2022-07-17 |  | Holiday
19 | 2022-07-18 |  | AWS Corss PlatForm
20 | 2022-07-19 |  | AWS Corss PlatForm
21 | 2022-07-20 |  | Leave
22 | 2022-07-21 |  | AWS Corss PlatForm
23 | 2022-07-22 |  | AWS Corss PlatForm
24 | 2022-07-23 |  | Holiday
25 | 2022-07-24 |  | Holiday
26 | 2022-07-25 |  | AWS Corss PlatForm
27 | 2022-07-26 |  | AWS Corss PlatForm
28 | 2022-07-27 |  | AWS Corss PlatForm
29 | 2022-07-28 |  | AWS Corss PlatForm
30 | 2022-07-29 |  | AWS Corss PlatForm
31 | 2022-07-30 |  | Holiday
32 | 2022-07-31 |  | Holiday

## AUG-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-08-01 |  | AWS Corss PlatForm
2 | 2022-08-02 |  | AWS Corss PlatForm
3 | 2022-08-03 |  | AWS Corss PlatForm
4 | 2022-08-04 |  | AWS Corss PlatForm
5 | 2022-08-05 |  | HRMS Application
6 | 2022-08-06 |  | Holiday
7 | 2022-08-07 |  | Holiday
8 | 2022-08-08 |  | HRMS Application
9 | 2022-08-09 |  | Penna Middleware
10 | 2022-08-10 |  | Leave
11 | 2022-08-11 |  | Leave
12 | 2022-08-12 |  | Doctor Visit Application
13 | 2022-08-13 |  | Holiday
14 | 2022-08-14 |  | Holiday
15 | 2022-08-15 |  | Penna Middleware
16 | 2022-08-16 |  | Penna Middleware
17 | 2022-08-17 |  | Penna Middleware
18 | 2022-08-18 |  | Leave
19 | 2022-08-19 |  | Penna Middleware
20 | 2022-08-20 |  | Holiday
21 | 2022-08-21 |  | Holiday
22 | 2022-08-22 |  | Penna Middleware
23 | 2022-08-23 |  | NextJS
24 | 2022-08-24 |  | NextJS
25 | 2022-08-25 |  | Penna Middleware
26 | 2022-08-26 |  | NextJS
27 | 2022-08-27 |  | Holiday
28 | 2022-08-28 |  | Holiday
29 | 2022-08-29 |  | Penna Scheduler
30 | 2022-08-30 |  | Penna Scheduler
31 | 2022-08-31 |  | Holiday

## SEP-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-09-01 |  | Leave
2 | 2022-09-02 |  | Penna Scheduler
3 | 2022-09-03 |  | Holiday
4 | 2022-09-04 |  | Holiday
5 | 2022-09-05 |  | NextJS
6 | 2022-09-06 |  | NextJS
7 | 2022-09-07 |  | Penna Scheduler
8 | 2022-09-08 |  | Penna Scheduler
9 | 2022-09-09 |  | Leave
10 | 2022-09-10 |  | Holiday
11 | 2022-09-11 |  | Holiday
12 | 2022-09-12 |  | Clearinghouse Database Rewrite Project
13 | 2022-09-13 |  | Clearinghouse Database Rewrite Project
14 | 2022-09-14 |  | Production control system
15 | 2022-09-15 |  | Penna Scheduler
16 | 2022-09-16 |  | MJA - Performance issue
17 | 2022-09-17 |  | MJA - Performance issue
18 | 2022-09-18 |  | Holiday
19 | 2022-09-19 |  | Holiday
20 | 2022-09-20 |  | MJA - Performance issue
21 | 2022-09-21 |  | MJA - RPA Scripts
22 | 2022-09-22 |  | MJA - RPA Scripts
23 | 2022-09-23 |  | MJA - RPA Scripts
24 | 2022-09-24 |  | Holiday
25 | 2022-09-25 |  | Holiday
26 | 2022-09-26 |  | Penna - StateWise OSOD Details
27 | 2022-09-27 |  | MJA - Query optimization
28 | 2022-09-27 |  | Clearinghouse Database Rewrite Project
29 | 2022-09-28 |  | Clearinghouse Database Rewrite Project
30 | 2022-09-29 |  | MJA - Query optimization
31 | 2022-09-30 |  | Penna - DashBoard

## OCT-2022
No | Date | Application | Task | % of completion | Status | Comments
1 | 2022-10-01 |  | Holiday
2 | 2022-10-02 |  | Holiday
3 | 2022-10-03 |  | Penna - DashBoard
4 | 2022-10-04 |  | Holiday
5 | 2022-10-05 |  | Holiday
6 | 2022-10-06 |  | Penna - Scheduler
7 | 2022-10-07 |  | Penna - Scheduler
8 | 2022-10-08 |  | Holiday
9 | 2022-10-09 |  | Holiday
10 | 2022-10-10 |  | SolarWinds PM Excel walk through
11 | 2022-10-10 |  | Penna - Scheduler
12 | 2022-10-11 |  | SolarWinds PM Excel walk through
13 | 2022-10-12 |  | SolarWinds PM Excel walk through, Discussion with Japan team
14 | 2022-10-12 |  | MJA Image Upload Discussion
15 | 2022-10-13 |  | SolarWinds PM Excel walk through
16 | 2022-10-14 |  | Penna - Scheduler
17 | 2022-10-15 |  | Holiday
18 | 2022-10-16 |  | Holiday
19 | 2022-10-17 |  | Penna - Scheduler
20 | 2022-10-18 |  | SolarWinds PM Excel walk through
21 | 2022-10-19 |  | SolarWinds PM Excel walk through
22 | 2022-10-20 |  | Penna - Scheduler
23 | 2022-10-21 |  | Penna - Scheduler
24 | 2022-10-22 |  | Holiday
25 | 2022-10-23 |  | Holiday
26 | 2022-10-24 |  | Holiday
27 | 2022-10-25 |  | Penna - Scheduler
28 | 2022-10-26 |  | Penna MRP Print issue
29 | 2022-10-27 |  | Penna - Scheduler
30 | 2022-10-28 |  | Penna - Scheduler
31 | 2022-10-29 |  | Holiday
32 | 2022-10-30 |  | Holiday
33 | 2022-10-31 |  | Penna - Scheduler

## Leave Details
Date | Reason | Type
20/01/2022 | puberty ceremony function | CL
24/03/2022 | Tirupati | CL
11/05/2022 | Passport Office | CL
10/06/2022 | Tirupati | CL
23/06/2022 | Home town festival | CL
24/06/2022 | Home town festival | CL
20/07/2022 | Sick Leave | ML
10/08/2022 | Sick Leave | ML
11/08/2022 | Sick Leave | ML
18/08/2022 | Sick Leave | ML
01/09/2022 | Relative marriage | CL
09/09/2022 | Monisha Marriage | CL