## OCT-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-10-01 | VASTU | Checking date time issue | 100% | Completed
2 | 2020-10-01 | RPA Dotnet | Project set up | 100% | Completed
3 | 2020-10-05 | QMVAR | DRS Count - Saw Discount changes and Issue | 100% | Completed
4 | 2020-10-06 | QMVAR | DRS Count - Saw Discount Summary & Details | 50% | WIP
5 | 2020-10-07 | QMVAR | DRS - Daily Revenue | 20% | WIP
6 | 2020-10-08 | QMVAR | DRS - Daily Revenue | 40% | WIP
7 | 2020-10-09 | QMVAR | DRS - Daily Revenue | 50% | WIP
8 | 2020-10-12 | QMVAR | DRS - Daily Revenue | 65% | WIP
9 | 2020-10-13 | QMVAR | DRS - Daily Revenue | 80% | WIP
10 | 2020-10-14 | QMVAR | DRS - Daily Revenue | 100% | Completed
15 | 2020-10-15 | SONIA | Go through Soica Project MDB File Application | 100% | Completed
16 | 2020-10-16 | SONIA | Check Suma Email and Start work application | 10% | WIP
17 | 2020-10-19 | SONIA | Access DB Migration - BIC CAMERA - 1 | 10% | WIP
18 | 2020-10-20 | SONIA | Access DB Migration - BIC CAMERA - 1 | 30% | WIP
19 | 2020-10-21 | SONIA | Access DB Migration - BIC CAMERA - 1 | 50% | WIP
20 | 2020-10-22 | SONIA | Access DB Migration - BIC CAMERA - 1 | 60% | WIP
21 | 2020-10-23 | SONIA | Access DB Migration - BIC CAMERA - 1 | 70% | WIP
22 | 2020-10-27 | SONIA | Access DB Migration - BIC CAMERA - 1 | 85% | WIP
23 | 2020-10-28 | SONIA | Access DB Migration - BIC CAMERA - 1 | 100% | Completed
24 | 2020-10-29 | SONIA | Analyze DB Migration for without Form DB
25 | 2020-10-29 | QMVAR | Help Balaji San for PL Tracking Sheet SONY
Status
WIP
Pending
Completed
Hold

## NOV-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-11-02 | SONIA | Changes completed in Bic_Report_soukatsu Project | 100% | Completed
2 | 2020-11-03 | SONIA | Set up file created for BIC CAMERA Module | 100% | Completed
3 | 2020-11-04 | SONIA | Analysis Bic Report Ivc | 100% | Completed
4 | 2020-11-05 | SONIA | Working Bic Report Ivc | 10% | WIP
5 | 2020-11-06 | SONIA | Working Bic Report Ivc | 20% | WIP
6 | 2020-11-09 | SONIA | Working Bic Report Ivc | 30% | WIP
7 | 2020-11-10 | SONIA | Working Bic Report Ivc | 40% | WIP
8 | 2020-11-11 | SONIA | Working Bic Report Ivc | 60% | WIP
9 | 2020-11-12 | SONIA | Working Bic Report Ivc | 80% | WIP
10 | 2020-11-13 | SONIA | Working Bic Report Ivc | 100% | Completed
11 | 2020-11-16 | SONIA | MS Access Program Issue fix | 50% | WIP
12 | 2020-11-17 | SONIA | MS Access Program Issue fix | 100% | Completed
13 | 2020-11-18 | SONIA | Bic_Report_soukatsu | 50% | WIP
14 | 2020-11-19 | SONIA | Bic_Report_soukatsu | 100% | Completed
15 | 2020-11-20 | SONIA | Best_Report_Ivc | 50% | WIP
16 | 2020-11-23 | SONIA | Best_Report_Ivc | 100% | Completed
17 | 2020-11-24 | nMAVAR | nMAVAR Project issue | 100% | Completed
18 | 2020-11-25 | SONIA | Best_Report_Ivc Latest DB issue fixed | 100% | Completed
19 | 2020-11-26 | SONIA | Bic_Report_soukatsu Latest DB issue fixed | 100% | Completed
20 | 2020-11-27 | SONIA | Coordinate SONIA issue | 100% | Completed
30 | 2020-11-30 | SONIA | Best_Report_Ivc Latest DB Working | 100% | Completed

## DEC-2020
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-12-01 | SONIA | Support SONIA Project | 100% | Completed
2 | 2020-12-01 | OTHER | Prepare issue and requirement document | 100% | Completed
3 | 2020-12-02 | SONIA | Best_Report_Ivc | 100% | Completed
4 | 2020-12-03 | SONIA | Bic_Report_soukatsu | 10% | WIP
5 | 2020-12-03 | SONIA | Discussion with japan team regarding Best_Report_Ivc & Bic_Report_Soukatsu | 20% | WIP
6 | 2020-12-04 | SONIA | Bic_Report_soukatsu | 30% | WIP
7 | 2020-12-07 | SONIA | Bic_Report_soukatsu | 40% | WIP
8 | 2020-12-08 | SONIA | Bic_Report_soukatsu | 50% | WIP
9 | 2020-12-09 | SONIA | Bic_Report_soukatsu | 60% | WIP
10 | 2020-12-10 | SONIA | Bic_Report_soukatsu | 70% | WIP
11 | 2020-12-11 | SONIA | Bic_Report_soukatsu | 80% | WIP
12 | 2020-12-14 | SONIA | Bic_Report_soukatsu | 90% | WIP
13 | 2020-12-15 | SONIA | Bic_Report_soukatsu | 100% | Completed
14 | 2020-12-16 | SONIA | Mr_Max_Import Issue worked | 100% | Completed
15 | 2020-12-16 | SONIA | STRM_Import issue working | 30% | WIP
16 | 2020-12-17 | SONIA | STRM_Import issue working | 100% | Completed
18 | 2020-12-18 | SONIA | Bic_Report_soukatsu issue fixed | 100% | Completed
19 | 2020-12-21 | SONIA | STRM_Import issue checking | 100% | Completed
20 | 2020-12-22 | SONIA | Performance issue checking MrMax_Import | 30% | WIP
21 | 2020-12-22 | Muji Store | refresh the application | 20% | WIP
22 | 2020-12-22 | SONIA | Functional issue informed elaya san in Bic_Report_soukatsu Project | 100% | Completed
23 | 2020-12-23 | Muji Store | refresh the application | 30% | WIP
24 | 2020-12-24 | Muji Store | refresh the application | 40% | WIP
25 | 2020-12-25 | Muji Store | refresh the application | 50% | WIP
26 | 2020-12-25 | Muji Store | KT Given to Entire team | 30% | WIP
27 | 2020-12-28 | SONIA | Testing issue | 50% | WIP
28 | 2020-12-29 | SONIA | Testing issue | 100% | Completed
29 | 2020-12-30 |  | Leave
30 | 2020-12-31 |  | Leave

## JAN-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-01-04 | Muji Store | Issue fixing | 10% | WIP
2 | 2021-01-05 | General | GitHub source control | 30% | WIP
3 | 2021-01-06 | General | GitHub source control | 50% | WIP
4 | 2021-01-07 | Muji Store | Documentation | 30% | WIP
5 | 2021-01-08 | Muji Store | Documentation | 60% | WIP
6 | 2021-01-11 | Muji Store | Documentation | 100% | Completed
7 | 2021-01-12 | Muji Store | YouTube Private Video |  | WIP
8 | 2021-01-13 | Muji Store | YouTube Private Video |  | WIP
9 | 2021-01-18 | SONIA | Change request | 100% | Completed
10 | 2021-01-19 | Muji Store | YouTube Private Video |  | WIP | Unable create Private video list
11 | 2021-01-20 | SONIA | Bug fixing | 100% | Completed
12 | 2021-01-20 | Muji Store | Bug fixing | 100% | Completed
13 | 2021-01-21 | Muji Store | YouTube Private Video |  | WIP
14 | 2021-01-22 | Muji Store | YouTube Private Video |  | WIP
15 | 2021-01-25 | General | System HD,OS Software Update | 50% | WIP
16 | 2021-01-27 | General | System HD,OS Software Update | 100% | Completed
17 | 2021-01-29 | SONIA | Bug fixing | 100% | Completed

## FEB-2021
No | Date | Application | Task | % of completion | Status | Comments
1 | 2021-02-01 | SONIA | Bug fixing | 100% | Completed
2 | 2021-02-02 | SONIA | Bug fixing | 100% | Completed
3 | 2021-02-03 | SONIA | Bug fixing | 100% | Completed
4 | 2021-02-04 | SONIA | Bug fixing | 100% | Completed
5 | 2021-02-05 | Muji Store | Issue fixing | 100% | Completed
6 | 2021-02-08 | NMVAR | Bug fixing | 100% | Completed
7 | 2021-02-08 | Muji Store | Functional checking | 10% | WIP
8 | 2021-02-09 | Muji Store | Functional checking | 40% | WIP
9 | 2021-02-10 | Muji Store | Functional checking | 70% | WIP
10 | 2021-02-11 | Muji Store | Google drive |  | WIP
11 | 2021-02-12 | Muji Store | Google drive |  | WIP
12 | 2021-02-15 | Muji Store | Google drive |  | WIP
13 | 2021-02-16 | Muji Store | Google drive |  | WIP
14 | 2021-02-17 | Muji Store | Google drive |  | WIP | Able to login and google drive files
15 | 2021-02-18 | NMVAR | Active Report checking | 50% | WIP
16 | 2021-02-19 | NMVAR | Active Report checking | 100% | Completed
17 | 2021-02-22 | SONIA | MrMax_Wrn | 100% | Completed | New Request
18 | 2021-02-23 | QMVAR | Weekly Revenue | 100% | Completed
19 | 2021-02-24 | SONIA | MrMax_Wrn | 100% | Completed
20 | 2021-02-24 | QMVAR | Weekly Revenue | 30% | WIP
21 | 2021-02-25 | QMVAR | Weekly Revenue | 100% | Completed
22 | 2021-02-25 | Muji Store | Code Merge and Deployment | 100% | Completed